## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0 | -1 | Leaves 2015-05-01 2015-05-25 I will need some leaves in APR/MAY on short notice
JS | Wednesday | 2015-04-01 | 8093 | 2.8_tests |  | 2.8 | Hotel | SQA tests between precache and prod | test + analysis | 3 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | 2.8 | Hotel | Make a list of quality control actions then tools to automate (JS+AF) | First discussion with Anne | 1 | 0 | -1
JS | Wednesday | 2015-04-01 |  | New | Documentation | 2.8 | Hotel | Describe usage +behavior of test tool EXP for DH |  | 1.5 | 0 | -1
JS | Wednesday | 2015-04-01 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 2 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | Afidium |  | Daily call |  | 0.25 | 0 | -1
JS | Wednesday | 2015-04-01 | 8586 | 2.8_tests |  | 2.8 | Hotel | Patch preparation + application | FTP patch update + test cleanup patch + apply . Wrote to CC on progress. + data check |  | 3.5 | 0
JS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25
JS | Thursday | 2015-04-02 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | tests + analysis | 2
JS | Thursday | 2015-04-02 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5
JS | Thursday | 2015-04-02 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5
JS | Thursday | 2015-04-02 |  | New | Analysis |  | Hotel | Dynamic search EXP |  | 3.5
JS | Thursday | 2015-04-02 | 8093 | 2.8_tests |  | 2.8 | Hotel | Launch SQA test tool |  | 0.25
JS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25
JS | Friday | 2015-04-03 |  | New | Analysis |  | Hotel | Dynamic search EXP |  | 4
JS | Friday | 2015-04-03 |  | Planning | internal | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions |  | 3.5
JS | Friday | 2015-04-03 |  | Discussion |  | Afidium |  | Daily call |  | 0.25
PS | Wednesday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 |  |  | Leaves 2015-04-08 to 2015-04-12 2015-05-01
PS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 1
PS | Wednesday | 2015-04-01 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Wednesday | 2015-04-01 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schema | based on CC's suggestion | 3
PS | Wednesday | 2015-04-01 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | Remaining work | 2
PS | Thursday | 2015-04-02 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25
PS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 0.5
PS | Thursday | 2015-04-02 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Thursday | 2015-04-02 | [5 empty] | Available to assign |  | 5.75
PS | Friday | 2015-04-03 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25
PS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 0.5
PS | Friday | 2015-04-03 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Friday | 2015-04-03 | [5 empty] | Available to assign |  | 5.75
ST | Wednesday | 2015-04-01 | [5 empty] | Leave |  |  |  |  | Leaves 2015-03-30 to 2015-04-05 2015-05-01
ST | Thursday | 2015-04-02 | [5 empty] | Leave
ST | Friday | 2015-04-03 | [5 empty] | Leave
ST | Monday | 2015-04-06
ST | Monday | 2015-04-06
ST | Monday | 2015-04-06
ST | Tuesday | 2015-04-07
ST | Tuesday | 2015-04-07
ST | Tuesday | 2015-04-07
UZ | Wednesday | 2015-04-01 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1 |  |  | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Wednesday | 2015-04-01 |  |  |  |  | Stock | Free to allocate |  | 5
UZ | Thursday | 2015-04-02 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1
UZ | Thursday | 2015-04-02 |  |  |  |  | Stock | Free to allocate |  | 5
UZ | Friday | 2015-04-03 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1
UZ | Friday | 2015-04-03 |  |  |  |  | Stock | Free to allocate |  | 5