## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Monday | 2015-03-02 | [5 empty] | LEAVE |  |  |  |  | Leaves 2015-05-01 2015-05-25 I will need some leaves in APR/MAY on short notice
JS | Tuesday | 2015-03-03 | [5 empty] | LEAVE
JS | Wednesday | 2015-03-04 | [5 empty] | LEAVE
JS | Thursday | 2015-03-05 | [5 empty] | LEAVE
JS | Friday | 2015-03-06 | [5 empty] | LEAVE
JS | Monday | 2015-03-09 | [5 empty] | LEAVE
JS | Tuesday | 2015-03-10 | [5 empty] | LEAVE
JS | Wednesday | 2015-03-11 | [5 empty] | LEAVE
JS | Thursday | 2015-03-12 |  | 2.8_tests |  | 2.8 | Hotel | Checked Anne's email for 2.8 hotel issues |  |  | 0.5 | 1
JS | Thursday | 2015-03-12 | 8303 | 2.8_tests |  | 2.8 | Hotel | EXP room update problem | Check + fix. Tested , started GT for 300 hotels | 5 | 4 | 0
JS | Thursday | 2015-03-12 | 8341 | 2.8_tests |  | 2.8 | Hotel | ABT MP | Test + deploy | 2 | 2 | 1
JS | Thursday | 2015-03-12 | 6602 | 2.8_tests |  | 2.8 | Hotel | Hotel import without city code | Discussed with Anne + changed code | 1 | 0.5 | 0
JS | Thursday | 2015-03-12 | 8392 | 2.8_tests |  | 2.8 | Hotel | Synchro hotel missing hotels | Listed use cases for missing hotels + discussion with Anne |  | 1.5 | 1
JS | Thursday | 2015-03-12 |  | Discussion |  |  | Hotel | Call with Anne for the 2.8 issues | Discussed #8303, #8392, #6602, #8341 |  | 0.5 | 1
JS | Friday | 2015-03-13 |  | Planning |  |  |  | Daily updates + discussions + next week plan | daily updates + afi call | 1 | 1 | 1
JS | Friday | 2015-03-13 | 8303 | 2.8_tests |  | 2.8 | Hotel | EXP room update problem | Checked data + finalized script |  | 1 | 1
JS | Friday | 2015-03-13 | 8341 | 2.8_tests |  | 2.8 | Hotel | ABT MP | Checked data + finalized script + to CC for TRM , RMT confirmation Discussion with CC + give more information |  | 2 | 0
JS | Friday | 2015-03-13 | 6602 | 2.8_tests |  | 2.8 | Hotel | Hotel import without city code | test + finalize | 1 | 0.5 | 1
JS | Friday | 2015-03-13 | 8392 | 2.8_tests |  | 2.8 | Hotel | Synchro hotel missing hotels | code + test + wiki | 4 | 3 | 1
JS | Friday | 2015-03-13 | [5 empty] | Check emails |  | 1 | 0.5 | 0
JS | Saturday | 2015-03-14 | 8392 | 2.8_tests |  | 2.8 | Hotel | Synchro hotel missing hotels | checked issue reported by ST + fixed + update install script |  | 1 | 1
JS | Monday | 2015-03-16 |  | Planning | logirythm |  |  | Weely planning | planning + clarifications from PS for last week + detailing | 1.5 | 2.5 | 1
JS | Monday | 2015-03-16 |  | Planning | Afi |  |  | Weekly planning + objectives |  | 1 | 1 | 1
JS | Monday | 2015-03-16 |  | Maintenance |  |  | Hotel | Check production server for 14th | All updates failed. Analysis + mails + discussions |  | 1 | 0
JS | Monday | 2015-03-16 | 8303 | 2.8_tests |  | 2.8 | Hotel | EXP room update problem | analysis + fix + tests | 0.5 | 3 | 1
JS | Monday | 2015-03-16 | 8412 | Analysis |  | 2.8 | Hotel | Strater Hotel Durango | Check issue from mail + analyse | 2 | 0.5 | 0
JS | Monday | 2015-03-16 | 8131 | New |  | 2.8 | Hotel | Child age import for VDM | prepare test cases | 3 | 0 | -1
JS | Tuesday | 2015-03-17 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Tuesday | 2015-03-17 | 8303 | 2.8_tests |  | 2.8 | Hotel | Expedia room update problem | checked data + restarted GT as yesterday update did not finish as expected Checked data OK. Changed SP per AF suggestion to avoid reactivation |  | 1 | 0
JS | Tuesday | 2015-03-17 | 8428 | Maintenance |  | 2.8 | Hotel | Jonview availability issue | Checked + fixed + tests + city correction script for prod + included in release scripts + patch |  | 1.5 | 1
JS | Tuesday | 2015-03-17 | 8430 | Maintenance |  | 2.8 | Hotel | Missing hotel in production | Checked + analyse. Need to synchro + wait for updates to finish |  | 0.75 | 1
JS | Tuesday | 2015-03-17 | 8131 | New |  | 2.8 | Hotel | Child age import for VDM | Checked code. Confused, Need Anne's help in correcting my understanding call with Anne + data check + asked ST for change test cases + call with ST + occupation test queries | 2 | 3.5 | 0
JS | Tuesday | 2015-03-17 | 8418 | 2.8_tests |  | 2.8 | Hotel | Validation error for ABI MP | Check + fix + test |  | 1 | 1
JS | Tuesday | 2015-03-17 |  | Discussion | snapin |  |  | Help PS answer questions | what should be URL of applications in a environment for RG testers : add reference to soap toolkit video |  | 0.5 | 1
JS | Tuesday | 2015-03-17 |  | Maintenance |  | 2.8 | Hotel | Deactivate GT for devcache. L precache files. | on 104 as its keeping 104 CPU busy |  | 0.25 | 1
JS | Tuesday | 2015-03-17 |  | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | tests + analysis | 3 | 0 | -1
JS | Tuesday | 2015-03-17 |  | Planning | internal | 2.9 | Hotel | Hg organization for galaxyref and non-galaxyred | separate branch for galaxyref related changes + DB organization | 2 | 0 | -1
JS | Wednesday | 2015-03-18 |  | Planning | internal |  |  | Daily updates + discussions | PS, ST, AF, CC | 1 | 1 | 1
JS | Wednesday | 2015-03-18 |  | Maintenance |  | 2.7 | Hotel | Prod VDM update failure | Checked lot problem. Corrected for 2.8 |  | 1 | 1
JS | Wednesday | 2015-03-18 | 8428 | 2.8_tests |  |  | Hotel | JNV availability problem + city code correction | Tested GT + L |  | 0.5 | 1
JS | Wednesday | 2015-03-18 | 8303 | 2.8_tests |  |  | Hotel | EXP room update problem | Tested SPs with precache files |  | 0.5 | 1
JS | Wednesday | 2015-03-18 | 8131 | 2.8_tests |  | 2.8 | Hotel | Child age import for VDM | test cases + testing + discussions | 4 | 5 | 1
JS | Wednesday | 2015-03-18 | 8467 | 2.8_tests |  | 2.8 | Hotel | se_availability__update problem | Discussion with Anne |  | 0.5 | 1
JS | Wednesday | 2015-03-18 | 8431 | Release | Patch | 2.8 | Hotel | Release patch for 2.8 | gathered files without child ages patch | 1 | 0.5 | 0
JS | Wednesday | 2015-03-18 |  | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | analysis | 2 | 0 | -1
JS | Wednesday | 2015-03-18 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 2.5 | 0 | -1
JS | Wednesday | 2015-03-18 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Wednesday | 2015-03-18 | 7768 | 2.9_tests |  | 2.9 | Hotel | Extrapolation - process less data | test | 1 | 0 | -1
JS | Thursday | 2015-03-19 |  | Planning | internal |  |  | tracking sheet update |  | 1 | 0.25 | 1
JS | Thursday | 2015-03-19 | 8428 | 2.8_tests |  | 2.8 | Hotel | JNV availability problem + city code correction | JNV city code explaination + check |  | 0.25 | 1
JS | Thursday | 2015-03-19 |  | Discussion | internal |  | Hotel | Discussion with ST for setting up web service to update new server |  |  | 0.25 | 1
JS | Thursday | 2015-03-19 | 8463 | Maintenance |  | 2.7 | Hotel | EXP CB problem | Analysis + how to fix on prod + discussion with CC, AF. Tried to reproduce, cannot reproduce the problem |  | 4.5 | 0
JS | Thursday | 2015-03-19 | 8467 | 2.8_tests |  | 2.8 | Hotel | se_availability__update problem | fix + test + finalize for patch | 1 | 1 | 1
JS | Thursday | 2015-03-19 | 8431 | 2.8_tests |  | 2.8 | Hotel | Make patch and retest |  | 2 | 2 | 1
JS | Thursday | 2015-03-19 |  | Discussion | snapin |  |  | Help for VBA macro setup | MM, SK are not able to add references to VBA project. It means it is not macro pb but installation pb. I have asked him to check with admin OR try on another machine Also asked to write a simple macro and see if it works to be sure the installation supports macro |  | 0.5 | 0
JS | Thursday | 2015-03-19 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Analysis + implementation | 4 | 0 | -1
JS | Thursday | 2015-03-19 |  | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | tests + analysis | 3 | 0 | -1
JS | Friday | 2015-03-20 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 0 | -1
JS | Friday | 2015-03-20 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 7 | 0 | -1
JS | Friday | 2015-03-20 | [5 empty] | LEAVE (personal)
JS | Monday | 2015-03-23 |  | Planning | internal | Logirythm | Hotel | Weekly planning + objectives | tracking sheet + checked assigned tasks | 2 | 2.5 | 1
JS | Monday | 2015-03-23 |  | Planning | internal | Afidium | Hotel | Weekly planning + objectives | 10 mins grp discussion | 1 | 0.25 | 0
JS | Monday | 2015-03-23 | 8463 | Maintenance |  | 2.7 | Hotel | EXP CB problem | Check further + discuss with AF, ST, try to reproduce the problem, decide next steps | 2 | 2.5 | 0
JS | Monday | 2015-03-23 |  | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests - precache vs prod - test + analysis. No information for patch application | started tests | 3 | 0.25 | 0
JS | Monday | 2015-03-23 |  | Discussion | internal |  | Hotel | Anne's email for spSearchMargins | Read + check + reply |  | 0.5 | 1
JS | Monday | 2015-03-23 |  | 2.8_tests |  | 2.8 | Hotel | Checked precache after update | vdm + synchro + EXP + ABT MP |  | 1 | 1
JS | Tuesday | 2015-03-24 |  | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | Checked data for mismatch for tests played yesterday. Mismatches are only for EXP and GTA. But they look OK. For EXP, 2.8 looks better than prod | 3 | 2 | 1
JS | Tuesday | 2015-03-24 |  | Planning | internal |  |  | Daily updates - tracking sheet |  | 0.25 | 0.25 | 1
JS | Tuesday | 2015-03-24 | 8463 | Maintenance |  | 2.7 | Hotel | EXP CB problem | Checked on 2.7, discuss with PS. Call with AF + ST Checked NOK cases | 3 | 2 | 0
JS | Tuesday | 2015-03-24 | 8283 | New |  |  | TUI | Addition of the parent log in the response | Implementation + tests | 1 | 0 | -1
JS | Tuesday | 2015-03-24 | 8281 | New |  |  | TUI | Implement TFL in Web Service transactions | Understand requirement + start implementation | 0.5 | 0 | -1
JS | Tuesday | 2015-03-24 |  | 2.8_tests | follow-up | 2.8 | Hotel | Follow up progress for dashboard tests - snapin | Talked to SK. All tests are OK except CSV as tester was waiting for CSV generation | 0.25 | 0.25 | 0
JS | Tuesday | 2015-03-24 |  | Discussion | internal |  | Hotel | Discussion with Anne for A2C2 | preliminary info. Need to check in detail + document |  | 0.25 | 0
JS | Tuesday | 2015-03-24 | 8412 | Maintenance |  | 2.7 | Hotel | Strater Hotel Durango | Check old files for RMT MP. Initial analysis |  | 0.25 | 0
JS | Tuesday | 2015-03-24 |  | Discussion | internal |  | Hotel | Discussion with CC for update of hotel 3001522 (EXP : 1723343) | Checked data on all servers + updated on devcache + our server + check that it will not get updated tonight and that when it updates next, it should be ok |  | 0.75 | 1
JS | Wednesday | 2015-03-25 | 8281 | New |  |  | TUI | Implement TFL in Web Service transactions | Implementation + tests | 2.25
JS | Wednesday | 2015-03-25 |  | Planning | internal |  |  | Daily updates - tracking sheet |  | 0.25
JS | Wednesday | 2015-03-25 | 8094 | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | precache vs prod - test + analysis | 4
JS | Wednesday | 2015-03-25 |  | Discussion | internal |  | Hotel | Make a list of quality control actions then tools to automate | Initial discussion with AF | 0.5
JS | Wednesday | 2015-03-25 | 8436 | Maintenance |  | 2.7 | Hotel | Patch the url of Abbey tours on 2.7 | Patch preparation + check for production | 1
JS | Thursday | 2015-03-26 |  | Planning | internal |  |  | Daily updates - tracking sheet |  | 0.25
JS | Thursday | 2015-03-26 | 8094 | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | tests + analysis | 3
JS | Thursday | 2015-03-26 |  | New | Documentation |  | Hotel | Make a list of quality control actions then tools to automate | List | 1
JS | Thursday | 2015-03-26 | 8290 | New | Documentation | 2.8 | Hotel | Description of test tool API feature |  | 1
JS | Thursday | 2015-03-26 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 2
JS | Thursday | 2015-03-26 | 8412 | Maintenance |  | 2.7 | Hotel | Strater Hotel Durango | Check old files for RMT MP | 0.75
JS | Friday | 2015-03-27 |  | Planning | internal |  |  | Daily updates - tracking sheet |  | 0.25
JS | Friday | 2015-03-27 | 8094 | 2.8_tests |  | 2.8 | Hotel | SQA test tool tests | tests + analysis | 3
JS | Friday | 2015-03-27 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 1.5
JS | Friday | 2015-03-27 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 2.5
JS | Friday | 2015-03-27 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5
PS | Monday | 2015-03-02 |  | Maintenance |  |  | Hotel | COts |  | 0.25 | 0.25 | 1 | Leaves 2015-04-08 to 2015-04-12 2015-05-01
PS | Monday | 2015-03-02 |  | Discussion | internal |  |  | Daily updates + discussions | ST: discussed for devcache + precache + check tasks updates + Task creations, Tracking shee | 0.75 | 2 | 1
PS | Monday | 2015-03-02 |  | Training | snapin |  |  | Co-ordinate with test team | Call with rupali for dashboard + SAO with Manali | 0.5 | 1 | 1
PS | Monday | 2015-03-02 | 8071 | New |  |  | Hotel | JNV Price GT failed on prod |  | 0.25 | 0.25 | 1
PS | Monday | 2015-03-02 | 8302 | New |  |  | TUI | Integrate additionnal Traveler typologies in the booking workflows | XSL changes but testing problem, debug, With CC | 1 | 3.5 | 0
PS | Tuesday | 2015-03-03 |  | Maintenance |  |  | Hotel | Cots | Mails + status for devcache PP : with ST | 0.25 | 0.25 | 1
PS | Tuesday | 2015-03-03 |  | Discussion | internal |  |  | Daily updates and discussions | Task creation + Task updates + Tracking sheet + venda report + CC (production checks) + Call with ST + discuss with Shubhad | 0.75 | 2.25 | 1
PS | Tuesday | 2015-03-03 |  | Training | snapin |  | TUI | Co-ordinate with test team |  | 0.5 | 0.75 | 1
PS | Tuesday | 2015-03-03 | 8302 | New |  |  | TUI | Integrate additionnal Traveler typologies in the booking workflows | Test GQA + CB + task update | 1 | 1.5 | 1
PS | Tuesday | 2015-03-03 | 8319 | New |  |  | TUI | [GQA/CB/GB] - Addition of the selling conditions in RS | Read + XSL Out finish for both | 2 | 2 | 0
PS | Tuesday | 2015-03-03 |  | Training | snapin |  | TUI | Review Tests + suggest |  | 0.5 | 0.5 | 1
PS | Wednesday | 2015-03-04 |  | Maintenance |  |  | Hotel | Cots | Mails + status for production | 0.25 | 0.25 | 1
PS | Wednesday | 2015-03-04 |  | Discussion | internal |  |  | daily updates + discussions | cot related tasks updates + checks + call with Shubhad + discussions | 0.75 | 2 | 1
PS | Wednesday | 2015-03-04 |  | Training | snapin |  | TUI | Co-ordinate with test team | Co-ordination +calls + work for rest of the week | 0.5 | 1.25 | 1
PS | Wednesday | 2015-03-04 | 8319 | New |  |  | TUI | [GQA/CB/GB] - Addition of the selling conditions in RS | Work on Response: XSLIN + complete sample + Discuss with CC | 6.5 | 4.5 | 0
PS | Thursday | 2025-03-05 | [5 empty] | LEAVE
PS | Friday | 2015-03-06 | [5 empty] | LEAVE
PS | Monday | 2025-03-09 |  | Maintenance |  |  | Hotel | Production COT | COT + mail reverts for issue + Discussion with ST | 0.25 | 0.5 | 1
PS | Monday | 2015-03-09 |  | Discussion | internal |  |  | Co-rdinations and calls for support | RG, ST, Problem resolution with MA, MM, SK | 2 | 4.5 | 1
PS | Monday | 2015-03-09 | 8319 | New |  |  | TUI | [GQA/CB/GB] - Addition of the selling conditions in RS | Finished remaining + questions to CC | 2 | 2 | 1
PS | Monday | 2015-03-09 | 8352 | New |  |  | Hotel | Web service error |  | 0.5 | 0.5 | 1
PS | Monday | 2015-03-09 | 8335 | New |  |  | Hotel | Prod: 0 availability Update for EXP | tried but stucked | 0.5 | 0.5 | 0
PS | Tuesday | 2015-03-10 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Tuesday | 2015-03-10 | 8283 | Discussion | snapin |  | TUI | Co-ordinations and calls for support | MA - support for running XFTWS project |  | 1.5 | 1
PS | Tuesday | 2015-03-10 | 8333 | Discussion | snapin |  | AIR | [Multilinguism] Additional translations for Fareopt | Support RG for Yii |  | 1 | 1
PS | Tuesday | 2015-03-10 |  | Discussion | snapin |  |  | Call with Shubhad for testers' tasks |  |  | 0.5 | 1
PS | Tuesday | 2015-03-10 | 7246 7749 | Discussion | snapin |  | Hotel | Hotel update issues | Tell MM about how to create tables in tasks and how to check updates |  | 0.25 | 1
PS | Tuesday | 2015-03-10 | 8293 | Discussion | snapin | dashboard | Hotel | Test Dashboard | Explain RN how to check correctness of markup % in dashboard |  | 0.5 | 1
PS | Tuesday | 2015-03-10 | 8319 | New |  |  | TUI | [GQA/CB/GB] - Addition of the selling conditions in RS | Further work as instructed by CC + checkout + discuss with CC | 2 | 3 | 1
PS | Tuesday | 2015-03-10 | 8388 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | Read the new task + checks related docs | 0.5 | 0.75 | 1
PS | Tuesday | 2015-03-10 |  | Planning | internal |  |  | Daily update | tracking sheet |  | 0.25 | 1
PS | Wednesday | 2015-03-11 |  | Maintenance |  |  | Hotel | Production COT | check + reply | 0.25 | 0.25 | 1
PS | Wednesday | 2015-03-11 | [5 empty] | Co-ordinations and calls for support | MM +MA + RG + SK +ST + RN | 2 | 2.5 | 1
PS | Wednesday | 2015-03-11 | 8388 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction |  | 5.75 | 5.25 | 0
PS | Thursday | 2015-03-12 |  | Maintenance |  |  | Hotel | Production COT | mail check | 0.25 | 0.25 | 1
PS | Thursday | 2015-03-12 |  | Discussion | internal |  |  | Co-ordinations and calls for support | MA + RG + MM + JS | 1 | 2 | 1
PS | Thursday | 2015-03-12 | 8288 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | Remaining work and discussion with CC , Finalized + doc + testing started | 6.75 | 5.75 | 0
PS | Friday | 2015-03-13 |  | Maintenance |  |  | Hotel | Production COT | Prod mails | 0.25 | 0.25 | 1
PS | Friday | 2015-03-13 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
PS | Friday | 2015-03-13 | 8335 | 2.8_tests |  | 2.8 | Hotel | Prod: 0 availability Update for EXP | check + discuss with JS + task update |  | 0.5 | 1
PS | Friday | 2015-03-13 | 8336 | Discussion | snapin |  | TUI | Implement Apply QuotedAvailability RQ for Amadeus | Call with manali and wrote way to proceed in Ticket. Clearified The understanding on CC's response . Again call to MA for clearification |  | 2 | 1
PS | Friday | 2015-03-13 | 8393 | Discussion | snapin |  | TUI | Test Search Quoted Availability | Discuss with Shubhad for alternative way to test + Macro problem group discussion + MM Verified MM's issue + tell her how to raise an issue |  | 1 | 1
PS | Friday | 2015-03-13 | 8293 | Discussion | snapin |  | Hotel | Test Dashboard | Co-ordination with RN to clearify his confusion over query + solution forwarded to her over the mail she sent for issue |  | 0.5 | 1
PS | Friday | 2015-03-13 |  | Discussion | internal |  |  | Discussion with JS + UZ |  |  | 0.25 | 1
PS | Friday | 2015-03-13 | 8288 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | Finish | 6.75 | 0 | -1
PS | Friday | 2015-03-13 | 8404 | New |  |  | TUI | [SQA-ERETAIL] - Sector duration are missing? | xsl change + test + update |  | 0.75 | 1
PS | Friday | 2015-03-13 | 8341 | 2.8_tests |  | 2.8 | Hotel | ABT MP | started data collection for tests |  | 1 | 0
PS | Friday | 2015-03-13 | 8407 | New |  |  | TUI | Issue in TUPI SQA response | Check + respond + doc corrections |  | 1.5 | 1
PS | Monday | 2015-03-16 |  | Maintenance |  |  | Hotel | Production COT | Production checks + precache check + mail | 0.25 | 0.75 | 1
PS | Monday | 2015-03-16 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet | 0.5 | 1 | 1
PS | Monday | 2015-03-16 |  | Discussion | internal |  |  | Clarification to JS for time spent in discussions | Clearifications on snapin co-ordination + discuss about whom to assign preccahe dashboard tests |  | 0.75 | 1
PS | Monday | 2015-03-16 | 8341 | 2.8_tests |  | 2.8 | Hotel | ABT MP | testgrid + testcases + tests | 3 | 3 | 0
PS | Monday | 2015-03-16 | 8388 | New |  |  | TUI | SQA - enhancements in amadeus transaction | Doc corrections | 1 | 1 | 1
PS | Monday | 2015-03-16 |  | Discussion | snapin |  |  | discussions + support for snapin | MM ( ask her to msg CC over #8407 and continue on the task + little co-ordination),ask RN to test dashboard Precache , AF(check for preccahe dashboard : not working), RG(gave path in svn to find examples) | 1.5 | 1.5 | 1
PS | Tuesday | 2015-03-17 |  | Maintenance |  |  | Hotel | Production COT | Procustion mail + devcache mail reply | 0.25 | 0.25 | 1
PS | Tuesday | 2015-03-17 |  | Planning | internal |  |  | Daily updates + discussions | with JS + Tracking sheet | 0.5 | 0.5 | 1
PS | Tuesday | 2015-03-17 |  | Discussion | snapin |  |  | discussions + support for snapin | RG: 0.5(testing problems in Yii) MA: 0.5 (AQA xsl steps) MM(SQA testing) , RN(dashboard) , SK(query) : little co-ordinations: 0.5 | 1.5 | 1.5 | 1
PS | Tuesday | 2015-03-17 | 8341 | 2.8_tests |  |  | Hotel | ABT MP | Tested for ABS GQA + TRM +Testgrid update+ task update + anomoly tested | 5.75 | 3 | 0
PS | Tuesday | 2015-03-17 | 8419 | New |  |  | TUI | [GQA/CB/GB] - Addition of tax details | XSL changed + tested + task updates |  | 3 | 1
PS | Wednesday | 2015-03-18 |  | Maintenance |  |  | Hotel | Production COT | mails + check updated + reply | 0.25 | 0.5 | 1
PS | Wednesday | 2015-03-18 |  | Planning | internal |  |  | Daily updates + discussions | Help from JS for macro problem for windows 8 system + old task cleanups + tracking sheet | 0.5 | 0.75 | 1
PS | Wednesday | 2015-03-18 |  | Discussion | snapin |  |  | discussions + support for snapin | RG : testing problems in Yii due to spanish language SK: co-ordination to solve MM's problem of macro, provided details MM: call for macro problem again Little co-ordinations with RN, SS | 1.5 | 1.5 | 1
PS | Wednesday | 2015-03-18 | 8438 | New |  |  | Hotel | [Point Projet 13 Mars] Validate CO on precache | CO tests |  | 0.75 | 1
PS | Wednesday | 2015-03-18 | 8303 | New |  |  | Hotel | [Exp] Tariff problem | Tested + discussion with JS + task updates |  | 3 | 1
PS | Wednesday | 2015-03-18 | 8071 | New |  |  | Hotel | JNV Price GT failed on prod | Prod DB checks + task update |  | 0.5 | 1
PS | Wednesday | 2015-03-18 | 5272 | New |  |  | Hotel | [Redmine] 1st Standardisation of VDM Natif Connector | Found info to fill the incomplete wiki |  | 1 | 1
PS | Thursday | 2015-03-19 |  | Maintenance |  |  | Hotel | Production COT | Mail checks + reply | 0.25 | 0.5 | 1
PS | Thursday | 2015-03-19 |  | Planning | internal |  |  | Daily updates + discussions | EP: Provided feedback for AQA task of MA JS: Co-ordination for planning Tracking sheet | 0.5 | 1 | 1
PS | Thursday | 2015-03-19 |  | Discussion | snapin |  |  | discussions + support for snapin | MM and RN : issues on testing TUAPI SQA # 8393 SK+MM+JS : Macro discussion + resolution | 1.5 | 2 | 1
PS | Thursday | 2015-03-19 | 8132 | 2.8_tests |  |  | Hotel | XSL change for child age implementation | Tests + discussion on testing | 3 | 4 | 1
PS | Friday | 2015-03-20 |  | Maintenance |  |  | Hotel | Production COT | Production status check + mail | 0.25 | 0.5 | 1
PS | Friday | 2015-03-20 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet | 0.5 | 0.25 | 1
PS | Friday | 2015-03-20 |  | Discussion | snapin |  |  | discussions + support for snapin | MM + RN for SQA issues | 1.5 | 1 | 1
PS | Friday | 2015-03-20 | 8455 | New |  |  | TUI | Add baggage allowance in SGA response (Fare_MasterPricerTravelBoardSearch) | Questions + clearifications with CC + xsl Modification + tests+ task update | 5.75 | 5 | 1
PS | Friday | 2015-03-20 | 8481 | New |  |  | TUI | List Seat returns NaN prices | Check + change XSL + test + update + task update |  | 0.5 | 1
PS | Monday | 2015-03-23 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Monday | 2015-03-23 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Monday | 2015-03-23 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Monday | 2015-03-23 | [5 empty] | Available to assign |  | 5.75
PS | Tuesday | 2015-03-24 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Tuesday | 2015-03-24 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Tuesday | 2015-03-24 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Tuesday | 2015-03-24 | [5 empty] | Available to assign |  | 5.75
PS | Wednesday | 2015-03-25 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Wednesday | 2015-03-25 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Wednesday | 2015-03-25 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Wednesday | 2015-03-25 | [5 empty] | Available to assign |  | 5.75
PS | Thursday | 2015-03-26 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Thursday | 2015-03-26 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Thursday | 2015-03-26 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Thursday | 2015-03-26 | [5 empty] | Available to assign |  | 5.75
PS | Friday | 2015-03-27 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Friday | 2015-03-27 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Friday | 2015-03-27 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Friday | 2015-03-27 | [5 empty] | Available to assign |  | 5.75
ST | Monday | 2015-03-02 | 8307 | New |  |  | Stock | Issue with persontypes in quotation | Analysis and task updated | 0.75 | 0.75 | 1 | Leaves 2015-03-30 to 2015-04-05 2015-05-01
ST | Monday | 2015-03-02 | 6618 | New |  |  | AIR | Use fareopt aggregation in dashboard | Corrected code and commit , task updated | 0.5 | 0.5 | 1
ST | Monday | 2015-03-02 | 7868 | New |  |  | Stock | db improvements SP + Index | Task updated | 0.25 | 0.25 | 1
ST | Monday | 2015-03-02 |  | Planning | internal |  |  | Daily updates + discussions | Discussion with PS + Tracking sheet, discussion with Anne | 1 | 1 | 1
ST | Monday | 2015-03-02 | 8311 |  |  |  | Hotel | 0 Accomodation updates for Bonotel on precache and Devcache | Analysis and task updated, discussion with Anne | 0.5 | 0.5 | 1
ST | Monday | 2015-03-02 | 8312 |  |  |  | Hotel | Devcache : SQM failing for last four days | Analysis and execution on devcache, discussion with Anne and PS | 1 | 1 | 1
ST | Monday | 2015-03-02 | 8287 | Training | internal |  |  | KT on Stock Database |  | 2 | 1.5 | 0
ST | Monday | 2015-03-02 |  |  |  |  | Stock | Discussion with DAVID, GK, Anne and AR | Discussion | 0.5 | 0.5 | 1
ST | Tuesday | 2015-03-03 | 8222 | New |  |  | Stock | Improve sto_journey__list to take less time | Analysis and discussion, coding, testing | 2 | 1.5 | 0
ST | Tuesday | 2015-03-03 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis and discussion, coding, testing | 2 | 1.5 | 0
ST | Tuesday | 2015-03-03 | 8287 | Training | internal |  |  | KT on Stock Database |  | 1.5 | 1.5 | 0
ST | Wednesday | 2015-03-03 |  | Planning | internal |  |  | Daily updates + discussions | Plan for the week activity, tracking sheet and weekly meeting page updated, Discussion with PS for PROD EXP issue | 0.5 | 1.5 | 1
ST | Wednesday | 2015-03-03 |  | Planning | internal |  |  | Call with Anne , PS, SK, UM, DM | Plan for all DB resources for current and next week | 1 | 1 | 1
ST | Wednesday | 2015-03-03 | 8254 |  |  |  | Stock | SP "sto_journey__search" is slow | Discussion with David and GK | 1 | 1 | 0
ST | Wednesday | 2015-03-04 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | Analysis, discussion with Dhanesh and explain him and helping him | 1 | 1 | 0
ST | Wednesday | 2015-03-04 | 8222 | New |  |  | Stock | Improve sto_journey__list to take less time | Analysis and discussion, coding, testing, discussion with Anne | 1 | 0.5 | 0
ST | Wednesday | 2015-03-04 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet , discussion with PS | 0.5 | 0.5 | 1
ST | Wednesday | 2015-03-04 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis and discussion, coding, testing | 1 | 4 | 0
ST | Thursday | 2025-03-05 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Search and Documentation | 2 | 2 | 1
ST | Thursday | 2025-03-05 | 8330 | New |  |  | Stock | Memory problem | Analysis and coding | 1 | 0 | -1
ST | Thursday | 2025-03-05 | 8307 | New |  |  | Stock | Issue with persontypes in quotation | Analysis | 0.5 | 0 | -1
ST | Thursday | 2025-03-05 | 8287 | Training | internal |  |  | KT on Stock Database | Call with DM, UZ. Discussion with DM , UZ for postgresql and stock database | 1.5 | 2 | 0
ST | Thursday | 2025-03-05 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
ST | Thursday | 2025-03-05 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | Review code and finalize, discussion with emillise, coding and testing | 1 | 3 | 1
ST | Friday | 2015-03-06 | 8287 | Training | internal |  |  | KT on Stock Database | Discussion with Uma for sock database understanding and wiki update | 1 | 1.5 | 1
ST | Friday | 2015-03-06 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet , discussion with Anne | 0.5 | 0.5 | 1
ST | Friday | 2015-03-06 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis and discussion, coding, testing for __search and __list | 1 | 0.5 | 0
ST | Friday | 2015-03-06 | 7868 | New |  |  | Stock | db improvements of SP + indexes | Wiki updated, and task closed | 0.25 | 0.25 | 1
ST | Friday | 2015-03-06 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | Read comments and task updated | 0.25 | 0.25 | 1
ST | Friday | 2015-03-06 | 8350 | New |  |  | Hotel | Honeymoon prices issue for Lemuria Seychelles | Read the comments and req | 0.25 | 0.25 | 1
ST | Friday | 2015-03-06 | 8307 | New |  |  | Stock | Issue with persontypes in quotation | Discussion with AR, YT , analysis | 0.5 | 1 | 1
ST | Friday | 2015-03-06 | 6922 | New |  |  | AIR | AIR DB Cleanup | Analysis | 3 | 2 | 0
ST | Monday | 2015-03-09 | 6922 | New |  |  | AIR | AIR DB Cleanup | discussion with Dhanesh and explain him the details | 1 | 1 | 1
ST | Monday | 2015-03-09 |  | Planning | internal |  |  | Daily updates and discussions | Plan for the week activity, discussion with Uma | 1 | 1 | 1
ST | Monday | 2015-03-09 | 7639 | New |  |  | Hotel | Setup of Replication Activity | Setup of new server and login for all | 1 | 1 | 0
ST | Monday | 2015-03-09 |  | Planning | internal |  |  | Discussion with Anne | Discussion about this week's activity for whole database team | 1 | 1 | 1
ST | Tuesday | 2015-03-10 | 7639 | New |  |  | Hotel | Setup of Replication Activity | Database creation | 2 | 1.5 | 0
ST | Tuesday | 2015-03-10 |  | Planning | internal |  |  | Daily updates and discussions | Discussion with Anne, EP and Dhanesh for 6922 and 8361 | 1 | 1 | 1
ST | Tuesday | 2015-03-10 | 6922 | New |  |  | AIR | AIR DB Cleanup | Discussion with Dhanesh about his understanding | 1 | 0.5 | 0
ST | Tuesday | 2015-03-10 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | Analysis and discussion | 1 | 0.5 | 0
ST | Tuesday | 2015-03-10 | 8359 | New |  |  | Stock | Modify dic functions | Code review and suggested changes | 0.5 | 0.5 | 1
ST | Wednesday | 2015-03-11 | 7639 | New |  |  | Hotel | Setup of Replication Activity | Replication setup | 2 | 2 | 0
ST | Wednesday | 2015-03-11 | 8392 | New |  |  | Hotel | Hotel 3001930 Deactivation | Analysis and tseting | 1 | 1 | 1
ST | Wednesday | 2015-03-11 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | coordinate with Dhnaesh for coding and testing | 0.5 | 0.5 | 1
ST | Wednesday | 2015-03-11 |  |  | internal |  |  | Daily updates and discussions | Discussion with Uma , tracking sheet | 0.5 | 0.5 | 1
ST | Thursday | 2015-03-12 | 6922 | New |  |  | AIR | AIR DB Cleanup | Coordinate with Dhnaesh for coding, discussion, call with Anne | 1 | 1.5 | 0
ST | Thursday | 2015-03-12 |  | New |  |  | Stock | Discussion with Uma for stock update SP proposal and analysis |  | 1.5 | 0 | -1
ST | Thursday | 2015-03-12 | 7639 | New |  |  | Hotel | Setup of Replication Activity | Discussion with Uma for new DB creation script |  | 0.5 | 1
ST | Thursday | 2015-03-12 | 8392 | 2.8_tests |  |  | Hotel | Synchro hotel missing hotels | Discussion with JS |  | 0.25 | 1
ST | Thursday | 2015-03-12 |  | 2.8_tests |  |  | Hotel | Analysis and tests for Dashboard queries raised by testing team | Analysis, testing |  | 0.5 | 1
ST | Thursday | 2015-03-12 |  | Planning | internal |  |  | Daily updates and discussions | Tracking sheet and Discussion with JS | 0.5 | 0.5 | 1
ST | Friday | 2015-03-13 | 6922 8376 | New |  |  | AIR | AIR DB Cleanup | Coordinate with Dhnaesh for coding | 1.5 | 2 | 0
ST | Friday | 2015-03-13 |  | New |  |  | Stock | Discussion with Uma for new DB creation script + sys functions |  | 1 | 0.5 | 1
ST | Friday | 2015-03-13 |  | Planning | internal |  |  | Daily updates and discussions |  | 0.5 | 0.5 | 1
ST | Friday | 2015-03-13 | 8392 | 2.8_tests |  |  | Hotel | Synchro hotel missing hotels | Checklist creation + tests for 8392 , 6602 | 2.5 | 4 | 1
ST | Monday | 2015-03-16 | 8131 | 2.8_tests |  |  | Hotel | Change child age import for VDM | Analysis, Coding , Call with Anne , Testing 1.5 hour for analysis and discussion with Anne 45 mins - trying to create single query to check. Unsuccessful find cases + test + document tests - 2.5 hr | 5.5 | 5 | 1
ST | Monday | 2015-03-16 |  | Planning | internal |  |  | Daily updates + discussions | Discussion with JS about week's plan and replication status | 0.5 | 0.5 | 1
ST | Monday | 2015-03-16 | 7639 | Discussion | Replication |  | Hotel | Replication setup on new server | Discussion with Uma for basic data scripts |  | 0.5 | 0
ST | Monday | 2015-03-16 | 8316 | Discussion | internal |  | Stock | Merge dic_meta_parameter and sys_data table | Discussion with Dhanesh, Anne and EP |  | 0.5 | 0
ST | Monday | 2015-03-16 | 8376 | Discussion | internal |  | AIR | AIR DB Cleanup | coordinate with Dhnaesh for coding and testing |  | 0.5 | 0
ST | Tuesday | 2015-03-17 | 8131 | 2.8_tests |  |  | Hotel | Change child age import for VDM | Modified and tested for change in flow, discussion, coding and testing | 1.5 | 2 | 0
ST | Tuesday | 2015-03-17 |  | Planning | internal |  |  | Planning for all DB team and daily update | Planning for DB team , tracking sheet and discussions | 0.5 | 1 | 1
ST | Tuesday | 2015-03-17 |  | Discussion | internal |  | AIR | Discussion with Uma and Dhanesh |  | 1 | 0 | -1
ST | Tuesday | 2015-03-17 | 8316 | New |  |  | Stock | Merge dic_meta_parameter and sys_data table | Coordinate with Dhanesh for testing and task update |  | 0.5 | 0
ST | Tuesday | 2015-03-17 | 8427 | New |  |  | Hotel | Automation of Hotel and VDM synchro Tests | Discussion with Uma for analysis |  | 0.5 | 0
ST | Tuesday | 2015-03-17 | 7639 | New |  |  | Hotel | Replication setup on new server | DB setup + populate DB + hotel synchro + tests | 3 | 2 | 0
ST | Wednesday | 2015-03-18 |  | Planning | internal |  |  | Daily updates + discussions | Daily updates + Call with Uma for diff tasks | 0.5 | 1 | 1
ST | Wednesday | 2015-03-18 | 7639 | New |  |  | Hotel | Replication setup on new server | VDM synchro + corrected the problem in replication +testing | 4 | 2.5 | 0
ST | Wednesday | 2015-03-18 | 8376 | New |  |  | AIR | AIR DB Cleanup | coordinate with Dhanesh for coding and testing |  | 0.5 | 0
ST | Wednesday | 2015-03-18 | 8131 | 2.8_tests |  |  | Hotel | Change child age import for VDM | Modified and tested for change in flow, discussion, coding and testing | 1.5 | 8 | 1
ST | Thursday | 2015-03-19 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and Discussion with all | 0.5 | 0.5 | 1
ST | Thursday | 2015-03-19 | 8287 | Training | internal |  | Stock | KT on Stock Database | KT session on booking SP to Uma |  | 1.5 | 1
ST | Thursday | 2015-03-19 | 8376 | New |  |  | AIR | AIR DB Cleanup | coordinate with Dhnaesh for coding and testing | 2 | 1 | 0
ST | Thursday | 2015-03-19 | 7639 | New |  |  | Hotel | Replication setup on new server | Check if replication is working correctly with nightly updates | 1 | 0 | -1
ST | Thursday | 2015-03-19 | 8460 | New |  |  | Stock | Booking + Winter | Analysis and Discussion |  | 0.5 | 1
ST | Friday | 2015-03-20 |  | Planning | internal |  |  | Daily updates + discussions | discussions with stock team , and answers to queries | 0.5 | 0.5 | 1
ST | Friday | 2015-03-20 | 8376 | New |  |  | AIR | AIR DB Cleanup | code review and testing, and archieving discussion |  | 1 | 0
ST | Friday | 2015-03-20 | 8287 | Training | internal |  |  | KT on Stock Database | KT session on booking replaceSP to Uma | 1 | 1 | 1
ST | Friday | 2015-03-20 | 8463 | Maintenance |  | 2.7 | Hotel | [EXPEDIA] Afidium web service error | Analysis , coding and testing, discussion with Anne | 2.5 | 2.5 | 0
ST | Monday | 2015-03-23 |  | Planning | internal |  |  | Weekly planning for DB resources |  | 2 | 0 | -1
ST | Monday | 2015-03-23 | 8463 | Maintenance |  | 2.7 | Hotel | [EXPEDIA] Afidium web service error | Analysis , coding and testing, discussion with JS, Call with Anne | 4 | 4 | 0
ST | Monday | 2015-03-23 | 8480 | New |  |  | Stock | Update PNR (Passive Booking) on booking | Analysis, call with Anne and Uma |  | 1 | 0
ST | Monday | 2015-03-23 | 8376 | New |  |  | AIR | AIR DB Cleanup | Discussion with Dhanesh |  | 0.5 | 0
ST | Monday | 2015-03-23 | 6618 | New |  |  | AIR | Use fareopt aggregation in dashboard | Corrected code and commit , discussion with Dhanesh |  | 0.5 | 0
ST | Tuesday | 2015-03-24 |  | Planning | internal |  |  | Daily updates + discussions | Plan for DB team and discussions | 1.5
ST | Tuesday | 2015-03-24 | 8463 | Maintenance | discussion | 2.7 | Hotel | [EXPEDIA] Afidium web service error | Discussion with JS, AF | 0.5
ST | Tuesday | 2015-03-24 | 8480 | Discussion | internal |  | Stock | Update PNR (Passive Booking) on booking | Discussion with Uma | 0.5
ST | Tuesday | 2015-03-24 | 8376 | Discussion | internal |  | AIR | AIR DB Cleanup | Call with Anne and Dhanesh | 1
ST | Tuesday | 2015-03-24 |  | Planning | internal |  |  | Call with David for DB team work |  | 0.5
ST | Tuesday | 2015-03-24 |  | Discussion | internal |  | Hotel | Answer to testing team for email for COT | email, call if possible | 0.5
ST | Tuesday | 2015-03-24 | 8489 | Discussion | internal |  | Stock | Add booking id/ref column in bkg_log table | discussion with Uma | 0.5
ST | Tuesday | 2015-03-24 | 8442 | Analysis |  |  | Stock | [Query][DB] Create table and SPs for SearchQuery | Analysis, code review | 1.5
ST | Wednesday | 2015-03-25 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
ST | Wednesday | 2015-03-25 | 7639 | New | Replication |  | Hotel | Test replication on new server |  | 1
ST | Wednesday | 2015-03-25 | [5 empty] | Free to allocate |  | 4.5
ST | Thursday | 2015-03-26 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
ST | Thursday | 2015-03-26 | 7639 | New | Replication |  | Hotel | Test replication on new server |  | 1
ST | Thursday | 2015-03-26 | [5 empty] | Free to allocate |  | 4.5
ST | Friday | 2015-03-27 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
ST | Friday | 2015-03-27 | 7639 | New | Replication |  | Hotel | Test replication on new server |  | 1
ST | Friday | 2015-03-27 | [5 empty] | Free to allocate |  | 4.5
UZ | Monday | 2015-02-02 | 8287 | Training |  |  | Stock | KT on Stock Database | Study + call with ST for queries + updates | 5.5 | 5.5 | 1 | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Monday | 2015-02-02 | 8249 | New | pgsql |  | Stock | Core module migration |  | 0.5 | 0.5 | 0
UZ | Tuesday | 2015-03-03 | 8287 | Training |  |  | Stock | KT on Stock Database |  | 5.5 | 5.75 | 1
UZ | Tuesday | 2015-03-03 |  | Planning | internal |  |  | Planning for work | Call with ST | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-03-03 | 8249 | New | pgsql |  | Stock | Core module migration |  | 0.5 | 0 | -1
UZ | Wednesday | 2015-02-04 | 8344 | New | pgsql |  | Stock | SP "sto_journey__search" is slow | check existing SPs & created SPs | 1 | 1 | 0
UZ | Wednesday | 2015-02-04 | 8287 | Training |  |  | Stock | KT on Stock Database |  | 5 | 5 | 1
UZ | Thursday | 2015-02-05 | 8359 | New | pgsql |  | Stock | Modify dic functions | Modified some functions | 0.75 | 0.75 | 0
UZ | Thursday | 2015-03-05 | 8287 | Training |  |  | Stock | KT on Stock Database | Call with ST+DM, Study | 5.25 | 5.25 | 1
UZ | Friday | 2015-02-06 | 8287 | Training |  |  | Stock | KT on Stock Database | call with ST + study | 2.5 | 2.5 | 1
UZ | Friday | 2015-02-06 | 8359 | New | pgsql |  | Stock | Modify dic functions | modification + coordination with TC + created DB | 3.5 | 3.5 | 1
UZ | Monday | 2015-03-09 | 8359 | New | pgsql |  | Stock | Modify dic functions | Task updated | 0.5 | 0.75 | 1
UZ | Monday | 2015-03-09 | 8367 | New | pgsql |  | Stock | Modify sys functions | Create task + query to AR | 0.75 | 0.75 | 1
UZ | Monday | 2015-03-09 | 7639 | New | Replication |  | Hotel | New server setup | Created script for 2.7,2.8,2.9 DB + install manegement studio 2014 | 3 | 4 | 0
UZ | Tuesday | 2015-03-10 | [5 empty] | leave
UZ | Wednesday | 2015-03-11 | 8359 | New | pgsql |  | Stock | Modify dic functions | add hist comment + add in related file + test + commite | 1 | 1 | 0
UZ | Wednesday | 2015-03-11 | 7639 | New | Replication |  | Hotel | setup of replication activity | remove unwanted table/sps & create 2.9 DB | 1.75 | 1.75 | 0
UZ | Wednesday | 2015-03-11 | 8367 | New | pgsql |  | Stock | modify sys functions | call with ST + modification | 1.5 | 1.75 | 0
UZ | Thursday | 2015-03-12 | 7639 | New |  |  | Hotel | setup of replication activity | create 2.9 DB + call with ST | 0.5 | 1.5 | 0
UZ | Thursday | 2015-03-12 | 8359 | New | pgsql |  | Stock | Modify dic functions | testing | 3 | 3 | 1
UZ | Thursday | 2015-03-12 | 8367 | New | pgsql |  | Stock | modify sys functions | modification | 1.5 | 1.25 | 0
UZ | Thursday | 2015-03-12 |  | Discussion |  |  |  | Discussions with Dhanesh | Help Dhanesh for wiki + hide code in task |  | 0.25 | 1
UZ | Friday | 2015-03-13 | 8369 | New | pgsql |  | Stock | implement SPs to update only what has changed |  | 5.25 | 0 | -1
UZ | Friday | 2015-03-13 | 7639 | New | Replication |  | Hotel | setup of replication activity | delete + re-create 2.9 DB, run insert generator script for basic data | 0.75 | 1.5 | 1
UZ | Friday | 2015-03-13 | 8367 | New | pgsql |  | Stock | modify sys functions | modified functions + Need to test |  | 4.5 | 0
UZ | Monday | 2015-03-16 |  | Planning | internal |  |  | Weekly planning + discussion |  | 0.5 | 0.25 | 1
UZ | Monday | 2015-03-16 | 8369 | New | pgsql |  | Stock | implement SPs to update only what has changed | call with ST | 5.5 | 0.5 | 1
UZ | Monday | 2015-03-16 | 8367 | New | pgsql |  | Stock | Modify sys functions | testing |  | 2 | 0
UZ | Monday | 2015-03-16 | 7639 | New | Replication |  | Hotel | Setup of Replication Activity | generated script for basic data + inserted data+ call with ST |  | 3.5 | 1
UZ | Tuesday | 2015-03-17 | 7639 | New | Replication |  | Hotel | Replication setup on new server | Commit the scripts for new db creation and base data insertion in hg | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-03-17 |  | Planning | internal |  |  | Daily updates + discussions | call with ST for today's work | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-03-17 | 8427 | new |  |  | Hotel | Automation of hotel & VDM synchro test | Create SP + test | 5 | 5 | 1
UZ | Tuesday | 2015-03-17 | 8367 | New | pgsql |  | Stock | Modify sys functions | Update task | 0.25 | 0.25 | 1
UZ | Wednesday | 2015-03-18 | 8367 | New | pgsql |  | Stock | Modify sys functions | Complete sys_alert__list coding and testing | 2.5 | 2 | 1
UZ | Wednesday | 2015-03-18 | 8359 | New | pgsql |  | Stock | Modify dic functions | testing |  | 0.5 | 1
UZ | Wednesday | 2015-03-18 | 8395 | New | pgsql |  | Stock | Improve stats speed | study SP + discussion with Anne |  | 1 | 1
UZ | Wednesday | 2015-03-18 | 8287 | Training | pgsql |  | Stock | KT on Stock Database | Study bkg_booking function | 2.5 | 2 | 0
UZ | Wednesday | 2015-03-18 |  | Planning | internal |  |  | Call with ST |  |  | 0.5 | 1
UZ | Wednesday | 2015-03-18 |  |  | pgsql |  | Stock | Booking change for V1.1 | Coding and Testing in coordination with ST | 1 | 0 | -1
UZ | Thursday | 2015-03-19 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.25 | 1
UZ | Thursday | 2015-03-19 | 8359 | New | pgsql |  | Stock | Modify dic functions | Testing |  | 0.5 | 0
UZ | Thursday | 2015-03-19 | 8460 | New | Documentation |  | Stock | Booking + Winter | created daigram for tables & SPs used in booking_update SP |  | 1 | 1
UZ | Thursday | 2015-03-19 | 8287 | Training | internal |  | Stock | Booking change for V1.1 | KT+Study | 5.5 | 4 | 1
UZ | Friday | 2015-03-20 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.25 | 1
UZ | Friday | 2015-03-20 |  |  |  |  | Stock | Booking change for V1.1 | Coding and Testing in coordination with ST | 2 | 0 | -1
UZ | Friday | 2015-03-20 | 8369 |  | pgsql |  | Stock | Update SPs : implement SPs to update only what has changed | Analysis and Proposal Document | 3.5 | 0 | -1
UZ | Friday | 2015-03-20 | 8287 | Training | internal |  | Stock | KT on Stock Database | KT + Study |  | 3 | 1
UZ | Friday | 2015-03-20 | 8460 | New |  |  | Stock | Booking + Winter | Created Daigram for tables & SPs used in booking__replace SP |  | 0.75 | 1
UZ | Friday | 2015-03-20 | 7639 | New | Replication |  | Hotel | Setup of Replication Activity | Create wenji_log_2.9 DB & insert basic data in all wenji DB |  | 1 | 1
UZ | Friday | 2015-03-20 | 8359 | New | pgsql |  | Stock | Modify dic functions | Testing |  | 0.25 | 1
UZ | Friday | 2015-03-20 | 8367 | New | pgsql |  | Stock | Modify sys functions | Task updated |  | 0.25 | 1
UZ | Monday | 2015-03-23 |  | Planning | internal |  |  | Weekly planning with ST |  | 1
UZ | Monday | 2015-03-23 | [5 empty] | Free to allocate |  | 5
UZ | Tuesday | 2015-03-24 |  | Planning | internal |  |  | Daily status update |  | 0.5
UZ | Tuesday | 2015-03-24 | [5 empty] | Free to allocate |  | 5.5
UZ | Wednesday | 2015-03-25 |  | Planning | internal |  |  | Daily status update |  | 0.5
UZ | Wednesday | 2015-03-25 | [5 empty] | Free to allocate |  | 5.5
UZ | Thursday | 2015-03-26 |  | Planning | internal |  |  | Daily status update |  | 0.5
UZ | Thursday | 2015-03-26 | [5 empty] | Free to allocate |  | 5.5
UZ | Friday | 2015-03-27 |  | Planning | internal |  |  | Daily status update |  | 0.5
UZ | Friday | 2015-03-27 | [5 empty] | Free to allocate |  | 5.5