## JS
Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment
Tuesday | 2014-11-25 | 7003 | Maintenance | AFI | Hotel | EXP CHD Price correction | Execute script daily on prod | 0.1 | 0.1 | 1 | 5 mins
Tuesday | 2014-11-25 | 7401 | Maintenance | AFI | Hotel | Multiple quotations for tourplan | Finish script writing + unit test. Start on precache | 3 | 3 | 0 | Wrote scripts + unit tested in 3H. Started the data correction on precache afterwards.
Tuesday | 2014-11-25 | 7458 | Maintenance | AFI | Hotel | Check ATI GQA Error on Prod | Check, discuss with CC and fix | 1 | 0.5 | 0 | Confirm with CC that this is only ATI Test env behavior and we do not need to change anything
Tuesday | 2014-11-25 | 7242 | Maintenance | Host | Hotel | JNV format change | Analyse + document + propose solution + discuss with AF/ CC | 4 | 2.5 | 0 | To AF as I could not understand it clearly. Later had a call with AF about it
Tuesday | 2014-11-25 |  | Coordination |  | Hotel | Coordination with Uma | Discuss assigned task + answer questions | 0.5 | 0.5 | 1
Tuesday | 2014-11-25 |  | Coordination |  | Hotel | Call with AF, ST for 2.9 |  | 1 | 1 | 1
Tuesday | 2014-11-25 | 6797 | New |  | Air | CQA | Check CQA SF issue |  | 2 | 0 | Understood SF problem. Had planned for Wednesday, but because I saved time on 7242, took it up
Wednesday | 2014-11-26 | 7003 | Maintenance | AFI | Hotel | EXP CHD Price correction | Execute script daily on prod | 0.1 | 0.1 | 1 | 5 mins
Wednesday | 2014-11-26 |  | Maintenance | AFI | Hotel | EXP 300 patch + verification + wiki update |  | 0.5 | 0.5 | 1
Wednesday | 2014-11-26 |  | Maintenance | AFI | Hotel | 104 - update and test native test utility, reschedule EXP GT, check servers, created 7490 |  |  | 0.5 | 1 | Unplanned
Wednesday | 2014-11-26 |  | Coordination |  | Hotel | Call with Uma to explain 2.9 tasks that she may expect in next 2 days |  | 1 | -1 | -1
Wednesday | 2014-11-26 | 7401 | Maintenance | AFI | Hotel | Multiple quotations for tourplan | Finish tests on precache. Prepare patch | 2.5 | 3 | 1
Wednesday | 2014-11-26 | 6797 | New |  | Air | CQA | Finish CQA and test | 2.5 | 0.25 | 0 | Started but could not finish
Wednesday | 2014-11-26 | 7242 | Maintenance | Host | Hotel | JNV format change | Implement solution as discussed with Anne + Test | 1 | 0.25 | 0
Wednesday | 2014-11-26 |  | Coordination |  |  | Status update from logirythm team |  | 0.5 | 1.5 | 1 | Took more time as I prepared the sheet for all and explained them how we will do it.
Wednesday | 2014-11-26 |  | New |  | Hotel | Go through VDM synchro wiki by AF and prepare tasks for UZ |  | 1 | -1 | -1
Wednesday | 2014-11-26 | 7490 | Maintenance | AFI | Hotel | Tourplan update problem | Fix XSL + test, discuss with Anne to patch with 7260, 7401 | 1 | 2 | 1 | To AF for decision to include on precache + prod patch. The reported problem was fixed within time but I found another issues of loading texts correctly - which took more time. DF said this correction can wait till 2.8.
Thursday | 2014-11-27 | 7003 | Maintenance | AFI | Hotel | EXP CHD Price correction | Execute script daily on prod | 0.1 | -1 | -1 | Could not start with post processing in processing state
Thursday | 2014-11-27 |  | Coordination |  | Hotel | Call with Uma to explain 2.9 tasks that she may expect in next 2 days |  | 1 | 1 | 1
Thursday | 2014-11-27 | 7401 | Maintenance | AFI | Hotel | Multiple quotations for tourplan | Prepare patch | 1 | 0.5 | 0 | Created 2.7 version of SPR XSL. Applied on precache, to test after pool recycle
Thursday | 2014-11-27 | 7500 | New |  | Hotel | Go through VDM synchro wiki by AF and prepare tasks for UZ |  | 2 | 4 | 1
Thursday | 2014-11-27 | 6797 | New |  | Air | CQA | Finish CQA and test | 4 | 4 | 1 | Have some doubts about my changes. Need CC's opinion
Thursday | 2014-11-27 |  | Coordination |  |  | Status update from logirythm team |  | 0.5 | 0.5 | 0.5
Friday | 2014-11-28 | 7513 | Maintenance | AFI | Hotel | JNV tarif occupancy problem |  |  | 3.5 | 1 | Corrected and tested for 2.7 and 2.8 + patch creation. UNPLANNED
Friday | 2014-11-28 | 7500 | New |  | Hotel | More tasks for Uma + JS |  | 1.5 | 0.5 | 0 | Not feeling well. Stopping for the day
Friday | 2014-11-28 | 7242 | Tests | 2.8 | Hotel | XSL change for JNV price xsl | change XSL + test | 1 | 0.5 | 1
Friday | 2014-11-28 | 7435 | Tests | 2.8 | Hotel | GTA Markup search issue | Check, discuss with AF, fix , test | 2 | 1 | 1
Friday | 2014-11-28 |  | Coordination |  |  | Status update from logirythm team |  | 0.5 | 0.5 | 1 | Not with ST
Friday | 2014-11-28 | 7003 | Maintenance | AFI | Hotel | EXP CHD Price correction | Execute script daily on prod | 0.1 | 0.1 | 1
Friday | 2014-11-28 | 7246 | Tests | 2.8 | Hotel | EXP GT Issue |  | 3 | 0 | -1
| 2014-11-28 | 7315 | Tests | 2.8 | Hotel | Check dashboard speed problem |  | 1
| 2014-11-28 | 7104 | New |  | Air | UB for TAU | Continue on UB with CheckBooking + test | 4
| 2014-11-28 |  | New |  | Hotel | Check problems with tourplan Focussed updates. Propose solution, discuss with AF |  | 4
For next week

## PS
Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment
Tuesday | 2014-11-25 | 7413 | New | Documentation | TUI | Documentation |  |  | 6 | 0 | SA RQ doc + RNG First documentation took time
Tuesday | 2014-11-25 |  | Coordination |  |  | Coordinate with PLS, DD |  |  | 1.5 | 1 | About villa nomade, TUI testgrid,
Tuesday | 2014-11-25 |  | Maintenance | AFI |  | Production operational test |  |  | 0.5 | 1
Wednesday | 2014-11-26 | 7413 | New | Documentation | TUI | Documentation | XB, GB, SB, SA RS | 7 | 8 | 0 | XB RQ RS - doc + RNG done GB RQ - doc + RNG done GB RS needs a lot of changes for RNG SB, SA RS - not started
Wednesday | 2014-11-26 |  | Coordination |  |  | Coordinate with PLS, DD |  | 0.5 | 0.5 | 1
Wednesday | 2014-11-26 |  | Maintenance | AFI |  | Production operational test |  | 0.5 | 0.25 | 1
Thursday | 2014-11-27 | 7413 | New | Documentation | TUI | Documentation | GB RS, CB, SA | 7 | 8 | 1 | reprioritized after PS discussion with CC
Thursday | 2014-11-27 |  | Coordination |  |  | Coordinate with PLS, DD |  | 0.5 | 0 | -1
Thursday | 2014-11-27 |  | Maintenance | AFI |  | Production operational test |  | 0.5 | 0 | -1
Friday | 2014-11-28 | 7413 | New | Documentation | TUI | Documentation | GQ, SQA | 7.5 | 7.5 | 1
Friday | 2014-11-28 |  | Maintenance | AFI |  | Production operational test |  | 0.5 | 0.5 | 1
UB + SB + queue related
To be done in next week
leave - 1st Dec
leave - 5th - 14th Dec

## TS
Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment
Tuesday | 2014-11-25 | 7299 | New | Documentation | TUI | Wiki documentation |  |  | 3.5 | 1
Tuesday | 2014-11-25 |  | Maintenance | AFI |  | Weekly updates |  |  | 1 | 1
Tuesday | 2014-11-25 | 7265 | Maintenance | AFI |  | Redmine user creations |  |  | 0.5 | 1
Tuesday | 2014-11-25 |  | New | Documentation |  | Prd - en doc updates - Air |  |  | 3 | 1
Wednesday | 2014-11-26 | 7299 | New | Documentation | TUI | Wiki documentation |  | 5 | 4.5 | 0
Wednesday | 2014-11-26 |  | Maintenance |  |  | updates, follow up, reminders |  | 1.5 | 0.75 | 0 | Did not do reminders.
Wednesday | 2014-11-26 |  | New | Documentation |  | Prd - doc - Air |  | 1.5 | 1.5 | 1
Wednesday | 2014-11-26 |  | Coordination |  |  | Call with JS for weekly plan |  |  | 0.75 | 1
Wednesday | 2014-11-26 |  | Coordination |  |  | Call with Uma |  |  | 0.5 | 1
Thursday | 2014-11-25 | 7299 | New | Documentation | Corsair | Wiki documentation |  | 6 | 9 | 1
Thursday | 2014-11-27 |  | Maintenance |  |  | VDM - Hotel meeting preparation |  | 1 | 0 | -1
Thursday | 2014-11-27 |  | New | Documentation |  | Prd - doc - Air |  | 1 | 0 | -1
Friday | 2014-11-28 |  | New | Documentation | TUI | TUI & TUI group documentation |  | 3 | 3 | 1
Friday | 2014-11-28 |  | Maintenance |  |  | Task maintenance Wnj |  | 2 | 2 | 1
Friday | 2014-11-28 |  | Maintenance |  |  | VDM - Hotel meeting preparation |  | 1 | 1 | 1
Friday | 2014-11-28 |  | Maintenance |  |  | Weekly - updates |  | 0.5 | 0.5 | 1
Friday | 2014-11-28 |  | Maintenance |  |  | Meetings - follow up |  | 1 | 0.5 | 0
Friday | 2014-11-28 |  | Maintenance |  |  | Htl - Release notes |  | 1 | 1 | 1
Friday | 2014-11-28 |  | New | Documentation |  | Prd - doc - Air |  | 2
Friday | 2014-11-28 |  | Maintenance |  |  | Cli - Tasks follow up |  | 2
Friday | 2014-11-28 |  | Maintenance |  |  | Validation of work |  | 1
Next week

## UZ
Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment
Tuesday | 2014-11-25 | 6281 | New |  | Hotel | Configure cleanup tarif dates | Test | 2 | 3 | 1
Tuesday | 2014-11-25 | 7337 | Maintenance | Documentation | Hotel | Update spUploadAvailability doc | wiki for uploadAvailability | 2 | 1 | 0
Wednesday | 2014-11-26 | 7337 | Maintenance | Documentation | Hotel | Update documentation | Finish wiki for uploadAvailability + start dashboard SPs | 2 | 2.5 | 1
Wednesday | 2014-11-26 | 6281 | New |  | Hotel | Configure cleanup tarif dates | Documentation | 1 | 1 | 1
Wednesday | 2014-11-26 |  | Coordination |  |  | Call with Jyotsna for synchro SP + dashboard |  | 1 | 0 | -1
Wednesday | 2014-11-26 |  | Coordination |  |  | Call with Jyotsna for weekly hours |  |  | 0.5 | 1
Thursday | 2014-11-27 | 7337 | Maintenance |  | Hotel | Study dashboard SPs + update documentation |  | 1 | 1.5 | 1
Thursday | 2014-11-27 | 7264 | Tests | 2.8 | Hotel | Check dashboard problem in validation |  | 2 | 0.5 | -1 | Tried to understand but not clear
Thursday | 2014-11-27 |  | Coordination |  |  | Call with Jyotsna for synchro SP + dashboard |  | 1 | 1 | 1
Thursday | 2014-11-27 |  |  |  |  | Study existing hotel synchro SPs |  |  | 1 | 1
Friday | 2014-11-28 | 7503 | New | 2.9 | Hotel | Table changes | Change tables + list places where brand blis + binary are used + wiki | 4 | 4 | 1

## ST
Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment
Tuesday | 2014-11-25 | 7440 | New |  | Stock | Fix bkg_booking__replace function | Analysis and Coding | 3 | 2.25 | 1
Tuesday | 2014-11-25 | 7335 | New |  | Stock | Migrate from TC version's to ST version (quotation, booking and WINTER) | Corrected hg files, Booking update is working properly | 0.5 | 0.75 | 1
Tuesday | 2014-11-25 |  | Coordination |  | Stock | With YT | Testing of booking update | 0.5 | 0.5 | 1
Tuesday | 2014-11-25 |  | Coordination |  | Stock | Call with AF for combined quotation |  | 1 | 1 | 1
Tuesday | 2014-11-25 |  | Coordination |  | Hotel | Call with AF JS for 2.9 |  | 1 | 1 | 1
Wednesday | 2014-11-26 | 7466 | New |  | Stock | Support AR quotations using A+R stocks |  | 3 | 4 | 1
Wednesday | 2014-11-26 | 7480 | New |  | Stock | Fixed SP for booking |  | 2 | 1 | 1
Wednesday | 2014-11-26 |  | Coordination |  | Stock | Discussion about Combine Quotation with AF and AR |  | 1 | 1 | 1
Thursday | 2014-11-27 | 7466 | New |  | Stock | Support AR quotations using A+R stocks |  | 4 | 4 | 1
Thursday | 2014-11-27 |  | Coordination |  | Stock | Discussion about Combine Quotation |  | 1 | 1 | 1
Thursday | 2014-11-27 |  | Maintenance |  | Hotel | Check Post processing on production |  | 0.5 | 0.5 | 1
Friday |  |  |  |  | Stock | Call with Anne - stock |  | 0.5 | 0.5 | 1
Friday | [5 empty] | Leave
Friday | [5 empty] | Leave
Saturday | 2014-11-29 | 7466 | New |  | Stock | Support AR quotations using A+R stocks | Table structure + analysis for booking replace |  | 3 | 1
Sunday | 2014-11-30 | 7466 | New |  | Stock | Support AR quotations using A+R stocks | Booking replace coding |  | 6 | 1
[5 empty] | 7466 | Estimate not clear yet. May need time in next week as well
ST does not have confirmations about structure changes
The logic is complicated and ST is thinking about it and not completely clear