## Consolidated
Initials | Day | Date | Task | Category | sub-category | Project | Task description | Next action | Planned time | Actually spent | Status | Comment | Important information
JS | Thursday | 2015-01-01 |  | Leave | [8 empty] | Leaves : 2015-02-03 - 4 hours. Work from 8-12 2015-02-16 - 2015-02-22 2015-04-03 - 2015-04-12
JS | Friday | 2015-01-02 | 7592 | new | 2.9 | Hotel | Call with Anne + SP changes | SE transaction code + test. SPR SP change |  | 4 | 1
JS | Friday | 2015-01-02 |  |  |  | Hotel | Call with Shweta |  |  | 1 | 1
JS | Friday | 2015-01-02 |  |  |  | Hotel | Call with PS , Uma |  |  | 0.5 | 1
JS | Friday | 2015-01-02 | 7744 |  |  | Hotel | Correct ref_afidium data on Sd-29142 for VDM tests |  |  | 1 | 1
JS | Friday | 2015-01-02 | 5571 | New | 2.9 | Hotel | Tourplan focussed update - mixed files check |  |  | 1 | 1
JS | Friday | 2015-01-02 | 7744 | new | 2.9 | Hotel | GTA tests for CB RS room code |  |  | 0.25 | 1
JS | Friday | 2015-01-02 | 7435 | new | 2.8 | Hotel | GTA markup logic change - code + test |  |  | 0.5 | 1
JS | Monday | 2015-01-05 |  |  | AFI |  | Weekly planning call |  |  | 0.5 | 1
JS | Monday | 2015-01-05 | 7592 |  |  |  | Call with Anne - new format + vdm booking + galaxyref |  |  | 0.5 | 1
JS | Monday | 2015-01-05 |  |  |  |  | Call with ST, PS, UZ for weekly planning + task discussions |  |  | 3 | 1
JS | Monday | 2015-01-05 | 7689 | new | 2.9 | Hotel | Discussion with CC PS AF | VDM CB details, Create Option |  | 0.5 | 1
JS | Monday | 2015-01-05 | 7592 | new | 2.9 | Hotel | SPR, SQA SP + format changes | code + unit tests + corrections to other SPs + tests |  | 4 | 0
JS | Monday | 2015-01-05 | 7435 | new | 2.8 | Hotel | Support PS for tests for GTA markup |  |  | 0.25 | 1
JS | Monday | 2015-01-05 | 7805 | Tests | 2.9 | Hotel | Populate VDM data in DB + data correction |  |  | 1 | 1
JS | Tuesday | 2015-01-06 | 7500 | New | 2.9 | Hotel | Test SQA + data in 2.9 |  | 2 | 1 | 0
JS | Tuesday | 2015-01-06 | 7779 | Maintenance |  | Hotel | Check issue + inform CC | Checked data. Do not see any problem. Need CC help to understand query/problem | 2 | 1 | 1 | CC confirmed it is not a bug
JS | Tuesday | 2015-01-06 | 7629 | Maintenance |  | Hotel | Explain CC - give more details |  | 0.5 | 0.5 | 1
JS | Tuesday | 2015-01-06 | 7777 | Maintenance |  | Hotel | Check duplicate data found by ST |  | 3 | 3.5 | 1
JS | Tuesday | 2015-01-06 |  |  |  |  | Call with AF , ST |  |  | 1.25 | 1
JS | Tuesday | 2015-01-06 | 7841 | Maintenance | 2.7 | Hotel | Checked issue |  |  | 0.5 | 1
| Tuesday | 2015-01-06 | 7689 | new | 2.9 | Hotel | VDM CO change | analysis + change |  | 0.5 | 1
JS | Tuesday | 2015-01-06 |  |  |  |  | Daily status updates + discussions |  | 0.5 | 1 | 1
JS | Wednesday | 2015-01-07 | 7500 | new | 2.9 | Hotel | Wiki updates + organize documentation + test |  | 2 | 2 | 0 | Tested but need more time for organizing documentation properly
JS | Wednesday | 2015-01-07 | 7841 | new |  | Hotel | Check and fix | Marking new because problem is not because of our code. Still we can improve our code to reduce dependency on them | 2 | 1.5 | 1 | Not a bug but improvement
JS | Wednesday | 2015-01-07 |  |  |  |  | Daily stuatus updates + discussions |  | 1 | 1 | 1
JS | Wednesday | 2015-01-07 | 7759 | new | 2.9 | Hotel | phase 2 analysis + tasks for UZ |  |  | 0.75 | 1
JS | Wednesday | 2015-01-07 | 7689 | new | 2.8 | Hotel | VDM CO - check problem reported by PS + fix |  |  | 0.5 | 1
JS | Wednesday | 2015-01-07 | 7924 | new | 2.7 | Hotel | Discussion with CC for PPT to VDM + check on precache | Checked on precache |  | 1.25 | 1
JS | Wednesday | 2015-01-07 |  |  | AFI |  | Daily call |  |  | 0.3 | 1
JS | Wednesday | 2015-01-07 | 7845 | new | 2.9 | Hotel | Checked issue. Not problem in code but in galazy DB |  |  | 0.25 | 1
JS | Wednesday | 2015-01-07 | 7801 | new |  | TUI | Implement List Seat transaction | brief from CC + code + test | 3 | 0.5 | 0
JS | Thursday | 2015-01-08 | 7801 | new |  | TUI | Implement List Seat transaction | coded C# to exec from sequencer. Will test after XSLIN is ready for ListSeat | 4 | 5 | 1
JS | Thursday | 2015-01-08 | 7744 | new | 2.9 | Hotel | linked server error check + fix |  |  | 0.25 | 1
[7 empty] | Call with CC + daily call AFI |  |  | 0.5 | 1
JS | Thursday | 2015-01-08 | 7846 7847 | new | 2.9 | Hotel | SQA, SPR issue fixes | check + discuss + fix | 1.5 | 1.5 | 1
JS | Thursday | 2015-01-08 |  |  |  |  | Daily status update + discussions + planning |  | 1 | 1 | 1
JS | Thursday | 2015-01-08 |  | Maintenance |  | Hotel | Check SQA speed on precache |  | 1.5 | 1.5 | 0
JS | Friday | 2015-01-09 | 7515 | new | 2.9 | Hotel | nvarchar fields | code + test | 2 | 0 | -1 | For next week
JS | Friday | 2015-01-09 |  |  |  |  | SQA Speed on precache |  | 1 | 0.5 | 1
JS | Friday | 2015-01-09 | 7863 | Maintenance |  | Air | Run queries for portugese clients |  | 1.5 | 1 | 1
JS | Friday | 2015-01-09 |  |  |  |  | documentation organization for phase 1, 2 | Template creation + task for tazeen for assistance |  | 0.5 | 0
JS | Friday | 2015-01-09 | 7860 | new | 2.9 | Hotel | Hotel closed dates implementation | code + test done. Wiki in progress | 3.5 | 3.5 | 0 | SPR SQA documentation to do after import is done
JS | Friday | 2015-01-09 | 7246 | Tests | 2.8 | Hotel | EXP GT problem reason + proposed solution |  |  | 0.5 | 0 | Planning for Monday
JS | Friday | 2015-01-09 | 7500 |  | 2.9 | Hotel | Preferred bit implementation + test | tested by creating data for 1 hotel (3003838) |  | 0.75 | 1
JS | Friday | 2015-01-09 |  |  |  |  | Daily status update call |  | 0.5 | 0.5 | 1
JS | Friday | 2015-01-09 |  |  |  |  | Discussions - CC, AF, PS, UZ |  |  | 0.5 | 1
JS | Friday | 2015-01-09 |  |  |  |  | Daily AFI call |  |  | 0.25 | 1
JS | Friday | 2015-01-09 | 7837 + 7838 | new | 2.9 | Hotel | test + fix Uma's tasks for se_hvendor_at import |  | 1.5 | 0 | -1
JS | Monday | 2015-01-12 | 7246 |  |  |  | EXP GT improvement | code + test | 5 | 3 | 0 | started tests on devcache
JS | Monday | 2015-01-12 |  |  |  |  | devcache space check |  |  | 0.5 | 1
JS | Monday | 2015-01-12 | 7837 + 7838 | new | 2.9 | Hotel | test + fix Uma's tasks for se_hvendor_at import |  |  | 2.25 | 1
JS | Monday | 2015-01-12 | 7675 | Tests | 2.8 | Hotel | availability for VDM validation + start processes on devcache |  |  | 0.5 | 1
JS | Monday | 2015-01-12 |  |  |  |  | Weekly planning - PS, UZ |  | 2 | 2 | 1
JS | Monday | 2015-01-12 |  |  |  |  | Discussion - TZ for wiki organization |  | 0.5 | 0 | -1
JS | Monday | 2015-01-12 |  |  |  |  | Weekly planning call - AFI |  | 0.5 | 0.75 | 1
JS | Tuesday | 2015-01-13 | 7759 | new | 2.9 | Hotel | Create test data + change SPs to use se_currency correctly | Created test data | 2 | 1 | 0
JS | Tuesday | 2015-01-13 | 7246 |  |  |  | EXP GT improvement | Monitor devcache + SP improvement | 1 | 0 | -1
JS | Tuesday | 2015-01-13 | 7675 | Tests | 2.8 | Hotel | Generate fresh availability data for TRP, JNV |  | 1 | 0 | -1
JS | Tuesday | 2015-01-13 | 7924 | new | 2.7 | Hotel | PPT to VDM migration | script + time measurements | 1 | 0.5 | 0
JS | Tuesday | 2015-01-13 |  |  |  |  | Check new server |  | 1 | 0.5 | 1
JS | Tuesday | 2015-01-13 | 6903 | Maintenance | 2.7 | Hotel | Write script for cleaning tarifs | Wrote script, determining figures on precache |  | 2 | 0
JS | Tuesday | 2015-01-13 |  |  |  |  | VDM synchro on all servers |  |  | 1 | 1
JS | Tuesday | 2015-01-13 |  |  |  |  | Daily call - AFI |  |  | 0.5 | 1
JS | Tuesday | 2015-01-13 | 7923 | Maintenance | 2.7 | Hotel | Check hotel synchro problem | corrected + tested problem for 2.8 + discussion with Anne | 1 | 3 | 1
JS | Tuesday | 2015-01-13 |  |  |  |  | status updates + discussions |  | 1 | 0.5 | 1
JS | Wednesday | 2015-01-14 | 7843 | new | 2.9 | Hotel | Test markup modification by UZ + bug fix | started getting data in sm_searchengine_2.9 | 1.5 | 0.25 | 0
JS | Wednesday | 2015-01-14 | 6903 | Maintenance | 2.7 | Hotel | Continue tests + time measurements for clearnup |  | 1 | 0.5 | 0
JS | Wednesday | 2015-01-14 | 7902 | new | 2.10 | Hotel | phase 3 analysis |  | 2 | 2 | 1
JS | Wednesday | 2015-01-14 |  |  |  |  | Check VDM lot + monitor updates + check data |  |  | 0.5 | 1
JS | Wednesday | 2015-01-14 | 7925 | new |  | Hotel | Check impact of GTA changes | and check PPT data |  | 0.75 | 1
JS | Wednesday | 2015-01-14 | 7631 | Maintenance |  | Hotel | Checked CC comment. Asked PS to check |  |  | 0.5 | 0
JS | Wednesday | 2015-01-14 | 6223 | Tests | 2.8 | Hotel | Test the transaction logging. If no improvement - revert |  | 1 | 0 | -1
JS | Wednesday | 2015-01-14 | 7653 |  | 2.9 | Hotel | Test UZ changes in other SPs to use se2_at |  | 1.5 | 1.5 | 1
JS | Wednesday | 2015-01-14 |  | new | 2.9 | Hotel | Guide Uma for server setup |  | 0.5 | 0 | -1
JS | Wednesday | 2015-01-14 |  |  |  |  | Discussions + daily updates |  | 0.5 | 0.75 | 1
JS | Wednesday | 2015-01-14 |  | new | 2.10 | Hotel | Call with AF - testing + phase 3 |  | 0.5 | 1 | 1
JS | Thursday | 2015-01-15 | 7643 | new | 2.9 | Hotel | Test tourplan update data |  | 1 | 0 | -1
JS | Thursday | 2015-01-15 | 7787 | new | 2.9 | Hotel | Test JNV update data |  | 1 | 0 | -1
JS | Thursday | 2015-01-15 | 6903 | Maintenance | 2.7 | Hotel | Continue tests + time measurements for clearnup |  | 1 | 0.5 | 0
|  |  | 7843 | new | 2.9 | Hotel | Test markup modification by UZ + bug fix |  | 1.5 | 2 | 1
JS | Thursday | 2015-01-15 | 6223 | Tests | 2.8 | Hotel | Test the transaction logging. If no improvement - revert |  | 1 | 0 | -1
JS | Thursday | 2015-01-15 |  |  |  |  | status updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-01-15 | 7391 |  | 2.9 | Hotel | Tests - CB error - booking reference | To PLS to find some cases | 0.5 | 0 | -1
JS | Thursday | 2015-01-15 |  |  |  | Hotel | VDM debriefing call with CC, AF |  | 0.5 | 0 | -1 | AF not available
JS | Thursday | 2015-01-15 | 7767 7768 | new | 2.9 | Hotel | Test ST work for reducing data size during post processing + extrapolation |  | 2.5 | 0 | -1
JS | Friday | 2015-01-16 | 7515 | new | 2.9 | Hotel | nvarchar fields | code + test | 2 | 0.5 | 1 | With analysis to AF
JS | Friday | 2015-01-16 | 7490 | Tests | 2.8 | Hotel | semicolon replacement - need AF advise for changing existing implementation |  |  | 0.25 | 0
JS | Friday | 2015-01-16 | 7643 | new | 2.9 | Hotel | Test tourplan update data |  | 1 | 2 | 1
JS | Friday | 2015-01-16 | 6903 | Maintenance | 2.7 | Hotel | Continue tests + time measurements for clearnup | changed script for GTA + executed |  | 1 | 0
JS | Friday | 2015-01-16 | 7787 | new | 2.9 | Hotel | Test JNV update data |  | 0.5 | 1 | 1
JS | Friday | 2015-01-16 | 7767 7768 |  |  |  | Test ST work for reducing data size during post processing + extrapolation | Test + change code + vdm extrapolation code change | 1.5 | 2.5 | 0
JS | Friday | 2015-01-16 | 7391 |  | 2.9 | Hotel | Tests - CB error - booking reference |  | 1 | 0 | -1
JS | Friday | 2015-01-16 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.75 | 1
JS | Monday | 2015-01-19 | 7964 | Maintenance | 2.7 | Hotel | Check why EXP booking failed on preprod | checked. Discussed with AF + composed mail | 1 | 1.5 | 0
JS | Monday | 2015-01-19 | 6903 | Maintenance | 2.7 | Hotel | Complete cleanup on precache |  | 1 | 0.75 | 0
JS | Monday | 2015-01-19 | 7490 | Tests | 2.8 | Hotel | Change per AF advise + test |  | 1 | 1.5 | 1
JS | Monday | 2015-01-19 | 7856 | New |  | TUI | Check C# problem |  | 1 | 0.5 | 1
JS | Monday | 2015-01-19 | 7746 | Documentation | 2.7 | Hotel | Review extrapolation documentation |  | 1 | 0.5 | 0
JS | Monday | 2015-01-19 |  | new | 2.9 | Hotel | Discuss occuapncy CR + hotelcarac CR with AF + tasks for Uma |  | 0.5 | 0.75 | 1
JS | Monday | 2015-01-19 |  | Planning |  | AFI | Weekly planning call |  |  | 1 | 1
JS | Monday | 2015-01-19 |  |  |  |  | VDM debriefing with GK for dashboard |  | 0.5 | 0 | -1
[6 empty] | TUI | search wiki + create task for search add on |  |  | 0.5 | 1
JS | Monday | 2015-01-19 |  | Planning |  |  | Plan whole week for everyone |  | 2 | 2 | 1
JS | Tuesday | 2015-01-20 | 7787 | Tests | 2.9 | Hotel | Test more with data comparison |  | 1.5 | 0 | -1 | next week
JS | Tuesday | 2015-01-20 | 7695 | Maintenance | 2.7 | Hotel | Check markup propagation |  |  | 1.5 | 1
JS | Tuesday | 2015-01-20 | 8007 | Maintenance | 2.7 | Hotel | Check difference between precache and prod | comparison + check BNO + send email |  | 2.5 | 1
JS | Tuesday | 2015-01-20 | 7746 | Documentation | 2.7 | Hotel | Review extrapolation documentation | review + changes |  | 2 | 0
JS | Tuesday | 2015-01-20 |  |  |  |  | Analyse dashboard problems + Discussion with EM | Checked a task for SP | 1.5 | 0.25 | 0
JS | Tuesday | 2015-01-20 |  |  |  |  | Child ages for VDM - check current implementation + impact |  | 2 | 1.5 | 1
JS | Tuesday | 2015-01-20 |  |  |  |  | Call with Anne - child ages |  | 0.5 | 0 | -1
JS | Tuesday | 2015-01-20 | 7643 | Tests | 2.9 | Hotel | Test more with data comparison |  | 1.5 | 0 | -1 | next week
JS | Tuesday | 2015-01-20 | 7767 7768 | Tests |  |  | create 2.8 version + Test extrapolation on devcache |  | 2 | 0 | -1 | next week
JS | Tuesday | 2015-01-20 |  |  |  |  | Daily updates + discussions |  | 0.5 | 1 | 1
JS | Tuesday | 2015-01-20 |  | New | 3.0 | Hotel | Test tool analysis + implementation details + discussions with Anne + tasks |  | 1 | 0 | -1 | Tomorrow
JS | Wednesday | 2015-01-21 | 8015 | New | 3.0 | Hotel | Test tool analysis + implementation details + discussions with Anne + tasks |  | 2 | 1.25 | 0
JS | Wednesday | 2015-01-21 | 7746 | new | 2.9 | Hotel | Finish extrapolation documentation |  | 3 | 4 | 1
JS | Wednesday | 2015-01-21 | 7675 | Tests | 2.8 | Hotel | tourplan, jonview GT + queue for load |  | 1 | 1 | 1
JS | Wednesday | 2015-01-21 | 6903 | Maintenance | 2.7 | Hotel | Finalize the patch for prod | changed SP + applied on precache to monitor split script | 1 | 0.5 | 0
JS | Wednesday | 2015-01-21 |  | new | 2.7 | Hotel | Patch - code + test child ages |  | 3 | 0 | -1 | tomorrow
[7 empty] | Call with Camille |  |  | 0.25 | 1
JS | Wednesday | 2015-01-21 |  |  |  |  | Dashboard DB changes for 2.8 |  | 0.5 | 0 | -1
JS | Wednesday | 2015-01-21 | 6223 | Tests | 2.8 | Hotel | Improve transaction logging tests + revert if no advantage |  | 1.5 | 0 | -1 | next week
JS | Wednesday | 2015-01-21 |  |  |  |  | Daily updates + discussions | daily call + discussion with Anne | 0.5 | 1 | 1
JS | Thursday | 2015-01-22 | 7653 | Tests | 2.9 | Hotel | Review changes + test |  | 0.5 | 0 | -1
JS | Thursday | 2015-01-22 |  |  |  |  | Mail responses + Prod check |  |  | 1 | 1
JS | Thursday | 2015-01-22 | 7690 | Tests | 2.8 | Hotel | Tests + correction + documentation of se_availability__update |  |  | 2.5 | 1
JS | Thursday | 2015-01-22 | 7675 | Tests | 2.8 | Hotel | Generate availability data |  |  | 1 | 1
JS | Thursday | 2015-01-22 |  | new | 2.9 | Hotel | Exchange rate change + tests |  | 3 | 0 | -1
JS | Thursday | 2015-01-22 |  | Tests | 2.9 | Hotel | server setup |  | 3 | 0 | -1
JS | Thursday | 2015-01-22 |  |  |  |  | Daily updates + discussions |  | 1 | 0.5 | 1
JS | Thursday | 2015-01-22 |  |  |  |  | VDM debriefing call with CC, AF, CG |  | 0.5 | 0 | -1
JS | Friday | 2015-01-23 |  | Maintenance | 2.7 | Hotel | Check EXP update count + analysis | check + document + recheck 90 hotels |  | 3 | 1
JS | Friday | 2015-01-23 |  | new | AFI | Hotel | SQL server installation - failed | Failed - mail to Anne with details |  | 1 | -1
JS | Friday | 2015-01-23 | 7653 | Tests | 2.9 | Hotel | Review changes + test |  | 0.5 | 0 | -1
JS | Friday | 2015-01-23 | 7856 |  |  | TUI | Help PS on ListSeat XSL |  |  | 1 | 1
|  |  | 8014 |  |  | TUI | sequencer upgrade | code + some tests. Need to see with PS XSL |  | 2 | 0
JS | Friday | 2015-01-23 | 6903 | Maintenance | 2.7 | Hotel | Deliver patch |  | 0.5 | 0.5 | 1
JS | Friday | 2015-01-23 |  |  |  |  | Discussion with Anne for test tool |  | 0.5 | 1 | 1
JS | Friday | 2015-01-23 | 6223 | Tests | 2.8 | Hotel | Improve transaction logging tests + revert if no advantage |  | 1.5 | 0 | -1
JS | Friday | 2015-01-23 |  |  |  |  | VDM debriefing call with CC, AF, CG |  | 0.5 | 0 | -1
JS | Friday | 2015-01-23 | 7964 | Maintenance | 2.7 | Hotel | EXP examples |  |  | 0.5 | 1
JS | Friday | 2015-01-23 |  |  |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Monday | 2015-01-26 | 8014 | new |  | TUI | Test sequencer auto replacement logic |  | 1 | 1 | 1
JS | Monday | 2015-01-26 |  | Planning |  |  | Weekly plan for everybody |  | 2 | 2 | 1
JS | Monday | 2015-01-26 | 6903 | Maintenance | 2.7 | Hotel | Disucss with AF + finalize the patch |  | 0.5 | 0 | -1
JS | Monday | 2015-01-26 |  | Planning |  | AFI | Weekly planning call |  |  | 1 | 1
JS | Monday | 2015-01-26 | 7653 | Tests | 2.9 | Hotel | Review + test |  | 1 | 0.5 | 1
JS | Monday | 2015-01-26 | 8047 | Maintenance | 2.7 | Hotel | Make the utility for errored hotels available through web |  | 2 | 2 | 0
[7 empty] | SQL server download + installation |  |  | 0.75 | 1
JS | Monday | 2015-01-26 | 8042 | new | 2.9 | Hotel | exchange rate change + discuss with Uma | code + test transaction SPs | 1.5 | 0.75 | 0
JS | Tuesday | 2015-01-27 | 8042 | new | 2.9 | Hotel | exchange rate change + discuss with Uma | code + test transaction SPs | 2 | 2.5 | 1
JS | Tuesday | 2015-01-27 |  |  |  |  | Installed FTP + tried to configre. Failed |  |  | 1 | -1
JS | Tuesday | 2015-01-27 | 8047 | Maintenance | 2.7 | Hotel | Make the utility for errored hotels available through web |  |  | 1 | 1
JS | Tuesday | 2015-01-27 | 7767 7768 | Tests | 2.9 | Hotel | Test the extrapolation + post processing |  | 2 | 0 | -1
JS | Tuesday | 2015-01-27 |  |  |  | Hotel | VDM meeting preparation call |  |  | 1 | 1
JS | Tuesday | 2015-01-27 |  |  |  |  | Support to CC for questions + marmara on SD |  |  | 0.5 | 1
JS | Tuesday | 2015-01-27 |  |  |  |  | Daily updates + discussions |  | 1 | 1 | 1
[7 empty] | DB server setup |  |  | 1 | 1
JS | Tuesday | 2015-01-27 | 7643 | Tests | 2.9 | Hotel | Test more with data comparison |  | 1.5 | 0 | -1
JS | Tuesday | 2015-01-27 | 7787 | Tests | 2.9 | Hotel | Test more with data comparison |  | 1.5 | 0 | -1
JS | Wednesday | 2015-01-28 | 7391 | Tests | 2.9 | Hotel | Check CB error response |  | 2 | 0 | -1
JS | Wednesday | 2015-01-28 | 6223 | Tests | 2.8 | Hotel | Improve transaction logging tests + revert if no advantage |  | 2 | 0 | -1
JS | Wednesday | 2015-01-28 |  | new | 2.9 | Hotel | Child ages for VDM implementation | code + tests | 3 | 0 | -1
JS | Wednesday | 2015-01-28 |  |  |  |  | Server setup - DBs |  |  | 4 | 1
JS | Wednesday | 2015-01-28 | 7643 | New | 2.9 | Hotel | Tourplan data analysis by comparison with devcache data |  |  | 3 | 0
JS | Wednesday | 2015-01-28 |  |  |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-01-29 | 7246 | Tests | 2.8 | Hotel | Check if there is a way to not lock tables during post processing |  | 1 | 0 | -1
JS | Thursday | 2015-01-29 |  |  |  |  | galaxy ref + ref_afidium restore + start synchro with 2.8 |  |  | 1 | 1
JS | Thursday | 2015-01-29 | 7643 | new | 2.9 | Hotel | Improvement for TRP and JNV focussed updates | code + test | 3 | 3.5 | 1 | Will need to generate reports again next week
JS | Thursday | 2015-01-29 | 7801 | new |  | TUI | Add support for session less transaction in soap 4.0 |  |  | 1.5 | 1
JS | Thursday | 2015-01-29 | 7801 | new |  | TUI | SkipCustomError support in sequencer |  |  | 0.5 | 1
|  |  | 8071 | Maintenance | 2.7 | Hotel | JNV GT failed on prod | analysis + tried to reproduce |  | 1 | 0
JS | Thursday | 2015-01-29 | 7757 | Tests | 2.9 | Hotel | Test changes I requested |  | 1 | 0 | -1
JS | Thursday | 2015-01-29 |  |  |  |  | markup import from galaxy | code + test/ tests | 3 | 0 | -1
JS | Thursday | 2015-01-29 |  |  |  |  | Start preparing the release |  | 1 | 0 | -1
JS | Thursday | 2015-01-29 |  |  |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Friday | 2015-01-30 |  |  |  |  | Finalize 2.9 release + test on new server |  | 3 | 0 | -1
JS | Friday | 2015-01-30 | 8080 | new | 2.8 | Hotel | Analysed + stated my understanding of child ages. Need confirmation to start coding | Analysis + checked other tasks , need debriefing |  | 2 | 0
JS | Friday | 2015-01-30 | 8065 | Maintenance | 2.7 | Hotel | Analyse index rebuild problem |  |  | 1.5 | 1
JS | Friday | 2015-01-30 | 7981 | Tests | 2.8 | Hotel | Dashboard correction |  |  | 0.5 | 1
JS | Friday | 2015-01-30 | 8044 | Documentation |  | Hotel | Release procedure |  | 1 | 0 | -1
JS | Friday | 2015-01-30 |  |  |  |  | Call with GK for dashboard issues | call + task for EM , PS + coordinate |  | 1 | 1
JS | Friday | 2015-01-30 |  |  |  |  | Debriefing call with DF, AF, CC |  |  | 1 | 1
JS | Friday | 2015-01-30 |  | Maintenance | 2.7 | Hotel | VDM synchro issue check on servers |  |  | 0.5 | 1
JS | Friday | 2015-01-30 |  |  |  |  | Daily updates + discussions | success assetion to PS + updates | 1 | 0.5 | 0
JS | Friday | 2015-01-30 | 8015 | New | 3 | Hotel | Test tool development | Importer | 4 | 1 | 0
PS | Thursday | 2015-01-01 |  | Maintenance |  | Hotel | Cots |  | 0.5 | 0.5 | 1
PS | Thursday | 2015-01-01 | 7770 | New | 2.9 | Hotel | SPR + SQA testcases |  | 4.5 | 4.5 | 1
PS | Thursday | 2015-01-01 |  |  |  |  | Testgrid update with data |  | 1 | 1 | 1
PS | Thursday | 2015-01-01 |  |  |  | Others | Cots issues with ST + mails |  | 0.5 | 0.5 | 1
PS | Thursday | 2015-01-01 | 7315 | Tests | 2.8 |  | CSV check for data |  | 0.5 | 0.5 | 1
PS | Thursday | 2015-01-01 | 7770 | New | 2.9 | Hotel | Changes if needed in tedtgrid or testcases after review by JS |  | 1 | 0 | -1
PS | Thursday | 2015-01-01 |  |  |  | Others | Co-ordination with TS for task priority + delivery page |  | 0.5 | 0.5 | 1
PS | Thursday | 2015-01-01 | 7770 | New | 2.9 | Hotel | Start test |  | 2 | 0 | -1
PS | Friday | 2015-01-02 | 7805 | New | 2.9 | Hotel | Basic data creation |  |  | 2 | 0
PS | Friday | 2015-01-02 |  | Maintenance |  | Hotel | Cots |  |  | 0.5 | 1
PS | Friday | 2015-01-02 |  |  |  |  | Daily status update call with JS |  |  | 0.5 | 1
PS | Friday | 2015-01-02 | 7744 | New |  |  | VDM cases prep - stuck | and venda report |  | 0.5 | 0
PS | Friday | 2015-01-02 | 7435 | New | 2.9 | Hotel | GTA case check on SD-29142 | Not sufficient data. Need to check on devcache |  | 0.5 | 1
PS | Friday | 2015-01-02 | 7817 | New | 2.9 | Hotel | Setup 2.9 web service on SD-29142 |  |  | 2 | 0 | Need JS to look into problem
PS | Monday | 2015-01-05 | 7435 | New | 2.9 | Hotel | GTA testing on DEVCACHE |  |  | 1 | 1
PS | Monday | 2015-01-05 |  | Maintenance |  | Hotel | COT |  |  | 0.5 | 1
PS | Monday | 2015-01-05 | 7689 | New | 2.8 | Hotel | VDM Natif tests | Discussion with CC + checks . to JS for activating CO |  | 1 | 1
PS | Monday | 2015-01-05 | 7805 | New | 2.9 | Hotel | population of data in 2.9 |  | 1 | 1 | 1
PS | Monday | 2015-01-05 | 7315 | Tests | 2.8 dashboard | Hotel | Tests | discussion with EM + tests | 2 | 1.25 | 0 | To EM with question
PS | Monday | 2015-01-05 | 7592 | New | 2.9 | Hotel | Format change to make title options |  |  | 0.25 | 1
PS | Monday | 2015-01-05 |  |  |  |  | Call with JS |  |  | 1 | 1
PS | Monday | 2015-01-05 |  | Tests | 2.9 | Hotel | SE tests |  | 1.5 | 2 | 1
PS | Tuesday | 2015-01-06 | 7770 | Tests | 2.9 | Hotel | SPR | test case updates + tests + data checks | 2 | 0 | -1
PS | Tuesday | 2015-01-06 | 7825 | Tests | 2.9 | Hotel | SE issue to JS | discuss + retest |  | 1 | 1
PS | Tuesday | 2015-01-06 | 7689 | Tests | 2.9 | Hotel | Discussed with JS. Checked basic things | JS has applied on devcache now. Will have to check on devcache |  | 0.5 | 0
PS | Tuesday | 2015-01-06 | 7744 | Tests | 2.9 | Hotel | Room Code in VDM CB RS | Reviewed JS cases, for VDM prepared test cases. played GQA |  | 1.5 | 0
PS | Tuesday | 2015-01-06 | 7842 | Tests |  | TUI | TUI update tests | Saw problems. Informed CC. CC has replaced files, need to test again |  | 1 | 0
PS | Tuesday | 2015-01-06 |  |  |  |  | Discussions with ST, VDM XB samples, 2.9 data |  |  | 0.5 | 1
PS | Tuesday | 2015-01-06 |  |  |  |  | Daily call with JS |  |  | 0.5 | 1
PS | Tuesday | 2015-01-06 | 7740 | New |  | TUI | Test cases for Seat List | Use case from CC + read doc + prepared test cases. Testgrid in progress. Waiting for CC review of sample cases |  | 2.5 | 0
PS | Tuesday | 2015-01-06 |  | Maintenance |  | Hotel | COT |  | 0.5 | 0.5 | 1
PS | Wednesday | 2015-01-07 | 7770 | Tests | 2.9 | Hotel | SQA tests | test case updates + tests + F done. K in progress | 3.75 | 2.25 | 0
PS | Wednesday | 2015-01-07 | 7770 | Tests | 2.9 | Hotel | SPR Tests | SPR F, K tests | 2.5 | 3 | 1
PS | Wednesday | 2015-01-07 |  |  |  |  | Discussions + coordination |  |  | 0.75 | 1
PS | Wednesday | 2015-01-07 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-01-07 | 7689 | Tests | 2.9 | Hotel | Check VDM CO | Checked. To CC | 0.5 | 0.5 | 1
PS | Wednesday | 2015-01-07 | 7842 | Tests |  | TUI | TUI update tests | tests |  | 0.5 | 1
PS | Wednesday | 2015-01-07 | 7744 | Tests | 2.9 | Hotel | Room Code in VDM CB RS |  | 0.5 | 0.25 | 0
PS | Wednesday | 2015-01-07 | 7740 | Tests |  | TUI | Test grid + test cases for ListSeat | Testgrid finished | 0.5 | 0.5 | 1
PS | Thursday | 2015-01-08 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-01-08 | 7770 | Tests | 2.9 | Hotel | SQA Tests | K remains | 4 | 2.5 | 0
PS | Thursday | 2015-01-08 | 7846 7847 |  |  |  | SPR Retest fixed issues |  | 0.25 | 2 | 1
PS | Thursday | 2015-01-08 |  |  |  |  | Discussions + updates with JS |  | 0.5 | 0.75 | 1
PS | Thursday | 2015-01-08 | 7744 |  | 2.9 | Hotel | VDM CB tests |  | 0.5 | 0.5 | 0 | Decision taken to test on devcache. AF + JS
PS | Thursday | 2015-01-08 | 7855 | new |  | TUI | XSLOUT for ListSeat | code + test in oxygen + C# | 2.5 | 2 | 1
PS | Friday | 2015-01-09 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-01-09 | 7770 |  |  |  | SQA K tests | update test grid + test cases per data + test | 1.5 | 2.5 | 1
PS | Friday | 2015-01-09 |  |  |  |  | Discussions with JS |  | 1 | 0.5 | 1
PS | Friday | 2015-01-09 | 7689 |  |  |  | CO test with remark for CC |  |  | 0.25 | 1
PS | Friday | 2015-01-09 | 7856 |  |  | TUI | XSLIN for ListSeat | read wikis + discuss with CC + code | 5.25 | 4 | 0
PS | Monday | 2015-01-12 | 7856 |  |  | TUI | Finish ListSeat XSLOUT | code + tests + discuss with CC | 4.5 | 5 | 0
PS | Monday | 2015-01-12 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Monday | 2015-01-12 |  |  |  |  | Discussion with JS |  | 0.5 | 1 | 1
PS | Monday | 2015-01-12 | 7860 | Tests | 2.9 | Hotel | Closed date tests |  | 2.75 | 1.75 | 0 | SPR, SQA done. Need data for VDM GQA
PS | Tuesday | 2015-01-13 | 7855 | new |  | TUI | Improvements in ListSeat XSL as suggested by JS | code + test | 2 | 1 | 1
PS | Tuesday | 2015-01-13 | 7860 | Tests | 2.9 | Hotel | Closed date tests | VDM GQA , updated test cases + test grid. Also had to wait for JS to recreate data and retry | 0.5 | 1.5 | 1
PS | Tuesday | 2015-01-13 |  |  |  |  | ListSeat tests |  | 2.75 | 0 | -1
PS | Tuesday | 2015-01-13 | 7856 |  |  | TUI | ListSeat XSL RS | Progressed + discussion with CC |  | 4 | 0
PS | Tuesday | 2015-01-13 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-01-13 | 7500 | Tests | 2.9 | Hotel | Test prefered bit | need discussion, data with JS |  | 0.25 | 0
PS | Tuesday | 2015-01-13 | 6903 | Maintenance | 2.8 | Hotel | Run scripts on devcache, precache + note time | Scripts to be written by JS | 2 | 0 | -1
PS | Tuesday | 2015-01-13 |  |  |  |  | Discussions + daily updates |  | 0.5 | 1 | 1
PS | Wednesday | 2015-01-14 |  | Tests |  | TUI | ListSeat Tests |  | 3 | 0 | -1
PS | Wednesday | 2015-01-14 | 7856 | New |  | TUI | List Seat XSL RS | Discussions with CC + XSL coding | 3.5 | 6 | 0
PS | Wednesday | 2015-01-14 | 7500 | Tests | 2.9 | Hotel | Prefered bit tests |  | 0.5 | 0.75 | 1
PS | Wednesday | 2015-01-14 |  |  |  |  | Status updates + discussions |  | 0.75 | 1 | 1
PS | Wednesday | 2015-01-14 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-01-15 | 7920 | New |  | TUI | Recreate UML diagrams using Lucidchart |  | 3 | 0 | -1
PS | Thursday | 2015-01-15 |  | Tests |  | TUI | ListSeat Tests |  | 2 | 0 | -1
PS | Thursday | 2015-01-15 | 7856 | New |  | TUI | List Seat XSL RS | Discuss problem with JS + solve | 1 | 5.75 | 1
PS | Thursday | 2015-01-15 | 7631 | Tests |  | Hotel | Tests as suggested by JS |  | 1 | 0 | 0
PS | Thursday | 2015-01-15 |  |  |  |  | Discussions + status updates |  | 0.75 | 2 | 1
PS | Thursday | 2015-01-15 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-01-16 | 7920 | New |  | TUI | Recreate UML diagrams using Lucidchart |  | 4 | 0 | -1
PS | Friday | 2015-01-16 | 7753 | New | 2.9 | Hotel | Documentation correction |  |  | 0.5 | 1
PS | Friday | 2015-01-16 |  |  |  |  | Status updates + discussions |  |  | 0.75 | 1
PS | Friday | 2015-01-16 |  | Tests |  | TUI | ListSeat Tests |  |  | 1 | 0
PS | Friday | 2015-01-16 |  | New |  | TUI | List Seat XSL RS | CC review + more modifications + discussions + debug C# problem with JS | 2 | 5.5 | 1
PS | Friday | 2015-01-16 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Monday | 2015-01-19 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Monday | 2015-01-19 |  |  |  |  | Status updates + discussions |  | 0.5 | 1 | 1
| Monday | 2015-01-19 |  | Tests |  | TUI | ListSeat Tests + XSLIN modifications + run with C# problem |  | 4.5 | 4.5 | 1 | 1 issue seen. Need to fix
PS | Monday | 2015-01-19 |  | Tests |  | 7631 | Tests |  | 2 | 2 | 1
PS | Monday | 2015-01-19 |  | Maintenance | 2.7 | Hotel | Tests as asked by JS |  | 0.75 | 0 | -1
PS | Monday | 2015-01-19 | 7920 | New |  | TUI | Recreate UML diagrams using Lucidchart | understand + discuss with CC | 3.5 | 0 | -1
PS | Tuesday | 2015-01-20 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-01-20 |  |  |  |  | Status updates + discussions |  | 0.75 | 0.25 | 1
PS | Tuesday | 2015-01-20 | 7717 | new |  |  | Doc - Add Hist Comment wherever modified |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-01-20 | 7753 | new |  |  | Doc - Add Hist Comment wherever modified and Check RNC |  | 0.25 | 0.75 | 1
PS | Tuesday | 2015-01-20 | 7920 | New |  | TUI | Recreate UML diagrams using Lucidchart |  | 5.5 | 6.5 | 1
PS | Tuesday | 2015-01-20 | 7315 | Tests | 2.8 | Hotel | Dashboard tests + discuss with JS about issue |  | 1 | 0 | -1
PS | Wednesday | 2015-01-21 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-01-21 |  |  |  |  | Status updates + discussions | TS, CC, JS | 0.75 | 1 | 1
PS | Wednesday | 2015-01-21 | 7920 | New |  |  | Recreate UML diagrams using Lucidchart |  | 3 | 1 | 1
PS | Wednesday | 2015-01-21 | 7391 | Tests |  |  | Modify CB tests | not able to reproduce error |  | 0.25 | -1
PS | Wednesday | 2015-01-21 | 7977 | new |  |  | SearchAddon Read and discuss with CC | XSL out done. Not tested with C#. XSLIn stated | 5.5 | 5.5 | 0
PS | Thursday | 2015-01-22 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-01-22 |  |  |  |  | Status updates + discussions |  | 0.75 | 1 | 1
PS | Thursday | 2015-01-22 | 7391 | Tests | 2.9 | Hotel | Modify CB tests | No case found | 1 | 1 | 1
PS | Thursday | 2015-01-22 | 8014 | New |  |  | SearchADDon Implementation Out XSL+ Tests + testcases + start XSLIN | Cor-ordination with CC for XSL | 6 | 5.75 | 0
PS | Friday | 2015-01-23 |  | Maintenance |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-01-23 |  |  |  |  | Status updates + discussions |  | 0.5 | 1 | 1
PS | Friday | 2015-01-23 | 7856 | new |  |  | XSLIN for LS | Problem analysis: to CC for verification | 1 | 1 | 1
PS | Friday | 2015-01-23 | 7977 | New |  |  | XSLIN for Searchddon | XSLOut testing with C# + XSLIN | 7 | 5.75 | 0
PS | Monday | 2015-01-26 |  |  |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Monday | 2015-01-26 | 8014 | New |  |  | XSLIN for SAO | code to generate XFT RS | 6.75 | 6.25 | 0
PS | Monday | 2015-01-26 |  |  |  |  | Status updates + discussions | feedback from CC about LS. | 1 | 1.5 | 1
PS | Tuesday | 2015-01-27 |  |  |  | Hotel | COT |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-01-27 |  |  |  |  | Status updates + discussions |  | 0.75 | 0.75 | 1
PS | Tuesday | 2015-01-27 | 7856 |  |  |  | Work on Feedback : lS + Tests | XSL changes : |  | 5 | 0
PS | Tuesday | 2015-01-27 | 8014 | New |  |  | Finish XSLIN and start tests | code to generate XFT RS + start unit tests | 6 | 2 | 0
PS | Wednesday | 2015-01-28 |  |  |  | Hotel | COT | Checked mails + prod JNV availabiluity | 0.5 | 0.5 | 1
PS | Wednesday | 2015-01-28 |  |  |  |  | Status updates + discussions |  | 1 | 1 | 1
PS | Wednesday | 2015-01-28 | 7856 |  |  |  | LS-tests if problem identified and resolved | done : to CC | 1.5 | 1.5 | 1
PS | Wednesday | 2015-01-28 | 8014 |  |  |  | SAO tests | test grid + test cases | 5 | 5 | 1
PS | Thursday | 2015-01-29 |  |  |  | Hotel | COT |  | 0.25 | 0.5 | 1
PS | Thursday | 2015-01-29 |  |  |  |  | Status updates + discussions |  | 0.75 | 1.5 | 1
PS | Thursday | 2015-01-29 | 8014 |  |  |  | SAO tests | XSL + Testgrid + testcases added | 5 | 3.5 | 1 | 1 issue to correct on CC's advice
PS | Thursday | 2015-01-29 | 7059 |  |  |  | Dashboard: checks |  | 1 | 0 | 0
PS | Thursday | 2015-01-29 | 7315 |  |  |  | Dashboard: checks |  | 1 | 0 | 0
PS | Thursday | 2015-01-29 | 7801 |  |  |  | Ls: add more testcases + play + 2 corrections in xsl |  | 2 | 2.5 | 1
PS | Friday | 2015-01-30 |  |  |  | Hotel | COT |  | 0.25 | 0.5 | 1
PS | Friday | 2015-01-30 |  |  |  |  | Status updates + discussions |  | 0.75 | 1 | 1
PS | Friday | 2015-01-30 | 8014 | New |  | TUI | SAO : SuccessAssertion + tests | discuss with JS + code + test |  | 1.5 | 1
PS | Friday | 2015-01-30 | 7315 | Tests | 2.8 | Hotel | Dashboard checks |  |  | 0.75 | 1
PS | Friday | 2015-01-30 | 7059 | Tests | 2.8 | Hotel | Testgrid for V2 test cases | check GK tasks + update test grid + check dashboard |  | 1 | 1
PS | Friday | 2015-01-30 | 8105 | New | 2.8 | Hotel | Clarify documentation | wiki for GTA and EXP + discuss with JS |  | 2.5 | 1
PS | Friday | 2015-01-30 | 7391 | Tests | 2.8 | Hotel | [CB] Modify CB so that Native Booking reference | JS needs to help find cases |  | 0.75 | -1
ST | Thursday | [5 empty] | Leave
ST | Friday | 2015-01-02 | 7639 | New | 2.8 | Hotel | Study of replication after changes for data reduction | Setup of server + discussions | 1 | 0 | -1 |  | Leaves : 2015-01-01 2015-01-12 to 2015-01-18 2015-01-21 to 2015-01-21
ST | Friday | 2015-01-02 |  |  |  | Hotel | Call with SQL server vendor |  | 1 | 1 | 1
ST | Friday | 2015-01-02 | 7690 | New | 2.8 | Hotel | Testing of availability | analysis | 1.5 | 1 | 0
| Friday | 2015-01-02 | 7803 | Maintenance | 2.7 | Hotel | Discussion with Anne + checking data |  |  | 0.75 | 1
ST | Friday | 2015-01-02 |  |  |  |  | Call with Jyotsna |  | 0.5 | 1 | 1
ST | Friday | 2015-01-02 | 7658 | Maintenance |  | Stock | [Winter] Replace SP not counting stock on a given journey | analysis with current data. Cannot understanding root cause | 3 | 2.5 | 0
ST | Monday | 2015-01-05 |  |  |  | Hotel | Call with SQL server vendor |  | 1 | 0.5 | 1
ST | Monday | 2015-01-05 | 7658 | Maintenance |  | Stock | [Winter] Replace SP not counting stock on a given journey | Reproduce problem + analysis with winter | 3 | 1.5 | 1 | Problem not reproduced with AF, GK
ST | Monday | 2015-01-05 |  |  |  |  | Discussion with AF - Hotel, Stock |  |  | 0.75 | 1
ST | Monday | 2015-01-05 |  |  |  | Stock | Wiki update for Tables used in booking |  |  | 0.75 | 1
ST | Monday | 2015-01-05 | 7690 | New | 2.8 | Hotel | Testing of availability |  | 1 | 0 | -1
ST | Monday | 2015-01-05 | 7749 | Maintenance | 2.8 | Hotel | Devcache, precache problem |  | 0.5 | 0.5 | 1
ST | Monday | 2015-01-05 | 7777 | Maintenance | 2.7 | Hotel | duplicate deletion se_versioned_tarif | more info | 0.5 | 0.5 | 1
ST | Monday | 2015-01-05 |  |  |  |  | Call with JS |  | 0.5 | 1 | 1
ST | Monday | 2015-01-05 | 7768 | New | 2.9 | Hotel | Extrapolation figures | test | 0.3 | 0.5 | 1
ST | Tuesday | 2015-01-06 | 7746 | Documentation | 2.9 | Hotel | Extrapolation |  | 3 | 0 | -1
ST | Tuesday | 2015-01-06 | 7690 | New | 2.8 | Hotel | Testing of availability | code availability SP + test | 1.5 | 1 | 1
ST | Tuesday | 2015-01-06 | 7824 | New |  | Stock | Technical analysis of booking replace change | analysis + coding | 1.5 | 2 | 0
ST | Tuesday | 2015-01-06 |  |  |  |  | Discussions with Anne on skype | stock, hotel, task planning |  | 1.5 | 1
ST | Tuesday | 2015-01-06 | 7757 | New | 2.9 | Hotel | Call with AF, JS |  | 0.5 | 1 | 1
ST | Tuesday | 2015-01-06 |  |  |  |  | Daily call with JS |  | 0.5 | 0.5 | 1
ST | Wednesday | 2015-01-07 |  |  |  |  | Daily call with JS |  | 0.5 | 0.5 | 1
ST | Wednesday | 2015-01-07 |  |  |  |  | Discussion with CC - precache speed |  |  | 0.5 | 1
ST | Wednesday | 2015-01-07 |  |  |  |  | Discussion with AF for stock, precache, task planning |  |  | 0.5 | 1
ST | Wednesday | 2015-01-07 |  |  |  |  | Call with AR |  |  | 0.25 | 1
ST | Wednesday | 2015-01-07 | 6903 | Maintenance |  | Hotel | SP + script | for 2.8, 2.9 improvement + script for patch. Code + test on sd-29142 |  | 1 | 1
ST | Wednesday | 2015-01-07 | 7824 | New |  | Stock | booking replace change | code + test | 5.5 | 3.5 | 1
ST | Wednesday | 2015-01-07 | 6281 | New | 2.9 | Hotel | Test Um'a work + close |  |  | 0.25 | 1
ST | Wednesday | 2015-01-07 | 7748 | New | 2.9 | Hotel | Test Uma's work + close |  |  | 0.5 | 1
ST | Thursday | 2015-01-08 | 7849 | New |  | Stock | indexes for stock | code + test | 5 | 2.25 | 0
ST | Thursday | 2015-01-08 | 7824 | new |  | Stock | Booking replace - bug fix |  |  | 1 | 1
ST | Thursday | 2015-01-08 | 7865 | Maintenance |  | Stock | corrected problem on vdm server | discussion with GK AR + fix + test + reinstall |  | 1.25 | 1
ST | Thursday | 2015-01-08 | 7436 | New | 2.9 | Hotel | Check SP to rebuild IX_MAINTENANCE | test | 0.5 | 0.5 | 1
ST | Thursday | 2015-01-08 |  |  |  |  | Discussions with AF, TS, AR | correction for sto_route__update |  | 0.5 | 1
ST | Thursday | 2015-01-08 |  |  |  |  | Daily call with JS |  | 0.5 | 0.5 | 1
ST | Friday | 2015-01-09 | 7864 | Maintenance |  | Stock | Discussion with AR for understanding issue + analysis + correction | SQA + booking replace | 1 | 0 | -1
ST | Friday | 2015-01-09 | 7849 | New |  | Stock | indexes for stock | code + test | 2 | 2 | 1
ST | Friday | 2015-01-09 |  |  |  |  | Daily call with JS |  | 0.5 | 0.5 | 1
ST | Friday | 2015-01-09 | 7757 | New | 2.9 | Hotel | Test Uma' work for log_storedProcedure |  | 0.5 | 0.5 | 1
ST | Friday | 2015-01-09 | 6948 |  |  | Hotel | Add table for closure |  | 0.25 | 0.25 | 1
| Friday | 2015-01-09 | 6492 |  |  | Hotel | Review wiki for automate operational tests |  |  | 0.5 | 1
ST | Friday | 2015-01-09 | 7746 | Documentation | 2.9 | Hotel | Extrapolation |  | 1.75 | 0.25 | 0 | Discussion with JS for idea
ST | Friday | 2015-01-09 | 7767 7768 7690 | Documentation | 2.9 | Hotel | Wiki for changes done |  | 2 | 0 | -1 | Cannot be done in this week
ST | Monday | 2015-01-12 |  | leave | 2.9 | Hotel | Extrapolation wiki |  | 2 | 0 | -1
ST | Tuesday | 2015-01-13 |  | leave | [5 empty] | 2 | 1 | Finish extrapolation wiki
ST | Wednesday | 2015-01-14 |  | leave
ST | Thursday | 2015-01-15 |  | leave
ST | Friday | 2015-01-16 |  | leave
ST | Monday | 2015-01-19 |  | leave |  |  | Urgent shifting of home to another city | ST will discuss with AF for stock
ST | Monday | 2015-01-19 |  |  |  |  | Discussion with Anne |  |  | 0.5 | 1
ST | Tuesday | 2015-01-20 | 8006 | New |  | Stock | booking replace should save quotation if available | code + test | 6 | 5.5 | 1
ST | Wednesday | 2015-01-21 | 8006 | New |  | Stock | booking replace should save quotation if available | fix problems + discuss with AF | 1 | 1 | 0
ST | Wednesday | 2015-01-21 | 6618 | Evolution |  | AIR | Use fareopt aggregation in dashboard | code + task updated with details | 2 | 2 | 0
ST | Thursday | 2015-01-22 | 8006 | New |  | Stock | booking replace should save quotation if available |  | 1.5 | 1 | 0
[7 empty] | Discussions | Camille, AF, JS |  | 0.5 | 1
ST | Thursday | 2015-01-22 | 6618 | Evolution |  | AIR | Use fareopt aggregation in dashboard | apply code in DB and commit and task update | 1 | 1 | 1
ST | Thursday | 2015-01-22 |  |  |  | Hotel | Mail and dociument for 7346 and checked 7690 changes |  |  | 0.5 | 1
ST | Friday | 2015-01-23 |  |  |  |  | Leave
ST | Monday | 2015-01-26 |  |  |  |  | Leave
ST | Tuesday | 2015-01-27 |  |  |  |  | Leave
ST | Wednesday | 2015-01-28 |  |  |  |  | Leave
ST | Thursday | 2015-01-29 |  |  |  |  | Leave
ST | Friday | 2015-01-30 |  |  |  |  | Leave
UZ | Thursday | 2015-01-01 | 7757 | New | 2.9 | Hotel | created sp sp_cleanup, modified sp post processing + testing |  | 1.5 | 1.25 | 1 |  | Leaves : 2015-01-20 2015-02-16 - 2015-02-17 Half day May need half day on 2015-01-15 and 2015-01-19
UZ | Thursday | 2015-01-01 | 4777 | New | Documentation | Hotel | Updated document |  | 2.5 | 2.75 | 0
UZ | Friday | 2015-01-02 | 7515 | New | 2.9 | Hotel | Listed tables and columns using text fields |  | 3 | 3.5 | 1
UZ | Friday | 2015-01-02 | 6492 |  | Documentation | Hotel | Automate operational tests doc | Include Tazeen's comments |  | 0.75 | 1
UZ | Friday | 2015-01-02 | 4777 | New | Documentation | Hotel | Updated document |  | 1 | 0.5 | 0 | V2 tarif upload wiki pending
UZ | Monday | 2015-01-05 | 6492 |  | Documentation | Hotel | Automate operational tests doc | Include further comments by TS |  | 0.25 | 1
UZ | Monday | 2015-01-05 | 7500 | New | 2.9 | Hotel | Review JS changes |  |  | 0.75 | 1
UZ | Monday | 2015-01-05 | 7500 |  |  |  | Data in 2.8_test for tests |  |  | 0.5 | 1
UZ | Monday | 2015-01-05 | 4777 | New | Documentation | Hotel | V2 upload accomodation wiki |  | 2 | 0.5 | 0
UZ | Monday | 2015-01-05 | 7500 |  |  |  | Apply 2.9 objects on 2.9 DB |  | 0.5 | 0.75 | 1
UZ | Monday | 2015-01-05 | 7500 | New | 2.9 | Hotel | Update wikis after JS changes |  | 1.5 | 0.5 | 1
UZ | Monday | 2015-01-05 |  |  |  |  | Call with JS : weekly planning + discussions |  |  | 0.75 | 1
UZ | Tuesday | 2015-01-06 | 7500 | New | 2.9 | Hotel | Update wikis after JS changes |  | 1 | 1.5 | 1
UZ | Tuesday | 2015-01-06 | 4777 | New | 2.8 | Hotel | V2 upload accomodation wiki |  |  | 0.75 | 1
UZ | Tuesday | 2015-01-06 | 7806 | New | 2.9 | Hotel | 2.9 release script till phase 1 |  | 0.5 | 0 | -1
UZ | Tuesday | 2015-01-06 |  |  |  |  | Call with JS |  |  | 0.25 | 1
UZ | Tuesday | 2015-01-06 | 7837 | New | 2.9 | Hotel | se_hvendor_at__import : phase 2 |  | 2.5 | 1.5 | 1
UZ | Wednesday | 2015-01-07 |  |  |  |  | Daily call with JS |  | 0.5 | 0.5 | 1
UZ | Wednesday | 2015-01-07 | 7837 | new | 2.9 | Hotel | Script for se_hvendor_at alter + redo changes |  |  | 0.75 | 1
UZ | Wednesday | 2015-01-07 | 7837 | New | 2.9 | Hotel | se_hvendor_at__import : phase 2 |  | 1 | 1.25 | 1
UZ | Wednesday | 2015-01-07 | 7838 | New | 2.9 | Hotel | se_hvendor_at__delete : phase 2 | Need help from JS | 2.5 | 1.5 | 0
UZ | Thursday | 2015-01-08 | 7838 | New | 2.9 | Hotel | se_hvendor_at__delete : phase 2 |  | 2.5 | 1.5 | 0 | Worked for 2 hours
UZ | Thursday | 2015-01-08 |  |  |  |  | se_hvendor_at__import wiki |  |  | 0.5 | 1
UZ | Thursday | 2015-01-08 | 7844 |  |  |  | change se2_at__import + test + document |  | 1.5 | 0 | -1
UZ | Friday | 2015-01-09 | 7844 |  |  |  | change se2_at__import + test + document |  | 1 | 1 | 1
UZ | Friday | 2015-01-09 | 7843 | New | 2.9 | Hotel | Markup modifications | code + test | 3 | 3 | 0
UZ | Monday | 2015-01-12 | 7843 | new | 2.9 | Hotel | Markup modifications | code + test | 3.5 | 3.25 | 1
UZ | Monday | 2015-01-12 |  |  |  |  | Daily stuatus updates + discussions |  | 0.5 | 0.5 | 1
UZ | Monday | 2015-01-12 |  | New | 2.9 | Hotel | corrections of wiki per JS suggestions |  |  | 0.25 | 1
UZ | Tuesday | 2015-01-13 | 7516 | new | 2.9 | Hotel | update wiki per JS suggestion |  | 0.5 | 0.25 | 1
UZ | Tuesday | 2015-01-13 | 7837 + 7838 | New | 2.9 | Hotel | update per JS |  |  | 1.25 | 1
UZ | Tuesday | 2015-01-13 | 7844 | New | 2.9 | Hotel | update wiki |  |  | 1 | 1
UZ | Tuesday | 2015-01-13 |  |  |  |  | Daily stuatus updates + discussions |  | 0.5 | 0.25 | 1
UZ | Tuesday | 2015-01-13 | 7843 | New | 2.9 | Hotel | Markup modifications | test + wiki | 2 | 1.25 | 1
UZ | Wednesday | 2015-01-14 | 7653 |  | 2.9 | Hotel | add hist comment + alter table (FK) | apply on 2.9 | 1.25 | 1.25 | 0
UZ | Wednesday | 2015-01-14 | 7806 | New | 2.9 | Hotel | Realease script 2.9 |  | 0.5 | 0.5 | 0
UZ | Wednesday | 2015-01-14 | 7843 |  | 2.9 | Hotel | add hist comment + test | apply on 2.9 | 0.5 | 0.5 | 1
UZ | Wednesday | 2015-01-14 | 7746 | new | 2.9 | Hotel | Documentation - extrapolation | add missing wikis as suggested by ST | 1.5 | 1.5 | 1
UZ | Wednesday | 2015-01-14 |  |  |  |  | Daily stuatus updates + discussions |  | 0.25 | 0.25 | 1
UZ | Thursday | 2015-01-15 | 7844 | New | 2.9 | Hotel | Correct wiki per JS corrections |  | 0.5 | 1 | 1
UZ | Thursday | 2015-01-15 | 7653 |  | 2.9 | Hotel | Alter table (FK) |  | 0.25 | 0.25 | 1
UZ | Thursday | 2015-01-15 | 7843 | New | 2.9 | Hotel | correct table script + test |  | 0.5 | 0.5 | 1
UZ | Thursday | 2015-01-15 | 7806 | New | 2.9 | Hotel | Realease script 2.9 |  | 3 | 2.25 | 1
UZ | Friday | 2015-01-16 | 7806 | New | 2.9 | Hotel | Realease script 2.9 | finish + test |  | 3.5 | 1
UZ | Friday | 2015-01-16 |  |  |  |  | Create sm_searchengine_2.9_test |  |  | 0.5 | 0
UZ | Monday | 2015-01-19 | 7757 | New | 2.9 | Hotel | Add error message column + test |  | 3.5 | 2.5 | 1
UZ | Monday | 2015-01-19 | 7806 | New | 2.9 | Hotel | execute 2.8 script on 2.9_test DB |  | 0.25 | 0.25 | 1
UZ | Monday | 2015-01-19 | 7806 | New | 2.9 | Hotel | Updated script |  | 0.5 | 0.75 | 1
UZ | Monday | 2015-01-19 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-01-20 |  |  |  |  | Leave
UZ | Wednesday | 2015-01-21 | 7806 |  | 2.9 | hotel | Testing on 2.9_test DB |  | 3 | 3 | 0
UZ | Wednesday | 2015-01-21 | 5937 |  | 2.8,2.9 | hotel | do changes in SP and measure time for Fixed and auto rooming |  | 0.75 | 0.75 | 0
UZ | Wednesday | 2015-01-21 |  |  |  |  | Daily updates + discussions |  | 0.25 | 0.25 | 1
UZ | Thursday | 2015-01-22 | 7806 |  | 2.9 | Hotel | Testing un 2.9_test DB |  | 2.25 | 2.25 | 1
UZ | Thursday | 2015-01-22 | 5937 |  | 2.8,2.9 | Hotel | change SP + measure time for Fixed and auto rooming |  | 1.25 | 1.25 | 1
UZ | Thursday | 2015-01-22 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Friday | 2015-01-23 | 8032 | New | 3 | Hotel | Test tool DB change |  | 3.5 | 3.5 | 1
UZ | Friday | 2015-01-23 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Monday | 2015-01-26 | 8036 | New | 2.9 | Hotel | se_currency table change + start import | code + test + wiki | 3.5 | 3.5 | 0
UZ | Monday | 2015-01-26 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-01-27 | 8036 | New | 2.9 | Hotel | import se_currency | code + test + wiki | 3.5 | 3.5 | 1
UZ | Tuesday | 2015-01-27 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Wednesday | 2015-01-28 | 8060 | New | 3 | Hotel | Test tool - config table /SP + info table SP | code + test + wiki | 3.5 | 2 | 0
UZ | Wednesday | 2015-01-28 | 7806 |  |  | Hotel | corrections per JS suggestion |  |  | 1.75 | 1
UZ | Wednesday | 2015-01-28 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Thursday | 2015-01-29 | 8063 | New | 3 | Hotel | Test tool - config table /SP + info table SP | code + test + wiki | 3.5 | 2.75 | 1
UZ | Thursday | 2015-01-29 |  |  | 2.8 | Hotel | Add index creation script in installation script |  | 0.25 | 0.25 | 1
UZ | Thursday | 2015-01-29 | 8060 |  | 3 | Hotel | correct wiki |  | 0.5 | 0.5 | 1
UZ | Thursday | 2015-01-29 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Friday | 2015-01-30 |  |  | 2.9 | Hotel | Corrected some wikis |  | 0.75 | 0.75 | 1
UZ | Friday | 2015-01-30 | 8032 |  | 3 | Hotel | add column in table wt_tlog + modify SP |  | 0.5 | 0.5 | 1
UZ | Friday | 2015-01-30 |  |  |  |  | Daily updates + discussions |  | 0.5 | 0.75 | 1
UZ | Friday | 2015-01-30 | 8110 | New | 3 | Hotel | create SP wt_tlog__read | code + test + wiki | 2 | 2 | 1
TS | Thursday | 2015-01-01 |  | Maintenance |  |  | Task maintenance |  | 2.5 | 3 | 1
TS | Thursday | 2015-01-01 |  | Maintenance |  |  | Hotel release notes |  | 1.5 | 2 | 1
TS | Thursday | 2015-01-01 | #6492 | Other |  |  | wiki review, co-ordinate & assist Uma |  | 0.5 | 1 | 1
TS | Thursday | 2015-01-01 |  | Documentation |  |  | Sto data dictionary migration |  | 3 | 1.5 | 1
TS | Thursday | 2015-01-01 |  | Other |  |  | Co-ordination with PS |  |  | 0.5 | 1
TS | Friday | 2015-01-02 |  | Maintenance |  |  | Weekly updates |  | 0.5 | 0.5 | 1
TS | Friday | 2015-01-02 |  |  |  |  | Stats process | step1 | 2.5 | 2.5 | 1
TS | Friday | 2015-01-02 |  |  | Documentation |  | Sto data dictionary migration |  | 4 | 4 | 1
TS | Friday | 2015-01-02 |  | Maintenance |  |  | Meetings follow up |  | 1 | 1 | 1
TS | Monday | 2015-01-05 |  |  | Planning |  | Week/tracking |  | 0.5 | 0.5 | 1
TS | Monday | 2015-01-05 |  |  | Documentation |  | Sto data dictionary migration |  | 4 | 4.5 | 1
TS | Monday | 2015-01-05 |  |  | Maintenance |  | Stats process |  | 2.5 | 2.5 | 1
TS | Monday | 2015-01-05 |  |  | Other |  | co-ordiantion |  | 0.5 | 0.5 | 1
TS | Monday | 2015-01-05 |  |  |  | VDM | VDM meeting preparation |  | 1 | 1 | 1
TS | Tuesday | 2015-01-06 |  |  |  | VDM | Hotel weekly meeting prep |  | 1 | 1 | 1
TS | Tuesday | 2015-01-06 |  |  | Documentation |  | Sto data dictionary migration |  | 5 | 5.5 | 1
TS | Tuesday | 2015-01-06 |  |  | Maintenance |  | Tasks follow up |  | 2 | 1.5 | 1
TS | Tuesday | 2015-01-06 |  |  | Maintenance |  | Weekly updates |  | 1 | 0 | -1
TS | Wednesday | 2015-01-07 |  |  | Planning |  | Planning excel & cli excel review |  | 1.5 | 0 | -1
TS | Wednesday | 2015-01-07 |  |  | Documentation |  | Sto data dictionary migration & component doc |  | 4.5 | 5.5 | 1
TS | Wednesday | 2015-01-07 |  |  | Maintenance |  | Wiki review , tasks |  |  | 1 | 1
TS | Wednesday | 2015-01-07 |  |  | Maintenance |  | Stats issue review |  |  | 1 | 1
TS | Wednesday | 2015-01-07 |  |  | Documentation |  | Sto FAQ documentation |  | 1.5 | 0 | -1
TS | Wednesday | 2015-01-07 |  |  | Other |  | co-ordination |  |  | 0.5 | 1
TS | Thursday | 2015-01-08 |  |  | Documentation |  | Sto component doc |  | 2.5 | 2 | 1
TS | Thursday | 2015-01-08 |  |  | Maintenance |  | Release notes |  | 1.5 | 2 | 1
TS | Thursday | 2015-01-08 |  |  | Planning |  | Planning excel |  | 1 | 1 | 1
TS | Thursday | 2015-01-08 |  |  | Maintenance |  | Cli support |  | 1 | 1 | 1
TS | Thursday | 2015-01-08 |  |  | Documentation |  | Sto faq doc |  | 1.5 | 1.5 | 1
TS | Thursday | 2015-01-08 |  |  | Other |  | co-ordiantion |  |  | 0.5 | 1
TS | Friday | 2015-01-09 |  |  | Maintenance |  | Weekly updates |  | 1 | 1 | 1
TS | Friday | 2015-01-09 |  |  | Maintenance |  | Meetings follow up |  | 1.5 | 1.5 | 1
TS | Friday | 2015-01-09 |  |  | Documentation |  | Sto tree |  | 2 | 2 | 1
TS | Friday | 2015-01-09 |  |  | Maintenance |  | Cli generalization |  | 1 | 1 | 1
TS | Friday | 2015-01-09 |  |  | Maintenance |  | Task maintenance |  | 3 | 3 | 1
TS | Monday | 2015-01-12 |  |  | Planning |  | Week/tracking |  | 0.5 | 0.5 | 1
TS | Monday | 2015-01-12 |  |  | Documentation |  | Hotel meeting preparation |  | 1 | 1 | 1
TS | Monday | 2015-01-12 |  |  | Documentation |  | Prd air fst doc |  | 3 | 3 | 1
TS | Monday | 2015-01-12 |  |  | Documentation |  | Cdv accesses pages |  | 1 | 1 | 1
TS | Monday | 2015-01-12 |  |  | Maintenance |  | Tasks follow up |  | 2 | 2 | 1
TS | Monday | 2015-01-12 |  |  | Other |  | Co-ordination |  | 0.5 | 0.5 | 1
TS | Tuesday | 2015-01-13 |  |  | Planning |  | Planning excel and cli excel |  | 1.5 | 1.5 | 1
TS | Tuesday | 2015-01-13 |  |  | Maintenance |  | Weekly updates |  | 1.5 | 1.5 | 1
TS | Tuesday | 2015-01-13 |  |  | Documentation |  | Aérien - Accompagnement documentation |  |  | 1.5 | 0
TS | Tuesday | 2015-01-13 |  |  | Documentation |  | CDV modules and services missing doc list |  | 1 | 0 | -1
TS | Tuesday | 2015-01-13 |  |  | Documentation |  | CDV air delivery 1.18.1 | Client, private , roadmap |  | 3 | 1
TS | Tuesday | 2015-01-13 |  |  | Maintenance |  | certain follow ups and tasks creation |  |  | 1 | 1
TS | Wednesday | 2015-01-14 |  |  | Maintenance |  | Deliveries updates, follow up, reminders |  | 1.5 | 1.5 | 1
TS | Wednesday | 2015-01-14 |  |  | Documentation |  | Aérien - Accompagnement documentation |  | 2.5 | 2.5 | 1
TS | Wednesday | 2015-01-14 |  |  | Maintenance |  | Cli follow up |  | 2 | 2 | 1
TS | Wednesday | 2015-01-14 |  |  | Maintenance |  | Tasks updates for Hv2.9 gantt |  | 2 | 2 | 1
TS | Thursday | 2015-01-15 |  |  | Maintenance |  | Task maintenance |  | 3 | 3.5 | 1
TS | Thursday | 2015-01-15 |  |  | Maintenance |  | Release notes |  | 2 | 2 | 1
TS |  |  |  |  | Documentation |  | CDV tree setup |  | 2.5 | 2.5 | 0
TS | Thursday | 2015-01-15 |  |  | Documentation |  | CDV modules and services missing doc list |  | 1 | 0.5 | 1
TS | Friday | 2015-01-16 |  |  | Maintenance |  | Meeting preparation |  | 3 | 3 | 1
TS | Friday | 2015-01-16 |  |  | Documentation |  | Sto doc |  | 3 | 2.5 | 1
TS | Friday | 2015-01-16 |  |  | Maintenance |  | cli doc + task creation |  | 1 | 1.5 | 1
TS | Friday | 2015-01-16 |  |  | Maintenance |  | Meetings follow up |  | 1.5 | 0.5 | 0
TS | Friday | 2015-01-16 |  |  | Other |  | Co-ordination |  |  | 0.5 | 1
TS | Monday | 2015-01-19 |  |  | Planning |  | Week/tracking |  | 0.75 | 0.75 | 1
TS | Monday | 2015-01-19 |  |  | Maintenance |  | Weekly updates |  | 0.75 | 1 | 1
TS | Monday | 2015-01-19 |  |  | Maintenance |  | Hotel meeting preparation |  | 1 | 1.25 | 1
TS | Monday | 2015-01-19 | #7936 |  | New |  | Tourinov mail configuration |  | 0.5 | 0.5 | 1
TS | Monday | 2015-01-19 | #7711, #7753, #7651, #7665, #7712 |  | tests |  | tasks validation |  | 2 | 2 | 1
TS | Monday | 2015-01-19 |  |  | Other |  | co-ordination |  | 0.5 | 0.5 | 1
TS | Monday | 2015-01-19 |  |  | Maintenance |  | Tasks follow up |  | 2 | 0.5 | 0
TS | Monday | 2015-01-19 |  |  | Maintenance |  | Dashboard meeting report |  |  | 1.5 | 1
TS | Tuesday | 2015-01-20 | #8004 |  | Documentation |  | Sto dictionary updates |  | 3 | 2.5 | 1
TS | Tuesday | 2015-01-20 |  |  | Planning |  | Planning excel |  | 1.5 | 1.5 | 1
TS | Tuesday | 2015-01-20 |  |  | tests |  | tasks validation and discussion w PS |  | 2 | 1.5 | 1
TS | Tuesday | 2015-01-20 |  |  | Maintenance |  | Tasks follow up |  | 1.5 | 1 | 1
TS | Tuesday | 2015-01-20 |  |  | Maintenance |  | Cli support |  | 1 | 1 | 1
TS | Tuesday | 2015-01-20 |  |  | Other |  | co-ordination |  |  | 0.5 | 1
TS | Wednesday | 2015-01-21 |  |  | Documentation |  | Sto dictionary updates |  | 3 | 3 | 1
TS | Wednesday | 2015-01-21 |  |  | Maintenance |  | Deliveries updates, follow up, reminders |  | 1.5 | 0 | -1
TS | Wednesday | 2015-01-21 |  |  | Documentation |  | Stock schedule documentation |  | 3 | 3 | 1
TS | Wednesday | 2015-01-21 |  |  | Maintenance |  | VDM meeting tasks follow up + mails |  | 2 | 2 | 1
TS | Wednesday | 2015-01-21 |  |  | Documentation |  | CDV tree | next week | 1 | 0 | -1
TS | Thursday | 2015-01-22 |  |  | Maintenance |  | Release notes |  | 2 | 1 | 1
TS | Thursday | 2015-01-22 |  |  | Maintenance |  | VDM agenda preparation |  | 1.5 | 2 | 1
TS | Thursday | 2015-01-22 |  |  | Maintenance |  | Cli follow up |  | 2 | 2.5 | 1
TS | Thursday | 2015-01-22 |  |  | Documentation |  | Sto dictionary renaming updates |  | 1.5 | 2 | 1
TS | Thursday | 2015-01-22 |  |  | Other |  | Co-ordination |  |  | 0.5 | 1
TS | Friday | 2015-01-23 |  |  | Maintenance |  | Task maintenance |  | 3 | 3.5 | 1
TS | Friday | 2015-01-23 |  |  | Documentation |  | Stock schedule feature documentation |  |  | 0 | -1
TS | Friday | 2015-01-23 |  |  | Maintenance |  | Weekly update |  | 1 | 1 | 1
TS | Friday | 2015-01-23 |  |  | Documentation |  | Cli generalization |  | 2 | 2 | 1
TS | Friday | 2015-01-23 |  |  | Maintenance |  | Meetings follow up |  | 1 | 1.5 | 1
TS | Monday | 2015-01-26 |  |  | Planning |  | Week/tracking |  | 0.75 | 0.75 | 1
TS | Monday | 2015-01-26 |  |  | Documentation |  | Task creations |  | 1.25 | 1.5 | 1
TS | Monday | 2015-01-26 |  |  | Documentation |  | Stock schedule feature documentation |  | 2 | 2 | 1
TS | Monday | 2015-01-26 |  |  | Maintenance |  | Hotel meeting preparation |  | 1.5 | 1.25 | 1
TS | Monday | 2015-01-26 |  |  | Maintenance |  | Tasks follow up |  | 2 | 2 | 1
TS | Monday | 2015-01-26 |  |  | Other |  | Co-ordination, mails |  | 0.5 | 0.5 | 1
TS | Tuesday | 2015-01-27 |  |  | Planning |  | Planning excel and cli excel |  | 1.5 | 1.5 | 1
TS | Tuesday | 2015-01-27 |  |  | Maintenance |  | Weekly updates |  | 1.5 | 0 | -1
TS | Tuesday | 2015-01-27 |  |  | Maintenance |  | Cli follow up |  | 2
TS | Tuesday | 2015-01-27 |  |  | Documentation |  | work on mails migration and release content |  | 3 | 4 | 1
| Tuesday | 2015-01-27 |  |  | Other |  | co-ordination |  |  | 0.5 | 1
TS | Wednesday | 2015-01-28 |  |  | Maintenance |  | creations of tasks |  | 1 | 1 | 1
TS | Wednesday | 2015-01-28 | 7866 |  | Documentation |  | Hotel DB wiki organization |  | 4.5 | 4.5 | 1
TS | Wednesday | 2015-01-28 |  |  | Maintenance |  | weekly updates |  | 1 | 1 | 1
TS | Wednesday | 2015-01-28 |  |  | Maintenance |  | Release notes |  | 1.5 | 2 | 1
TS | Thursday | 2015-01-29 |  |  | Documentation |  | Meeting report, actions, todos |  | 5 | 5 | 1
TS | Thursday | 2015-01-29 |  |  | Maintenance |  | Cli generalization |  | 2 | 2 | 1
TS | Thursday | 2015-01-29 |  |  | Maintenance |  | CDV wiki |  | 1 | 1 | 1
TS | Friday | 2015-01-30 |  |  | Maintenance |  | Weekly updates |  | 1 | 1 | 1
TS | Friday | 2015-01-30 |  |  | Maintenance |  | Task maintenance |  | 3.5 | 3.5 | 1
TS | Friday | 2015-01-30 |  |  | Maintenance |  | Meeting followup |  | 1.5 | 1.5 | 1
TS | Friday | 2015-01-30 |  |  | Documentation |  | Sto doc and dashboard |  | 2 | 2 | 1