## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0 | -1 | Leaves 2015-05-01 2015-05-25 I will need some leaves in APR/MAY on short notice
JS | Wednesday | 2015-04-01 | 8093 | 2.8_tests |  | 2.8 | Hotel | SQA tests between precache and prod | test + analysis | 3 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | 2.8 | Hotel | Make a list of quality control actions then tools to automate (JS+AF) | First discussion with Anne | 1 | 0 | -1
JS | Wednesday | 2015-04-01 |  | New | Documentation | 2.8 | Hotel | Describe usage +behavior of test tool EXP for DH |  | 1.5 | 0 | -1
JS | Wednesday | 2015-04-01 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 2 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | Afidium |  | Daily call |  | 0.25 | 0 | -1
JS | Wednesday | 2015-04-01 | 8586 | 2.8_tests |  | 2.8 | Hotel | Patch preparation + application | FTP patch update + test cleanup patch + apply . Wrote to CC on progress. + data check |  | 3.5 | 0
JS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates | tracking sheet + weekly meetings table | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-02 | 8586 | 2.8_tests |  | 2.8 | Hotel | Checked precache GTA data | checkded data + relaunched GTA GT + queued L + checked results afterwards |  | 2 | 1
JS | Thursday | 2015-04-02 | 8577 | New |  | 2.7 | Hotel | Cuba extrapolation | Patch for 2.7 : prepare + test |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8554 | Maintenance |  |  | Hotel | Check why RMT update fails on prod after new URL update | reproduce problem + fix + test. + change to remove DTD |  | 2.5 | 0
JS | Thursday | 2015-04-02 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | tests + analysis | 2 | 0 | -1
JS | Thursday | 2015-04-02 | 8309 | New |  | 2.9 | Hotel | Dynamic search EXP | studied RQ document for EXP |  | 1 | 0
JS | Thursday | 2015-04-02 | 8283 | Discussion | internal |  | TUI | Assist PS for updating SD-29142 instance + guide for fix | update + guide |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8093 | 2.8_tests |  | 2.8 | Hotel | Launch SQA test tool |  | 0.25 | 0 | -1
JS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Friday | 2015-04-03 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Changed code for DTD removal + tested on SD. To PS for further tests. Discuss with PS |  | 1.5 | 0
JS | Friday | 2015-04-03 | 8309 | New | Analysis |  | Hotel | Dynamic search EXP | Manual requests + analysis + discussion with DF | 4 | 3.5 | 0
JS | Friday | 2015-04-03 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | XSL change + started DB change |  | 1.25 | 0
JS | Friday | 2015-04-03 |  |  |  |  | Hotel | Merged 2.8 changes to 2.9 |  |  | 1 | 1
JS | Friday | 2015-04-03 |  | Planning | internal | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions |  | 3.5 | 0 | -1
JS | Friday | 2015-04-03 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.5 | 1
JS | Monday | 2015-04-06 |  | Planning | internal |  |  | Weekly planning | tracking sheet + objective status update | 1 | 1 | 0
JS | Monday | 2015-04-06 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | changes SQA + SPR SPs. Yet to implement Match + XSL change. Asked PS for test cases | 2 | 2 | 0
JS | Monday | 2015-04-06 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | updated devcache + GTs + L + mentioned how to check | 1 | 1 | 0
JS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Check update files + finalize patch |  | 1.5 | 1
JS | Tuesday | 2015-04-07 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | finish code + Tests | 2 | 4.5 | 1
JS | Tuesday | 2015-04-07 |  | Discussion | internal |  | Hotel | Answer CC questions regarding EXP | EXP update for hotel + checked corrections for booking ref in 2.8 |  | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8309 | New |  |  | Hotel | Dynamic search EXP | Started test tool dev | 3 | 0.5 | 0
JS | Tuesday | 2015-04-07 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Tuesday | 2015-04-07 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Discuss with CC + start implementation | 2.5 | 0 | -1
JS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8654 | 2.8_tests |  | 2.8 | Hotel | EXP CB problem on precache | check + fix + test + patch |  | 3 | 1
JS | Wednesday | 2015-04-08 |  | Planning | internal | Afidium | Hotel | Hotel weekly planning | with DF, CC |  | 0.5 | 1
JS | Wednesday | 2015-04-08 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8309 | New |  |  | Hotel | Dynamic search EXP | Tool coding |  | 2.5 | 0
JS | Wednesday | 2015-04-08 |  | Discussion | snapin |  | Hotel | Call with Raj + Shubhad for brief on hotel and what to do for 8660 |  |  | 1 | 1
JS | Wednesday | 2015-04-08 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Implementation + tests | 7.5 | 0 | -1
JS | Wednesday | 2015-04-08 | 8566 | Discussion | internal | 2.8 | Hotel | Dashboard issue | Discussion with everybody + conclude as corner case. To DF for approval of planning for 2.9 |  | 0.5 | 1
JS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25
JS | Thursday | 2015-04-09 |  | Discussion |  | Afidium |  | Daily call |  | 0.25
JS | Thursday | 2015-04-09 | 8309 | New |  |  | Hotel | Dynamic search EXP | Finish Test tool coding + start tests | 7.5
JS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates |  | 0.25
JS | Friday | 2015-04-10 |  | Discussion |  | Afidium |  | Daily call |  | 0.25
JS | Friday | 2015-04-10 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5
JS | Friday | 2015-04-10 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5
JS | Friday | 2015-04-10 |  |  |  | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions |  | 3
JS | Friday | 2015-04-10 |  |  |  | 2.9 | Hotel | List use cases for 2.9 |  | 3
PS | Wednesday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.5 | 1 | Leaves 2015-04-08 to 2015-04-12 2015-05-01
PS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 1 | 1 | 1
PS | Wednesday | 2015-04-01 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-01 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schema | based on CC's suggestion | 3 | 0 | -1
PS | Wednesday | 2015-04-01 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | read doc + xsl + questions and problems to CC + test | 2 | 5 | 0
PS | Wednesday | 2015-04-01 | 8238 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | correction of an issue with CC + test |  | 1 | 1
PS | Thursday | 2015-04-02 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet + venda report | 0.5 | 1 | 1
PS | Thursday | 2015-04-02 |  | Discussion | snapin |  |  | discussions + support for snapin | MM + SK | 1.5 | 1 | 1
PS | Thursday | 2015-04-02 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | Done + remaining listed in task | 3 | 2.5 | 0
PS | Thursday | 2015-04-02 | 8283 | New |  |  | TUI | Addition of parend log in Response | Checked Issue + corrections C# + test + problems on my computer | 3 | 3 | 1
PS | Friday | 2015-04-03 |  | Maintenance |  |  | Hotel | Production COT | Mails+ Reply | 0.25 | 0.25 | 1
PS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 0.5 | 1.5 | 1
PS | Friday | 2015-04-03 |  | Discussion | snapin |  |  | discussions + support for snapin | Feedback to Raj for mail | 1.5 | 0.5 | 1
PS | Friday | 2015-04-03 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schemas according to the documentation Update |  | 3 | 3 | 1
PS | Friday | 2015-04-03 | 8554 | New |  |  | Hotel | RMT failed on production | Loads + analysis | 3 | 3 | 1
PS | Monday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates + discussions | Uma : some testcases to her | 1 | 0.5 | 1
PS | Monday | 2015-04-06 |  | Discussion | snapin |  |  | discussions + support for snapin | SK + Raj + MM | 1.5 | 0.5 | 1
PS | Monday | 2015-04-06 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency |  | 2 | 2 | 1
PS | Monday | 2015-04-06 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Remaing : questins with CC + 3rd step | 4 | 2.75 | 0
PS | Monday | 2015-04-06 | 8581 | New |  |  | Hotel | RMT failed on production |  | 2 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Maintenance |  |  | Hotel | Production COT | Prod Mail | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet+ ST (2.8_rep tests) | 1 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Discussion | snapin |  |  | discussions + support for snapin | Raj + SK + RN | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8554 | New |  |  | Hotel | RMT failed on production | Some testcases to execute | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency | Testcases correction | 0.5 | 1.5 | 1
PS | Tuesday | 2015-04-07 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | questions with CC + proceed, not finished | 2 | 1.5 | 0
PS | Tuesday | 2015-04-07 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add Service/Insurance segments, seat assignment and insurance booking in Bookings | Output to CC for verification + question | 2.25 | 0.75 | 0
PS | Wednesday | 2015-04-08 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Wednesday | 2015-04-08 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Wednesday | 2015-04-08 | [5 empty] | Available to assign |  | 5
PS | Thursday | 2015-04-09 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Thursday | 2015-04-09 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Thursday | 2015-04-09 | [5 empty] | Available to assign |  | 5
PS | Friday | 2015-04-10 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Friday | 2015-04-10 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5
PS | Friday | 2015-04-10 | [5 empty] | Available to assign |  | 5 |  |  | Leaves 2015-03-30 to 2015-04-05 2015-05-01
ST | Thursday | 2015-04-02 | [5 empty] | Leave
ST | Friday | 2015-04-03 | [5 empty] | Leave
ST | Monday | 2015-04-06 |  | Discussion | internal |  | Stock | Discussion with Uma | Discussion about this week's plan, 8619, 8395, Hotel new server | 1 | 1.4 | 1
ST | Monday | 2015-04-06 | 8187 | New | server setup | 2.8 | Hotel | 2.8 New server DB : Updates Issues | Apply the recent installation script, executed post processing manually | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8188 | New | server setup | 2.9 | Hotel | 2.9 New server DB : Updates Issues | Correct the synonyms | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Checked the GQA script and suggested UZ to take help of PS and run some sqa, spr and gqa valid queries |  | 0.4 | 1
ST | Monday | 2015-04-06 | 8244 | Maintenance |  | 2.8 | Hotel | Mail shows 0 room updated for JNV | check and updated task with details |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | New | server setup |  |  | Setup of sql server for Rajendra | Setup Raj id on sd-29142 and checked his access problem |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates and discussion | tracking sheet and weekly task | 0.25 | 0.4 | 1
ST | Tuesday | 2015-04-07 | 8636 | Maintenance |  | 2.8 | Hotel | sp_checkIndex need correction for 2.8 | Analysis and testing and task updated | 1 | 0.5 | 0
ST | Tuesday | 2015-04-07 | 8637 | New |  |  | Hotel | Create 2.9 DB without galaxyref | guide uma | 0.5 | 0 | -1
ST | Tuesday | 2015-04-07 | 8575 | 2.8_tests |  | 2.8 | Hotel | Check se_versioned_tarif cleanup | Analysis and testing and task updated | 1 | 2 | 1
ST | Tuesday | 2015-04-07 | 8619 | New |  | 1.1 | Stock | Change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Analysis, discussion and proposal | 1.25 | 1 | 1
ST | Tuesday | 2015-04-07 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Testing of SQA, GQA and SPR on 2.8_rep database |  | 0.5 | 1
ST | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.25
ST | Wednesday | 2015-04-08 | [5 empty] | Free to allocate |  | 3.75
ST | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.25
ST | Thursday | 2015-04-09 | [5 empty] | Free to allocate |  | 3.75
ST | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.25
ST | Friday | 2015-04-10 | [5 empty] | Free to allocate |  | 3.75
UZ | Wednesday | 2015-04-01 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1 | 0.5 | 1 | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Wednesday | 2015-04-01 | 8187 |  |  | 2.8 | Hotel | Sd-2.8 New server DB: Updates issues | checked updated on new server |  | 0.25 | 1
UZ | Wednesday | 2015-04-01 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | Modified SP + testing | 1 | 1.25 | 0
UZ | Wednesday | 2015-04-01 | 8528 | New | pgsql |  | Stock | improve location management | modified view + created SP + testing | 4 | 4 | 1
UZ | Thursday | 2015-04-02 | 8272 |  |  |  | Hotel | test data in replication server & execute search | data validation | 1 | 0.5 | 1
UZ | Thursday | 2015-04-02 | 7639 | New | Replication |  | Hotel | setup of replication activity | check for indexes are present or not on new server |  | 0.25 | 1
UZ | Thursday | 2015-04-02 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | added column in table + Modified SP |  | 1.25 | 0
UZ | Thursday | 2015-04-02 | 8604 | New | pgsql |  | Stock | create a SP to return external references for given booking | created SP + testing + coordinate with SS (to help him) |  | 2.5 | 1
UZ | Thursday | 2015-04-02 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | testing + update task |  | 1.25 | 1
UZ | Friday | 2015-04-03 | 8272 |  |  |  | Hotel | test data in replication server & execute search | testing + update task | 1 | 1 | 1
UZ | Friday | 2015-04-03 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | Modified SP + testing | 1 | 1.5 | 1
UZ | Friday | 2015-04-03 | 8619 | New | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | analysis | 4 | 1.75 | 0
UZ | Friday | 2015-04-03 | 8637 | New | pgsql |  | Stock | modify sys function | discuss with ST + update task |  | 0.25 | 1
UZ | Friday | 2015-04-03 |  | Planning | internal |  |  | discuss with ST | call with ST for Planning + work status |  | 0.5 | 1
UZ | Friday | 2015-04-03 | 8460 | New |  |  | Stock | booking + winter | correct daigram |  | 1 | 1
UZ | Monday | 2015-04-06 | 8188 | New | Replication | 2.9 | Hotel | 2.9 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.5 | 1
UZ | Monday | 2015-04-06 | 8187 | New | Replication | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.25 | 1
UZ | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | test data in replication server & execute search | data validation + created wiki + updated task | 1 | 1 | 1
UZ | Monday | 2015-04-06 | 8619 | New |  | 1.1 | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | discuss with ST + update task | 1 | 1 | 0
UZ | Monday | 2015-04-06 | 8395 | New |  | 1.1 | Stock | Improve stats speed | Discuss with ST, testing, updated task | 1 | 1.25 | 0
UZ | Monday | 2015-04-06 | 8528 | New | Documentation | 1.1 | Stock | improve location management | Created wiki for view & SP | 1.5 | 1.5 | 1
UZ | Monday | 2015-04-06 |  | Planning | internal |  |  | discuss with ST | call with ST for work planning | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-04-07 | 8272 |  |  |  | Hotel | test data in replication server & execute search | tested data + excuted search + updated task | 0.5 | 0.75 | 1
UZ | Tuesday | 2015-04-07 | 8188 |  |  |  | Hotel | Sd-2.9 New server DB : Updates Issues | checked updates | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | checked updates + updated task | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | call with ST + analysis + planning | 2.5 | 2.5 | 0
UZ | Tuesday | 2015-04-07 | 8567 |  | pgsql |  | Stock | Add error message into SP sto_quotation__search if quotation search doesn't return any results | discuss with YT and coding and testing | 1 | 1 | 1
UZ | Tuesday | 2015-04-07 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport | Analysis+praposal | 1.5 | 1 | 0
UZ | Tuesday | 2015-04-07 |  |  | internal |  |  | fill up tracking sheet |  |  | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 0.25
UZ | Wednesday | 2015-04-08 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task | 0.25
UZ | Wednesday | 2015-04-08 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task | 0.25
UZ | Wednesday | 2015-04-08 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions |  | 4
UZ | Wednesday | 2015-04-08 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport |  | 1
UZ | Thursday | 2015-04-09 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task
UZ | Thursday | 2015-04-09 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task
UZ | Thursday | 2015-04-09 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task
UZ | Thursday | 2015-04-09 | 8250 |  | pgsql |  | Stock | LogManagerFS : convert code from sql to pgsql | Coordinate with Dhanesh and help him to finish it
UZ | Thursday | 2015-04-09 | 8249 |  | pgsql |  | Stock | [PGSQL] Check All core_modules Tables | Coordinate with Dhanesh and help him to finish it
UZ | Thursday | 2015-04-09 | 8197 |  | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis and Discussion
UZ | Friday | 2015-04-10 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task
UZ | Friday | 2015-04-10 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task
UZ | Friday | 2015-04-10 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task
UZ | Friday | 2015-04-10 | 8187 |  | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Coding and testing
UZ | Friday | 2015-04-10 | 8629 |  | pgsql |  | Stock | document bkg_booking__replace | Documentation