## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Comment | Important information
JS | Monday | 2015-02-02 |  | Planning | internal |  |  | Daily updates + discussions | discussions + updates + weekly planning + ST + AF | 2 | 4 | 1 |  | Leaves 28 Feb - 8 Mar 3rd Apr - 12th Apr Work hours in Feb Wednesdays : 8AM - 5PM HKT Work hours from March Monday and Friday : 8AM - 5PM HKT
JS | Monday | 2015-02-02 | 8110 | New | test_tool_2.9 | 2.9 | Hotel | review Uma's work + plan time for this week | wt_tlog_read |  | 0.5 | 1
JS | Monday | 2015-02-02 | 8036 | New | galaxy_phase2 | 2.9 | Hotel | review Uma's work + plan time for this week | se_currency__import |  | 0.5 | 1
JS | Monday | 2015-02-02 | 8084 | New | 2.8_tests | 2.8 | Hotel | EXP currency change - tests | Provide examples to CC for CHF, EUR case | 1 | 0 | -1
JS | Monday | 2015-02-02 |  | Planning | internal | AFI |  | weekly planning call |  | 1 | 1 | 1
JS | Monday | 2015-02-02 | 8073 | New | 2.8_tests | 2.8 | Hotel | Tool for testing TRP availability | Analysis + documentation | 1.5 | 2 | 0
JS | Monday | 2015-02-02 |  | New | 2.7_lot_patch | 2.7 | Hotel | Check VDM import | checked lots + mail |  | 0.5 | 1
JS | Monday | 2015-02-02 |  | Planning | internal |  |  | Call with DF for hotel planning |  |  | 1 | 1
JS | Monday | 2015-02-02 | 8086 | New | 2.8_tests | 2.8 | Hotel | Check impact of disabling sort |  | 2 | 0 | -1
JS | Tuesday | 2015-02-03 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Tuesday | 2015-02-03 | 8084 | New | 2.8_tests | 2.8 | Hotel | EXP currency change - tests | Provide examples to CC for CHF, EUR case | 1 | 0.5 | 1
JS | Tuesday | 2015-02-03 | 8061 | Maintenance | 2.7_data_check | 2.7 | Hotel | Analysis of RMT Quad issue | Not a problem on our side |  | 1 | 1
JS | Tuesday | 2015-02-03 | 8127 | New | provider_change | 2.7 | Hotel | Change URLs for ABI, ABS | task for PS + update instances |  | 0.5 | 1
JS | Tuesday | 2015-02-03 | 8086 | New | 2.8_tests | 2.8 | Hotel | Check impact of disabling sort | Discussed impact with Anne. Yet to take decision | 2 | 2 | 0
JS | Tuesday | 2015-02-03 |  | tech_analysis | 2.8_tests |  |  | Discussion with Anne | child ages + disable sort + index rebuild |  | 2 | 1
JS | Tuesday | 2015-02-03 |  | design_review | 2.8_test_tool |  |  | Call with DF to present test tool proposal |  | 1 | 0.75 | 1
JS | Tuesday | 2015-02-03 | 8126 | New | 2.7_lot_patch | 2.7 | Hotel | Patch for VDM lot | code + test. Checked why th tarifs were picked up | 3 | 7 | 0
JS | Wednesday | 2015-02-04 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Wednesday | 2015-02-04 | 8126 | New | 2.7_lot_patch | 2.7 | Hotel | lot patch correction + tests | tests + corrections + wiki |  | 8 | 0
JS | Wednesday | 2015-02-04 | 8073 | New | 2.8_tests | 2.8 | Hotel | Availability test tool | code + test | 7 | 5 | 0
JS | Thursday | 2015-02-05 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA Test tool development | start coding |  | 0 | -1
JS | Thursday | 2015-02-05 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-02-05 | 8073 | New | 2.8_tests | 2.8 | Hotel | Availability test tool | code + test | 3 | 2.5 | 1
JS | Thursday | 2015-02-05 | 8126 | New | 2.7_lot_patch | 2.7 | Hotel | finalize lot patch |  | 4 | 6 | 1
JS | Friday | 2015-02-06 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Friday | 2015-02-06 | 8126 | New | 2.7_lot_patch | 2.7 | Hotel | Check prod data + post processing problem | prod check + analysis of sort failure + next actions + support finalization | 3.5 | 4 | 1
JS | Friday | 2015-02-06 |  | Maintenance | 2.7_data_check |  |  | EXP hotel list check - DF email | 3 hotel check + tool latest list |  | 0.5 | 1
JS | Friday | 2015-02-06 | 8073 | New | 2.8_tests | 2.8 | Hotel | Availability test tool | finished coding. Tests in next week | 3.5 | 3 | 0
JS | Friday | 2015-02-06 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA Test tool development | code + test | 0 | 0 | -1
JS | Monday | 2015-02-09 |  | Planning | internal |  |  | Weekly planning + discussions |  | 3 | 4 | 1
JS | Monday | 2015-02-09 |  | Planning | internal | AFI |  | Weekly planning call |  | 1 | 1 | 1
JS | Monday | 2015-02-09 |  | Planning | internal |  |  | Call with David - uma planning, sheet update |  |  | 0.5 | 1
JS | Monday | 2015-02-09 | 8073 | New | 2.8_tests | 2.8 | Hotel | Availability test tool | Tool tested. Need to start tests and generate files | 3 | 4 | 0
JS | Monday | 2015-02-09 | 7746 | New | documentation | 2.8 | Hotel | Improve documentation |  | 1 | 0 | -1
JS | Tuesday | 2015-02-10 | 7746 | New | documentation | 2.8 | Hotel | Improve documentation |  | 1 | 0 | -1
JS | Tuesday | 2015-02-10 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA Test tool development | coding - import + replay + compare | 4 | 4 | 0
JS | Tuesday | 2015-02-10 | 8073 | New | 2.8_tests | 2.8 | Hotel | Tourplan availability test tool | Started data tests | 3 | 2.5 | 0
JS | Tuesday | 2015-02-10 | 8081 | debriefing | internal |  | Stock | Calls with Anne, Uma |  |  | 1.5 | 1
JS | Tuesday | 2015-02-10 |  | 2.8_tests | internal | 2.8 | Hotel | Patch checking with CC | Have to check more to confirm |  | 0.25 | 0
JS | Tuesday | 2015-02-10 |  | Planning | internal |  |  | Daily updates + discussions | call with Shweta for planning of week | 1 | 0.5 | 1
JS | Wednesday | 2015-02-11 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA Test tool development | test + fix + refine + start data tests | 3 | 2 | 0
JS | Wednesday | 2015-02-11 | 8073 | New | 2.8_tests | 2.8 | Hotel | Tourplan availability test tool | Data analysis + final data generation | 4 | 5 | 1
JS | Wednesday | 2015-02-11 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Wednesday | 2015-02-11 | 8131 | New | 2.8_tests | 2.8 | Hotel | child ages implementation | XSL change + synchro + test + compare data + SQA tests | 4 | 0 | -1
JS | Thursday | 2015-02-12 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-02-12 | 8131 | New | 2.8_tests |  |  | child ages implementation | tests | 1 | 0 | -1
JS | Thursday | 2015-02-12 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA Test tool development | code + test + started data tests | 6 | 6 | 0
JS | Thursday | 2015-02-12 | 8167 | Discussions | internal |  | Hotel | Discussion with CC | CC wanted to understand about the EXP hotels mentioned in 8167 + proof for gaps in date ranges |  | 0.5 | 1
JS | Thursday | 2015-02-12 | 8103 | Tests | 2.8_tests | 2.8 | Hotel | Check dashboard task for CSV date problem | check + fix + test | 2 | 2 | 1
JS | Thursday | 2015-02-12 | 8007 | Maintenance | 2.7_data_check | 2.7 | Hotel | Compare prod + precache data |  | 3 | 0 | -1 | Friday or next week
JS | Friday | 2015-02-13 | 8094 | New | 2.8_release | 2.8 | Hotel | Finalize 2.8 installation | make + test | 4 | 0 | 0
JS | Friday | 2015-02-13 |  | Planning | internal |  |  | Daily updates + discussions | tracking sheet updates + discussions | 1 | 1 | 1
JS | Friday | 2015-02-13 |  | debriefing | internal |  |  | Debrief Pankhuri for tester training + plan with her |  |  | 1 | 1
JS | Friday | 2015-02-13 | 8132 | New | 2.8_tests |  | Hotel | child ages implementation | change XSL + test on 2.9, 2.8 and 2.7 |  | 1.5 | 1
JS | Friday | 2015-02-13 | 8044 | New | 2.8_release |  |  | Installation + patch documentation |  | 2 | 0 | -1
JS | Friday | 2015-02-13 | 7746 | New | documentation | 2.8 | Hotel | Extrapolation documentation | improve documentation | 2 | 0 | -1
JS | Friday | 2015-02-13 | 8103 | 2.8_tests | Dashboard | 2.8 | Hotel | Correct date on dashboard & CSV | tests on devcache |  | 0.5 | 1
JS | Friday | 2015-02-13 |  | Maintenance | internal | 2.8 | Hotel | List evolutions done in 2.8 during 2.7 maintenance tasks |  |  | 1 | 1
JS | Friday | 2015-02-13 | 8215 | Maintenance |  | 2.7 | Hotel | Room 2+2 issue | Analysis + checked past issues + call with Anne + further data check + script |  | 2.5 | 1
JS | Friday | 2015-02-13 | 8093 | New | 2.8_tests | 2.8 | Hotel | SQA test tool | Tests + analysis + data sheets | 4 | 3 | 0
JS | Monday | 2015-02-16 | 8169 | New |  | 2.2 | TUI | e-retail interface implementation, amadeus-eretail host | Code + connectivity with e-retail | 5 | 5 | 0
JS | Monday | 2015-02-16 |  | Planning | internal |  |  | Weekly planning calls |  | 3 | 3 | 1
JS | Monday | 2015-02-16 | 8184 | Maintenance |  | 2.7 | Hotel | Bonotel room update failure | Check + analyse + try to reproduce + explain in mail |  | 2 | 1
JS | Monday | 2015-02-16 | 8162 | Maintenance |  | 2.7 | Hotel | Check EXP hotels in this week |  |  | 0.5 | 1
JS | Tuesday | 2015-02-17 | 8169 | New |  | 2.2 | TUI | e-retail interface implementation, amadeus-eretail host | encoding + Logging + error handling + unit tests | 4 | 4 | 1
JS | Tuesday | 2015-02-17 | 8228 | New |  |  | TUI | Check duplicate log problem | Checked, discuss with CC + fix + test |  | 1 | 1
JS | Tuesday | 2015-02-17 | 8184 | Maintenance |  | 2.7 | Hotel | Bonotel room update failure | replicate + fix | 3 | 1.5 | 0
JS | Tuesday | 2015-02-17 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Wednesday | 2015-02-18 | 8093 | New |  | 2.8 | Hotel | SQA Test tool | analyse differences to ensure there are no problems | 4 | 4 | 0
JS | Wednesday | 2015-02-18 | 8184 | Maintenance |  | 2.7 | Hotel | Bonotel room update failure | Checked results - OK. To AF to ask If we patch |  | 0.5 | 1
JS | Wednesday | 2015-02-18 | 8165 | Release |  | 2.8 | Hotel | DB script for 2.8 release | hg diff for shweta to consider + check search margin + upload tarif SPs |  | 2 | 1
JS | Wednesday | 2015-02-18 |  | Maintenance |  | 2.7 | Hotel | Prod mail reports 0 JNV room update | Checked , mail problem. To ST |  | 0.5 | 1
JS | Wednesday | 2015-02-18 | 8132 | New |  | 2.7 | Hotel | child ages implementation | Finish XSL changes + test for data check + fixes | 3 | 0 | -1
JS | Wednesday | 2015-02-18 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-02-19 | 7490 | 2.8_tests |  | 2.8 | Hotel | Tourplan XSL improvement | test + finalize | 0.5 | 0 | -1
JS | Thursday | 2015-02-19 | 8093 | New |  | 2.8 | Hotel | SQA Test Tool | VDM case analysis + script for correction + discussion with Anne for patch |  | 5.5 | 0
JS | Thursday | 2015-02-19 | 8176 | 2.8_tests |  | 2.8 | Hotel | GTA XMl API change | Check impact | 0.5 | 0.5 | 1
JS | Thursday | 2015-02-19 | 8133 | Maintenance | discussion | 2.7 | Hotel | Expedia hotels | Discuss with CC + check + analyse + mail response |  | 0.5 | 1
JS | Thursday | 2015-02-19 |  | Maintenance | internal |  |  | New server problem | discuss with Anne + checks |  | 0.5 | 1
JS | Thursday | 2015-02-19 | 6223 | 2.8_tests |  | 2.8 | Hotel | Test log speed + async | Added speed test to test tool | 2 | 1 | 0
JS | Thursday | 2015-02-19 | 8165 | Release |  | 2.8 | Hotel | 2.8 DB release scripts | test + finalize | 4 | 0 | -1
JS | Thursday | 2015-02-19 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Friday | 2015-02-20 | 8094 | Release |  | 2.8 | Hotel | 2.8 release - installer | prepare + test + finalize installation | 5 | 0 | -1
JS | Friday | 2015-02-20 | 6223 | 2.8_tests |  | 2.8 | Hotel | Logging improvement | tests + reverted changes for 2.8 + next steps + call with Anne |  | 2.25 | 1
JS | Friday | 2015-02-20 | 8132 | 2.8_tests |  | 2.8 | Hotel | child ages implementation | Finalize XSL change + test + call with Anne |  | 2.25 | 1
JS | Friday | 2015-02-20 |  | Discussions |  |  | Air | Discuss with Sanket | answer queries + help |  | 0.5 | 1
JS | Friday | 2015-02-20 | 7490 | 2.8_tests |  | 2.8 | Hotel | Tourplan XSL improvement | test + finalize |  | 0.5 | 0
JS | Friday | 2015-02-20 | 8044 | Documentation |  | 2.8 | Hotel | Installation + patch documentation |  | 2 | 0 | -1
JS | Friday | 2015-02-20 | 8261 | Maintenance |  | 2.7 | Hotel | Patch for data correction for production | prepare patch + test |  | 1.5 | 1
JS | Friday | 2015-02-20 | 8131 | 2.8_tests |  | 2.8 | Hotel | child ages implementation | Check Shweta's work + test cases + discussions with Anne. Have questions |  | 2.5 | 0
JS | Friday | 2015-02-20 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Saturday | 2015-02-21 | 7490 | 2.8_tests |  | 2.8 | Hotel | Tourplan XSL improvement | test + finalize |  | 1.5 | 1
JS | Sunday | 2015-02-22 | 6903 | 2.8_tests |  | 2.8 | Hotel | Automatic cleanup of se_versioned_tarif | test + finalize |  | 2 | 1
JS | Monday | 2015-02-23 | 8094 | Release |  | 2.8 | Hotel | Prepare 2.8 release | prepared installer + async + se_task_control script + installation test cases + tested on devcache |  | 4.5 | 0
JS | Monday | 2015-02-23 | 8165 | Release |  | 2.8 | Hotel | 2.8 DB script | test script + recreated + tested + finalized |  | 4 | 1
JS | Monday | 2015-02-23 | 8094 | Release |  | 2.8 | Hotel | Prepare 2.8 release | Dashboard installation discussion with Emilise + try installation |  | 1 | 0
JS | Monday | 2015-02-23 |  | Planning | internal |  | Hotel | Weekly planning call |  |  | 1 | 1
JS | Monday | 2015-02-23 |  | Discussions | internal |  |  | Discussion with Anne about resources + new server |  |  | 0.5 | 1
JS | Tuesday | 2015-02-24 | 8094 | Release |  | 2.8 | Hotel | Prepare 2.8 release | Finalize release + dashboard installation | 4 | 2.5 | 1
JS | Tuesday | 2015-02-24 |  | Training | internal |  | Air | Discussion with Shubhad + Sanket + manali | Help on mod_stock to call module function + how sequencer works. Hotel project requirements + how to setup wiki |  | 1.5 | 1
JS | Tuesday | 2015-02-24 |  | Assistance | internal |  | TUI | Update marmara wenji on dev server | update + correct transacDecode |  | 0.5 | 1
JS | Tuesday | 2015-02-24 |  | Documentation |  | 2.8 | Hotel | List of evolutions and patches for 2.8 |  |  | 1 | 1
JS | Tuesday | 2015-02-24 | 8044 | Documentation |  |  | Hotel | Installation + patch documentation |  | 2 | 1.5 | 1
JS | Tuesday | 2015-02-24 | 8080 | 2.8_tests |  | 2.8 | Hotel | Call with Anne | Call with Anne for child ages |  | 0.5 | 1
JS | Tuesday | 2015-02-24 |  | Planning | internal |  |  | Weekly planning for PS, UZ, ST |  | 2 | 1.5 | 1
JS | Wednesday | 2015-02-25 |  | Discussions | internal | 2.9 | Hotel | Call with AF + ST | Planning for my leave + price v3 | 1 | 0 | -1
JS | Wednesday | 2015-02-25 |  | Analysis |  | 2.9 | Hotel | Analysis of price v3 |  | 2 | 0 | -1
JS | Wednesday | 2015-02-25 |  | Discussions | snapin |  |  | Discuss with Sanket, Shubhad, Manali | 8275 with Sanket, 8283 with Manali |  | 1 | 1
JS | Wednesday | 2015-02-25 |  | Documentation | internal | 2.9 | Hotel | List of use cases for 2.9 | Started making a list of evolutions for 2.9 |  | 0.5 | 0
JS | Wednesday | 2015-02-25 | 8286 | Maintenance |  | 2.7 | Hotel | Check hotels not extrapolated | Fixed with patch on 22nd. Checked each hotel mentioned in task |  | 1 | 1
JS | Wednesday | 2015-02-25 | 8257 | Analysis |  | 2.9 | Hotel | Bottlenecks in wenji code | checked code + bottlenecks |  | 3.5 | 0
JS | Wednesday | 2015-02-25 | 8087 | 2.8_tests | Patch | 2.8 | Hotel | EXP cache evolution | Analysis. This not needed. Call with AF | 3 | 1 | 0
JS | Wednesday | 2015-02-25 |  | 2.8_tests |  | 2.8 | Hotel | Daily SQA tests | test + analyse | 2 | 0 | -1
JS | Wednesday | 2015-02-25 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-02-26 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 1 | 1
JS | Thursday | 2015-02-26 |  | Maintenance | internal | 2.9 | Hotel | Grafted recent 2.8 revisions in 2.9 branch |  |  | 1 | 1
JS | Thursday | 2015-02-26 | 8295 | New |  | 2.8 | Hotel | Room only MP for ABT | code + test. |  | 2 | 0
|  |  | 8294 | 2.8_tests | Dashboard | 2.8 | Hotel | URL correction of hotel | Call with EM to explain problem |  | 0.25 | 1
JS | Thursday | 2015-02-26 | 8131 | 2.8_tests | Patch | 2.8 | Hotel | child ages implementation | test + finalize patch | 2 | 0 | -1
JS | Thursday | 2015-02-26 |  | Training | snapin |  |  | Discussions with Sanket + Manali + Shubhad | VS installation not ready yet. |  | 2.5 | 0
JS | Thursday | 2015-02-26 |  | Planning | internal |  | Hotel | Call with AF + ST | My leave planning + price v3 + child ages | 1 | 0.75 | 1
JS | Thursday | 2015-02-26 | 8290 | 2.8_tests | Patch | 2.8 | Hotel | EXP cache evolution | update test tool | 3 | 2 | 0
JS | Friday | 2015-02-27 |  | 2.8_tests |  | 2.8 | Hotel | Daily SQA tests | test + analyse | 2 | 0 | -1
JS | Friday | 2015-02-27 |  | Documentation |  | 2.9 | Hotel | 2.9 actions for tests - use cases |  | 2 | 0 | -1
JS | Friday | 2015-02-27 | 8290 | New |  | 2.8 | Hotel | Test tool for EXP hotel list | test + fix |  | 1.5 | 1
JS | Friday | 2015-02-27 | 8162 | Maintenance |  | 2.8 | Hotel | Check Expedia hotels this week | Checked hotels + discussed with PS |  | 0.5 | 1
JS | Friday | 2015-02-27 | 8303 | Maintenance |  | 2.8 | Hotel | Expedia child occupancy problem | analysis + discussion CC AF + fix + test |  | 4 | 0
JS | Friday | 2015-02-27 | 8294 | Maintenance | Dashboard | 2.8 | Hotel | Discuss with Eduard for dashboard correction | Discuss EM + EP for stable branch update + update instances + validate |  | 2 | 1
JS | Friday | 2015-02-27 | 8283 | Discussions | snapin |  | TUI | Discuss with Shubhad + Manali |  |  | 1.5 | 1
JS | Friday | 2015-02-27 | 8295 | New |  | 2.8 | Hotel | Abbeytours Room Only MP | test + ask PS for tests to finalize patch |  | 0.5 | 1
JS | Friday | 2015-02-27 |  | Planning | internal |  |  | Daily updates + discussions |  | 2 | 1 | 1
JS | Friday | 2015-02-27 |  | 2.8_tests |  | 2.8 | Hotel | Review dashboard tests | review + check + fix if any | 2 | 0 | -1
JS | Saturday | 2015-02-28 | [5 empty] | tracking sheet |  | 0.5 | 0.5 | 0
JS | Saturday | 2015-02-28 | 8303 | Maintenance |  | 2.8 | Hotel | Expedia child occupancy problem | Finalize patch + update installer |  | 4 | 1
PS | Monday | 2015-02-02 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1 |  | Leaves 2015-03-05 to 2015-03-06
PS | Monday | 2015-02-02 | [5 empty] | Daily updates + discussions | 8014 update + mails + weekplan | 0.75 | 1.5 | 1
PS | Monday | 2015-02-02 | [5 empty] | Venda report |  | 0.5 | 0.25 | 1
PS | Monday | 2015-02-02 | 7651 |  |  | 2.9 | Hotel | [SQA - SP RS] Documentation update | Problem in build_target | 1 | 1 | -1
PS | Monday | 2015-02-02 | 7711 |  |  | 2.9 | Hotel | [SE] Documentation SE_RQ and SE_RS | Problems reported | 3 | 2 | 1
PS | Monday | 2015-02-02 | 7079 |  |  | 2.8 |  | Dashboard re-check |  | 0.5 | 0.5 | 1
PS | Monday | 2015-02-02 | 7665 |  |  |  |  | [SQA - SP] Documentation update |  |  | 1 | 1
PS | Monday | 2015-02-02 | 8105 | Tests |  | 2.8 | Hotel | Clarify dashboard wikis | EXP n GTA Technical restore | 2 | 1.5 | 1
PS | Tuesday | 2015-02-03 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-02-03 | [5 empty] | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Tuesday | 2015-02-03 | 8105 | Tests |  | 2.8 | Hotel | Clarify dashboard wikis |  | 4 | 4 | 1
PS | Tuesday | 2015-02-03 | 7651 | New |  | 2.9 | Hotel | [SQA - SP RS] Documentation update | Tried the same for TUI. will discuss this with JS | 2 | 1.5 | 0
PS | Tuesday | 2015-02-03 | 8127 | New |  | 2.7 | Hotel | Test ABI, ABS URL changes |  | 1 | 1.5 | 1
PS | Wednesday | 2015-02-04 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-02-04 | [5 empty] | Daily updates + discussions |  | 0.75 | 1 | 1
PS | Wednesday | 2015-02-04 | 7651 | New |  | 2.9 | Hotel | [SQA - SP] Documentation update |  | 1 | 1.5 | 1
PS | Wednesday | 2015-02-04 | 8112 | Tests |  | 2.8 | Hotel | Test CO on devcache | testgrid + test cases + tests | 5 | 4 | 1
PS | Wednesday | 2015-02-04 | 7711 | New |  |  | Hotel | [SE] Documentation SE_RQ and SE_RS |  | 1 | 1 | 1
PS | Thursday | 2015-02-05 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-02-05 | [5 empty] | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Thursday | 2015-02-05 | 8141 | New |  | 2.1 | TUI | Implement RNC schema for SQA |  | 4 | 4 | 0
PS | Thursday | 2015-02-05 | 8147 | New |  |  | TUI | [CB/GB] - Issue with quotations | check + Solve + test |  | 3 | 1
PS | Thursday | 2015-02-05 | 8137 | Tests |  | 2.8 | Hotel | Test CO on devcache |  | 3 | 0 | -1
PS | Friday | 2015-02-06 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Friday | 2015-02-06 | [5 empty] | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Friday | 2015-02-06 | 8141 | New |  | 2.1 | TUI | Implement RNC schema for SQA | Wait for CC's doc update | 4 | 4.5 | 1
PS | Friday | 2015-02-06 | 8147 | Tests |  |  | TUI | [CB/GB] - Issue with quotations | Corrections + tests |  | 1 | 1
PS | Friday | 2015-02-06 | 8047 | New |  | 2.7 | Hotel | Exp hotels issue | Test around 50 hotels on precache/sd-29142 |  | 1.5 | 1
PS | Monday | 2015-02-09 |  | Maintenance |  |  | Hotel | Cots | Mails + discussion regarding Cots | 0.25 | 0.5 | 1
PS | Monday | 2015-02-09 | [5 empty] | Daily updates + discussions | update + tracking sheet | 0.75 | 0.5 | 1
PS | Monday | 2015-02-09 | 8137 | New |  | 2.8 | Hotel | Test CO on devcache |  | 4 | 5 | 1
PS | Monday | 2015-02-09 | 7391 | Tests |  | 2.9 | Hotel | Test CB error response | Co=ordination with JS over modifying SP while taking responses | 1.5 | 2 | 1
PS | Monday | 2015-02-09 | 6223 | Tests |  | 2.8 | Hotel | Test per JS suggestion |  | 1.5 | 0 | -1
PS | Tuesday | 2015-02-10 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-02-10 | 8187 8188 | server_setup | internal |  | Hotel | Issues with updates on new server | JS, ST, UZ : Regarding new server 2.8 and 2.9 DB : #8187 and #8188 + checking | 0.75 | 1 | 1
PS | Tuesday | 2015-02-10 | 6223 | Tests |  | 2.8 | Hotel | Test per JS suggestion |  | 1.5 | 0 | -1
PS | Tuesday | 2015-02-10 | 8170 | New |  |  | TUI | XSLOUT for Search QuotedAvailability transaction (eRetail FlexPricer). | code XSL + discussions with CC for technical difficulties | 6.5 | 7 | 1
PS | Wednesday | 2015-02-11 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-02-11 |  | Discussions | internal |  |  | Daily updates + discussions | Co-ordination with Uma(for launching 2.8 updates) + JS(COT info) | 0.75 | 0.5 | 1
PS | Wednesday | 2015-02-11 | 8187 8188 | server_setup | internal |  | Hotel | Check new server updates | for both 2.8 and 2.9 DBs | 0.5 | 0.75 | 1
PS | Wednesday | 2015-02-11 | 8171 | New |  |  | TUI | XSLIN for Search QuotedAvailability transaction (eRetail FlexPricer). | code XSL + discussions with CC for technical difficulties | 6.5 | 6.5 | 0
PS | Thursday | 2015-02-12 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-02-12 | 8187 8188 | server_setup | internal |  | Hotel | Daily updates + discussions | #8187, #8188 : updates + call with ST | 0.75 | 1.5 | 1
PS | Thursday | 2015-02-12 | 8171 | New |  |  | TUI | XSLIN for Search QuotedAvailability transaction (eRetail FlexPricer). | code XSL + discussions with CC for technical difficulties | 7 | 6.25 | 0
PS | Friday | 2015-01-13 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Friday | 2015-01-13 | [5 empty] | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Friday | 2015-01-13 | 8171 | New |  |  | TUI | XSLIN for Search QuotedAvailability transaction (eRetail FlexPricer). | code XSL + discussions with CC for technical difficulties | 7 | 7 | 0
PS | Monday | 2015-02-16 |  | Maintenance |  |  | Hotel | Cots | Mails + discussion regarding Cots | 0.25 | 0.5 | 1
PS | Monday | 2015-02-16 |  | Planning | internal |  |  | Daily updates + discussions | update + tracking sheet | 0.75 | 1 | 1
PS | Monday | 2015-02-16 | 8170 | New |  |  | TUI | Test XSLOUT with JS |  | 1 | 1 | 1
PS | Monday | 2015-02-16 | 8171 | New |  |  | TUI | XSLIN : remaining changes |  | 1 | 1 | 0
PS | Monday | 2015-02-16 |  | Training |  |  |  | Intro + co-ordinate new test team a/c to week plan |  | 4 | 4.5 | 1
PS | Tuesday | 2015-02-17 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-02-17 |  | Planning | internal |  | Hotel | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Tuesday | 2015-02-17 | 8171 | New |  |  | TUI | SQA Test XSLIN with C# |  | 1 | 1.5 | 1
PS | Tuesday | 2015-02-17 | 8170 | New |  |  | TUI | XSLOUT for Search QA (eRetail FlexPricer) | CC : new changes + Discussion |  | 1.5 | 0
PS | Tuesday | 2015-02-17 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | continue with CC's response | 1.5 | 0 | -1
PS | Tuesday | 2015-02-17 |  | Training |  |  |  | co-ordinate new test team a/c to week plan |  | 4 | 4 | 1
PS | Wednesday | 2015-02-18 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-02-18 |  | Discussions | internal |  |  | Daily updates + discussions |  | 0.75 | 0 | -1
PS | Wednesday | 2015-02-18 |  | Training |  |  |  | co-ordinate new test team a/c to week plan | Co-ordinate + Review work | 3 | 4 | 1
PS | Wednesday | 2015-02-18 | 8170 | New |  |  | TUI | XSLOUT: new changes | Discuss with CC + change + test |  | 2 | 1
PS | Wednesday | 2015-02-18 | 8171 | New |  |  | TUI | SQA XSLIN: new changes + test | Discuss with CC + change + test |  | 2.5 | 1
PS | Wednesday | 2015-02-18 | 8014 | New |  |  |  | SAO: start testing | Testcases, testgrid + data checks | 4 | 0 | -1
PS | Thursday | 2015-02-19 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-02-19 | [5 empty] | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Thursday | 2015-02-19 | 8171 | New |  |  | TUI | co-ordinate new test team a/c to week plan |  | 2.5 | 3 | 1
PS | Thursday | 2015-02-19 | 8171 | New |  |  | TUI | correct issues if any | CC discussion + changes + Test variour types of cases , unit | 2 | 4 | 1
PS | Thursday | 2015-02-18 | 8014 | New |  |  |  | SAO: correct issues if any with CC + tests |  | 2.5 | 0 | -1
PS | Friday | 2015-01-20 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Friday | 2015-01-20 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.75 | 0.75 | 1
PS | Friday | 2015-01-20 | 8171 | Training | internal |  | TUI | co-ordinate new test team a/c to week plan |  | 1 | 2.5 | 1
PS | Friday | 2015-01-20 | 8171 | New |  |  | TUI | SQA | issue correction | 2 | 2 | 1
PS | Friday | 2015-01-20 |  | Tests |  |  | TUI | Prepare some SQA testcases for CC to send Corsoir |  |  | 1.5 | 1
PS | Friday | 2015-01-20 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | continue with CC's response. Need CC input |  | 1 | 0
PS | Monday | 2015-02-23 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Monday | 2015-02-23 |  | Discussions | internal |  | Hotel | Daily updates + discussions | Installation test cases for JS | 0.75 | 0.75 | 1
PS | Monday | 2015-02-23 | 8171 | New |  |  | TUI | SQA implementation | CC asked for changes + RNC corrections | 1.5 | 1.5 | 1
PS | Monday | 2015-02-23 |  | Training | internal |  |  | Train new testers + discussions | Call with both to ask changes to test + replay |  | 2 | 1
PS | Monday | 2015-02-23 | 8276 | 2.8_tests | Dashboard | 2.8 | Hotel | Provide SQL queries to test Dashbaord | Update testgrid with current information |  | 1 | 0
PS | Monday | 2015-02-23 | 7246 | 2.8_tests |  | 2.8 | Hotel | Check EXP updates on 2.8 installations | update + check |  | 0.5 | 1
PS | Tuesday | 2015-02-24 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-02-24 |  | Planning | internal |  |  | Daily updates + discussions | Tracking Sheet + CC's co-ordiation for server update + Pepare week plan | 0.75 | 2 | 1
PS | Tuesday | 2015-02-24 | 8276 | 2.8_tests | Dashboard | 2.8 | Hotel | Provide SQL queries to test Dashbaord | Finish queries | 1 | 1 | 1
PS | Tuesday | 2015-02-24 |  | 2.8_tests | Dashboard | 2.8 | Hotel | Test dashboard with Uma |  | 2 | 0 | -1
PS | Tuesday | 2015-02-24 |  | Training |  |  | Air | Co-ordinate + call for new tasks to team |  | 1 | 1.5 | 1
PS | Tuesday | 2015-02-24 | 8014 | New |  |  | Air | SAO: changes + finish + Test | XSL changes + RNC Corrections + test cases | 2 | 2.25 | 1
PS | Tuesday | 2015-02-24 |  | Training |  |  | Air | SQA review tests | review + feedback to testers | 1 | 1 | 1
PS | Wednesday | 2015-02-25 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-02-25 |  | Planning | internal |  |  | Daily updates + discussions | Training WeekPlan update+ reposition with DF. | 0.75 | 1 | 1
PS | Wednesday | 2015-02-25 | 8137 | 2.8_tests |  | 2.8 | Hotel | VDM Create Option | Test CO for AF |  | 0.5 | 1
PS | Wednesday | 2015-02-25 |  | 2.8_tests | Dashboard | 2.8 | Hotel | Daily dashboard checks with Uma | checked devcache dashboard as JS suggested | 1 | 1.5 | 1
PS | Wednesday | 2015-02-25 |  | Training | snapin |  | Hotel | Co-ordinate a/c to week plan | Call with both to Cots + dashboard + installations |  | 1.25 | 1
PS | Wednesday | 2015-02-25 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | CC discussion+ xsl new changes + tests + problem in Booking creation. To CC for feedback now. | 6 | 3.5 | 1
PS | Thursday | 2015-02-26 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-02-26 |  | Planning | internal |  |  | Daily updates + discussions | Task Creation + Task updates+Tracking sheet + Discussions + Dashboard sheet updates with JS | 0.75 | 2 | 1
PS | Thursday | 2015-02-26 |  | 2.8_tests | Dashboard | 2.8 | Hotel | Co-ordinate with Testing team to sql queries call for dashboard | Call for dashboard + alike tasks + problems | 0.5 | 1.25 | 1
PS | Thursday | 2015-02-26 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | change code + test + 1 SQA test after update | 1 | 1 | 1
PS | Thursday | 2015-02-26 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | RNC Creation | 1 | 1.5 | 1
PS | Thursday | 2015-02-26 | 8282 | New |  |  | TUI | Addition of Code[@Role='Transaction'] in all TUI transactions | Finished | 4.5 | 2 | 1
PS | Friday | 2015-02-27 |  | Maintenance |  |  | Hotel | Cots |  | 0.25 | 0.25 | 1
PS | Friday | 2015-02-27 |  | Planning | internal |  |  | Daily updates + discussions | call with shweta for devache clearification + discuss with CC for SQA | 0.75 | 1.25 | 1
PS | Friday | 2015-02-27 |  | 2.8_tests | Dashboard | 2.8 | Hotel | Daily dashboard checks with Uma |  | 1 | 0 | -1
PS | Friday | 2015-02-27 | 8295 | 2.8_tests |  | 2.8 | Hotel | ABT MP room only | Test ABI MP tests on devccahe for JS | 2 | 2 | 1
PS | Friday | 2015-02-27 | 8014 | New |  |  | TUI | Implement Search AddOn transaction | Co-ordinate with Manali for SAO testing Call + issue solving | 1 | 1.5 | 1
PS | Friday | 2015-02-27 | 8162 | Tests |  |  | Hotel | Check EXP hotels again in next week | discussion with JS |  | 0.25 | 1
PS | Friday | 2015-02-27 | 8301 | New |  |  | TUI | Make soap:Fault template unique |  | 0.75 | 0.75 | 1
PS | Friday | 2015-02-27 | 8302 | New |  |  | TUI | Integrate additionnal Traveler typologies in the booking workflows |  |  | 2 | 0
ST | Monday | 2015-02-02 | 7757 | New |  | 2.9 | Hotel | Test Uma's work on logging |  | 0.5 | 0.5 | 1 |  | Leaves Half days : 2015-02-03, 2019-04-03 Full day leaves : 2015-02-11, 2015-02-16 2015-03-30 - 2015-04-05 Work hours : 6 hours per day
ST | Monday | 2015-02-02 | 7904 |  |  |  | Stock | Tariff id is not FK |  | 0.5 | 0.25 | 1
ST | Monday | 2015-02-02 | 8006 |  |  |  | Stock | study SP changes + work with Taras |  | 2 | 1 | 0
ST | Monday | 2015-02-02 | 7639 | New |  | 2.9 | Hotel | New server + replication setup | vdm complete synchro + start setup of immediate replication | 3 | 0 | -1
ST | Monday | 2015-02-02 | 8006 |  |  |  | Stock | Discussion with Taras for 8006 |  |  | 0.25 | 1
ST | Monday | 2015-02-02 |  |  |  |  | Stock | Discussion with Taras, GK and AR |  |  | 0.75 | 1
ST | Monday | 2015-02-02 |  |  |  |  | Stock | Discussion with Anne for diff tasks and changes |  |  | 0.5 | 1
ST | Monday | 2015-02-02 |  |  |  |  | Hotel | Discussion with JS for diff tasks and planning |  |  | 0.75 | 1
ST | Monday | 2015-02-02 |  |  |  |  | Hotel | Discussion with JS and PS for COTS |  |  | 0.25 | 1
ST | Monday | 2015-02-02 |  |  |  |  | Hotel | Discussion with Anne and JS for hotel prod issues |  |  | 0.75 | 1
ST | Tuesday | 2015-02-03 | 7864 |  |  |  | Stock | Discussion with AR |  | 0.5 | 0 | -1
ST | Tuesday | 2015-02-03 | [5 empty] | Daily updates + discussions |  | 0.5 | 0.25 | 1
ST | Tuesday | 2015-02-03 | 7639 | New |  | 2.9 | Hotel | Replication setup | vdm complete synchro(1 hour corrected the problem on new server + check the execution in between) + study replication(2) + discussion with JS(.5) | 4 | 3.5 | 0
ST | Tuesday | 2015-02-03 |  |  |  |  | Stock | Discussion with Taras and Anne for stock |  | 1 | 0.5 | 1
ST | Tuesday | 2015-02-03 | 8006 |  |  |  | Stock | study SP changes + work with Taras | Analysis of new req and task updated |  | 1 | 1
ST | Tuesday | 2015-02-03 | 8126 |  |  | 2.7 | Hotel | Ignore prices with invalid lot | Discussions + analysis + task updated |  | 1 | 1
ST | Wednesday | 2015-02-04 | [5 empty] | Daily updates + discussions | Discussion with JS for diff task + tracking sheet |  | 0.5 | 1
ST | Wednesday | 2015-02-04 | 7768 | New |  | 2.9 | Hotel | Test at DB level |  | 2 | 0 | -1
ST | Wednesday | 2015-02-04 | 8131 |  |  |  |  | Change child age import for VDM | Analysis, discussion, coding and testing | 5 | 5 | 0
ST | Wednesday | 2015-02-04 | [5 empty] | Call and Discussion with Anne for Hotel |  |  | 0.5 | 1
ST | Wednesday | 2015-02-04 | 7639 | New |  | 2.9 | Hotel | Replication setup | observations + wiki | 2.5 | 0 | -1
ST | Thursday | 2015-02-05 | [5 empty] | Daily updates + discussions |  | 1 | 0.75 | 1
ST | Thursday | 2015-02-05 | 7639 | New |  | 2.9 | Hotel | Replication setup | Study the replication | 3 | 1 | 0
ST | Thursday | 2015-02-05 | 7849 |  |  |  | Stock | index wiki | Wiki created + shared the details |  | 0.75 | 1
ST | Thursday | 2015-02-05 | 7864 |  |  |  | Stock | SQA selecting tariff is not working properly | Discussion, Analysis, coding and testing |  | 1.5 | 1
ST | Thursday | 2015-02-05 | 8131 | New |  | 2.7 | Hotel | Change child age import for VDM | wiki and coordinate with Uma for VDM Room Import wiki ad=nd review of wiki, testing | 2 | 2 | 0
ST | Friday | 2015-02-06 | [5 empty] | Daily updates + discussions |  | 0.5 | 0.25 | 1
ST | Friday | 2015-02-06 | 8154 | Maintenance |  | 2.7 | Hotel | Mail sent wrong info for VDM | Analysis, discussion | 0.5 | 0.5 | 1
ST | Friday | 2015-02-06 | [5 empty] | Discussion with JS for testing VDM issue |  |  | 0.5 | 1
ST | Friday | 2015-02-06 | 8131 | New |  | 2.8 | Hotel | VDM child age change implementation | Checked the old test cases of VDM , corrected it. Added new test cases for new tests. Tested the data for old and new cases | 3 | 4 | 1
ST | Friday | 2015-02-06 | 8155 | New |  | 2.9 | Hotel | Modify deactivate Accomodation | Analysis , review code and discussion |  | 0.5 | 1
ST | Friday | 2015-02-06 | 8139 | New |  | 2.9 | Hotel | Document the wiki for VDM SPs | task created and discussion for queries |  | 0.5 | 1
ST | Friday | 2015-02-06 | 8160 | New |  | 2.9 | Hotel | Create New database for replication | Analysis and task created with details |  | 0.75 | 1
ST | Monday | 2015-02-09 | [5 empty] | Daily updates + discussions + tracking sheet |  | 1 | 0.5 | 1
ST | Monday | 2015-02-09 | 8155 |  |  | 2.9 | Hotel | Modify deactivate Accomodation | Code review and testing | 0.5 | 0.75 | 1
ST | Monday | 2015-02-09 | 7768 |  |  | 2.8 | Hotel | Modify extrapolation procedure - limit end date | Discussion with JS for testing this | 1 | 0.25 | 0
ST | Monday | 2015-02-09 | 8131 | New |  | 2.7 | Hotel | child ages implementation | Wiki modification and discussion with JS and analyse the issue with old test cases | 2 | 1.25 | 1
|  |  | 8160 | New |  | 2.9 | Hotel | Create New database for replication | Discussion with Uma for new database setup |  | 0.25 | 0
ST | Monday | 2015-02-09 | 7639 | New |  | 2.9 | Hotel | Replication setup | Replication setup | 1.5 | 0.5 | 0
ST | Tuesday | 2015-02-10 | 7768 | New | 2.9_tests | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Testing | 2 | 0 | -1
ST | Tuesday | 2015-02-10 | 7639 | New | replication | 2.9 | Hotel | Replication setup | Discussion with JS, wiki created, Analysis of tables, appraoch planning and documented | 3.5 | 5 | 0
ST | Tuesday | 2015-02-10 |  | Planning | internal |  |  | Discussion with Anne | Discussion for planning of hotel and stock and stock tariff function |  | 0.4 | 1
ST | Tuesday | 2015-02-10 | 8187 | server_setup | internal |  | Hotel | update issues - new server for 2.8, 2.9 | Discussion with JS, PS and Uma |  | 0.75 | 0
ST | Tuesday | 2015-02-10 | 6618 | New |  |  | Air | Use fareopt aggregation in dashboard | Changes committed in hg and discussion with Emillise, revert back changes |  | 0.4
ST | Tuesday | 2015-02-10 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.75 | 1
ST | Tuesday | 2015-02-10 | 8183 | New |  | 2.9 | Hotel | Extrapolation limitation on 2.8 | Task created and accordingly modified 7768 |  | 0.2 | 1
ST | Tuesday | 2015-02-10 | 8160 | New |  | 2.9 | Hotel | Create New database for replication | Discussion with Uma and JS for new database setup |  | 0.5 | 1
ST | Wednesday | 2015-02-11 |  | Leave
ST | Thursday | 2015-02-12 | 7639 | New |  | 2.9 | Hotel | Replication setup | Replication setup + wiki | 3 | 0 | -1
ST | Thursday | 2015-02-12 | 8165 | New |  | 2.8 | Hotel | 2.8 release script | update + test | 2.5 | 3.5 | 1
ST | Thursday | 2015-02-12 | 8222 | New |  |  | Stock | Improve sto_journey__list to take less time | Analysis, discussion with taras and task created + discussion with Anne |  | 1.25 | 1
ST | Thursday | 2015-02-12 | 8188 8187 | server_setup | internal |  | Hotel | New server updates - 2.8, 2.9 instances | Discussion with PS, Uma , JS and testing and correction on our server |  | 0.75 | 1
ST | Thursday | 2015-02-12 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and discussion with JS |  | 0.5 | 1
ST | Friday | 2015-02-13 | 7639 | New | replication | 2.9 | Hotel | Replication setup | Analysis and decided the replication types for diff tables | 5.5 | 8 | 0
ST | Friday | 2015-02-13 | [5 empty] | Daily updates + discussions |  | 0.5 | 0 | -1
ST | Sunday | 2015-02-15 | 7639 | New | replication | 2.9 | Hotel | Replication setup | Setup of replication on server and executed |  | 10 | 0
ST | Monday | 2015-02-16 | leave
ST | Tuesday | 2015-02-17 | 7639 | New | replication | 2.9 | Hotel | Replication setup | Testing and if needed modify the replication setup | 3.5 | 1.5 | 0
|  |  |  | Discussions | internal |  |  | Discussion with JS for diff tasks and 8131 |  |  | 0.5 | 1
ST | Tuesday | 2015-02-17 |  | Planning | internal |  |  | Discussion with Anne for db resources training |  | 0.5 | 0.5 | 1
ST | Tuesday | 2015-02-17 |  | Planning | internal |  | Stock | Discussion with Anne for stock task planning |  | 1 | 0 | -1
ST | Tuesday | 2015-02-17 | 8131 | New |  | 2.8 | Hotel | child ages implementation | discussion with anne + execution |  | 1 | 0
ST | Tuesday | 2015-02-17 | 8187 | server_setup |  |  | Hotel | update issues - new server for 2.8, 2.9 | Check and arrange the update so that replication can be tested properly | 1 | 0 | -1
ST | Tuesday | 2015-02-17 | 8222 | New |  |  | Stock | Improve sto_journey__list to take less time | Discussion with Anne, GK, Taras, AR, Analysis and coding |  | 2 | 0
ST | Wednesday | 2015-02-18 | 7639 | New | replication | 2.9 | Hotel | Replication setup | testing + Training Uma for testing replication | 2 | 1.5 | 0
ST | Wednesday | 2015-02-18 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and other checks | 0.5 | 0.5 | 1
ST | Wednesday | 2015-02-18 | 8131 | New |  | 2.8 | Hotel | child ages implementation | discuss with Anne for empty ages + implement + test | 2 | 0.5 | 0
ST | Wednesday | 2015-02-18 | 8093 | Discussions |  |  | Hotel | SQA Test tool | VDM analysis - discussion with JS for extrapolation issue |  | 0.75 | 1
ST | Wednesday | 2015-02-18 | 8244 | Maintenance |  | 2.7 | Hotel | Mail shows 0 room update for JNV | Analysis - to JS with observations |  | 0.4 | 1
ST | Wednesday | 2015-02-18 | 8222 | New |  |  | Stock | Improve sto_journey__list to take less time | Testing, recode, discussion with AR |  | 1.35 | 1
ST | Wednesday | 2015-02-18 | 6903 | New |  | 2.8 | Hotel | For automatic se_versioned_tarif cleanup, create SP | create SP + test through ExecuteTransaction | 1.5 | 1 | 0
ST | Thursday | 2015-02-19 |  | Planning | internal |  |  | Daily updates + discussions | Discussion with JS, AR and tracking sheet | 0.5 | 0.5 | 1
ST | Thursday | 2015-02-19 | 8244 | Maintenance |  | 2.8 | Hotel | Correction of mail for JNV room update | Correct JNV room update figure + test + consider configurable email ids | 1.5 | 0 | -1
ST | Thursday | 2015-02-19 | 6903 | New |  | 2.8 | Hotel | For automatic se_versioned_tarif cleanup, create SP | Testing, recode and final testing |  | 1 | 1
ST | Thursday | 2015-02-19 | 8156 |  |  | 2.8 | Hotel | Improve sp_updateHotelSortPrices for 2.8 | Test Uma's work |  | 0.75 | 1
ST | Thursday | 2015-02-19 | 8165 | Release |  | 2.8 | Hotel | Finalize release script for 2.8 |  | 4 | 3.75 | 1
ST | Friday | 2015-02-20 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet | 0.5 | 0.25 | 1
ST | Friday | 2015-02-20 |  | Analysis | internal |  | Stock | Analyse Anne's question mentioned in email | analyse + answer | 1 | 0 | -1
ST | Friday | 2015-02-20 |  | Discussions | internal |  | Stock | Discussion with Anne for stock DB training |  | 1 | 0 | -1
ST | Friday | 2015-02-20 | 6903 | New |  | 2.8 | Hotel | Automatic cleanup of se_versioned_tarif | task updated with details + discuss with JS |  | 0.25 | 1
ST | Friday | 2015-02-20 | 8165 | Release |  | 2.8 | Hotel | Release script for 2.8 | Updated script |  | 0.25 | 1
ST | Friday | 2015-02-20 | 8156 | 2.8_tests |  | 2.8 | Hotel | Improve sp_updateHotelSortPrices for 2.8 | task updated |  | 0.25 | 1
ST | Friday | 2015-02-20 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis and Coding and testing | 4 | 0 | -1
ST | Friday | 2015-02-20 | 8131 | 2.8_tests |  | 2.8 | Hotel | child ages implementation | Testing for unavailable cases, discussion and checks for diff cases |  | 5 | 0
ST | Monday | 2015-02-23 | 6903 | New |  | 2.8 | Hotel | Automatic cleanup of se_versioned_tarif | Coding and testing |  | 1.5 | 1
ST | Monday | 2015-02-23 |  | Training | internal |  | Air | Discussion with Uma forpostgresql and AIR |  |  | 0.5 | 1
ST | Monday | 2015-02-23 |  | Planning | internal |  |  | Discussion with Anne for db resources training |  |  | 1 | 1
ST | Monday | 2015-02-23 | 8165 | Release |  | 2.8 | Hotel | Release script for 2.8 | Updated script and discussion with JS |  | 3 | 1
ST | Tuesday | 2015-02-24 | 8131 | 2.8_tests | Patch | 2.8 | Hotel | child age implementation | Discuss with JS. Nothing to do | 4.5 | 0.25 | 1
ST | Tuesday | 2015-02-24 |  | Training | internal |  | Stock | Training to Uma and Dhanesh for project overview | Traing to Uma and Dhanesh for project overview. Discussion with Dhanesh for setup. Discussion with AR and Taras for training to Uma and Dhanesh. |  | 2 | 1
ST | Tuesday | 2015-02-24 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis, Discussion with AR about input and output and wiki |  | 2.25 | 0
ST | Tuesday | 2015-02-24 | 6618 | Maintenance |  |  | Air | Use fareopt aggregation in dashboard | Coding and Testing and discussion with emillise |  | 1 | 1
ST | Tuesday | 2015-02-24 |  | Planning | internal |  |  | Discussion with Anne for db resources training | done on Monday | 1 | 0 | -1
ST | Tuesday | 2015-02-24 |  | Planning | internal |  |  | Daily updates + discussions | tracking sheet | 0.5 | 0.5 | 1
ST | Wednesday | 2015-02-25 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Analysis + code + discussion with AR | 3 | 3.5 | 0
ST | Wednesday | 2015-02-25 |  | Planning | internal |  |  | Call with AF + JS for JS leave planning + price v3 |  | 1 | 0 | -1
ST | Wednesday | 2015-02-25 | 8287 | Training | internal |  |  | DB resource training | KT Sessions and discussion | 1 | 1 | 0
ST | Wednesday | 2015-02-25 |  | Training | internal |  |  | Craete wiki and task for training to DB resources | Wiki created | 1 | 0.5 | 0
ST | Wednesday | 2015-02-25 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and discussion with JS | 0.5 | 1 | 1
ST | Thursday | 2015-02-26 | 8287 | Training | internal |  | Stock | KT on stock DB |  | 2 | 1.5 | 0
ST | Thursday | 2015-02-26 | 8254 | New |  |  | Stock | SP "sto_journey__search" is slow | Coding and Testing | 2.5 | 2.5 | 1
ST | Thursday | 2015-02-26 |  | Planning | internal |  | Hotel | Call with AF + JS for JS leave planning + price v3 |  | 1 | 1 | 1
ST | Thursday | 2015-02-26 |  | Planning | internal |  |  | Daily updates + discussions | tracking sheet + discussion with JS | 0.5 | 0.5 | 1
ST | Thursday | 2015-02-26 |  | Planning | internal |  |  | Discussion with Anne for DB KT planning |  | 0.5 | 0.5 | 1
ST | Friday | 2015-02-27 | 8249 | New |  |  | Stock | LogManagerFS : convert code from sql to pgsql | Answer Uma's concern | 1
ST | Friday | 2015-02-27 |  | Planning | internal |  |  | daily updates + discussions | discussion wiith JS, discussion with PS for COT mail query, tracking sheet | 1
ST | Friday | 2015-02-27 | 8287 | Training | internal |  |  | DB resource training |  | 4
UZ | Monday | 2015-02-02 | [5 empty] | Daily updates + discussions |  | 1 | 0.75 | 1 |  | Leaves 2015-02-16 to 2015-02-17 Work hours : 6 hour per day starting Feb
UZ | Monday | 2015-02-02 | 8117 | New |  | 3 | Hotel | se_markup__import | code + test + wiki | 4 | 3.75 | 0
UZ | Monday | 2015-02-02 | 8036 | New |  | 2.9 | Hotel | corrections per JS suggestion |  | 1 | 0.75 | 1
UZ | Monday | 2015-02-02 | 8110 | New |  | 2.9 | Hotel | corrections per JS suggestion |  |  | 0.75 | 1
UZ | Tuesday | 2015-02-03 | 8117 | New |  | 3 | Hotel | se_markup__import |  | 1.5 | 1.5 | 1
UZ | Tuesday | 2015-02-03 | [5 empty] | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-02-03 | 8124 |  |  | 2.8 | Hotel | Sp for availability test tool | code + test + wiki | 2 | 2 | 1
UZ | Tuesday | 2015-02-03 | 8125 |  |  | 2.8 | Hotel | Sp for availability test tool | code + test + wiki | 2 | 2 | 1
UZ | Wednesday | 2015-02-04 | 8139 |  |  |  | Hotel | Documentation |  | 4.5 | 4.5 | 0
UZ | Wednesday | 2015-02-04 | [5 empty] | Daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Wednesday | 2015-02-04 | 8125 |  |  |  |  | Sp for availability test tool | modify + test | 1 | 1 | 1
UZ | Thursday | 2015-02-05 | 8139 |  |  |  | Hotel | Documentation |  | 3 | 2.5 | 0
UZ | Thursday | 2015-02-05 | 7598 |  |  | 2.9 | Hotel | time measurment |  |  | 1 | 0 | need to discuss with JS
UZ | Thursday | 2015-02-05 | [5 empty] | Daily updates + discussions |  | 0.5 | 1.25 | 1
UZ | Thursday | 2015-02-05 | 8124, 8125 |  |  | 2.8 | Hotel | Test Tool SP update | Modify wiki | 0.25 | 0.25 | 1
UZ | Friday | 2015-02-06 | 8155 |  |  | 2.9 | Hotel | Modify SPs |  | 1 | 1 | 1
UZ | Friday | 2015-02-06 | 8156 |  |  | 2.8 | Hotel | Create function +sp, Modify SP | code +test+wiki | 3 | 3 | 0
UZ | Friday | 2015-02-06 | 8160 |  |  | 2.8 | Hotel | Create database |  | 1 | 1 | 0
UZ | Friday | 2015-02-06 | [5 empty] | Daily updates + discussions |  | 1 | 1 | 1
UZ | Monday | 2015-02-09 | 8156 |  |  | 2.8 | Hotel | Improve sort SP to take default markup | test + finish | 3 | 0.5 | 0
UZ | Monday | 2015-02-09 | [5 empty] | Daily updates + discussions |  | 1 | 1 | 1
UZ | Monday | 2015-02-09 | 8124 |  |  | 2.8 | Hotel | Test Tool SP update | Update wiki | 0.25 | 0.25 | 1
UZ | Monday | 2015-02-09 | 7757 |  |  | 2.9 | Hotel | log the steps of post processing | release script + hg update | 0.5 | 0.5 | 1
UZ | Monday | 2015-02-09 | 8155 |  |  | 2.9 | Hotel | deactivation sp update | study + release script + hg update | 0.5 | 0.5 | 1
UZ | Monday | 2015-02-09 | 8160 |  |  | 2.9 | Hotel | Create New database for replication | assist ST for replication | 1 | 3.25 | 1
UZ | Tuesday | 2015-02-10 | 8160 |  |  | 2.9 | Hotel | Create New database for replication | assist ST for replication + discussion | 2 | 3 | 1
UZ | Tuesday | 2015-02-10 | 8156 |  |  | 2.8 | Hotel | Improve sort SP to take default markup | test + finish | 2 | 1 | 1
UZ | Tuesday | 2015-02-10 | 8081 | debriefing | internal |  | Air | Task table in postgres for stock | Discussion with JS, AF + reading + installation |  | 2 | 1
UZ | Tuesday | 2015-02-10 | discussions | internal |  |  |  | Daily updats + discussions |  | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-02-10 | 8166 |  |  | 3 | Hotel | Time measurement - markup fetch |  | 1.5 | 0 | -1
UZ | Wednesday | 2015-02-11 | 8183 |  |  | 2.9 | Hotel | Extrapolation limitation | hg update + DB application | 2 | 1 | 0
UZ | Wednesday | 2015-02-11 | 7391 | 2.9_tests |  | 2.9 | Hotel | CB reference in case of error | Perform VDM synchro on 2.9 DB |  | 0.5 | 1
UZ | Wednesday | 2015-02-11 | discussions | internal |  |  |  | Daily updats + discussions |  | 0.5 | 0.5 | 1
UZ | Wednesday | 2015-02-11 | 8180 |  |  |  | Air | Support PGSQL version |  | 3.5 | 4 | 0
UZ | Thursday | 2015-02-12 | 8180 | New |  |  | Air | Support PGSQL version | tests + technical difficulties + solution + wiki | 5.5 | 5 | 1
UZ | Thursday | 2015-02-12 | 8165 | New |  | 2.8 | Hotel | Update 2.8 release script | as advised by ST |  | 0.5 | 0
UZ | Thursday | 2015-02-12 | [5 empty] | daily updates + discussions |  | 0.5 | 0.5 | 1
UZ | Friday | 2015-02-13 | 8180 |  |  |  | Air | Support PGSQL version | corrections + tests + wiki | 5.5 | 3 | 1
UZ | Friday | 2015-02-13 | [5 empty] | daily updates + discussions | update + discussion for leave | 0.5 | 0.5 | 1
UZ | Friday | 2015-02-13 | 8166 |  | internal | 2.9 | Hotel | time measurement for sort improvement |  |  | 2.5 | 1
UZ | Monday | 2015-02-16 | [5 empty] | leave
UZ | Tuesday | 2015-02-17 | [5 empty] | leave
UZ | Wednesday | 2015-02-18 | 8124 8125 | Documentation |  | 2.8 | Hotel | Update documentation per JS changes |  | 1 | 0.5 | 1
UZ | Wednesday | 2015-02-18 | 7639 | Training |  | 2.9 | Hotel | Discussion with Shweta for training on how to test replication |  | 1 | 1.25 | 1
UZ | Wednesday | 2015-02-18 | 8180 | pgsql |  |  | Air | Task table in postgres for stock | Improvements as asked by Anne | 2 | 1.5 | 0
UZ | Wednesday | 2015-02-18 | 8250 | pgsql |  |  | Air | LogManagerFS : convert code from sql to pgsql | code | 1.5 | 2.5 | 0
UZ | Thursday | 2015-02-19 | 8250 | pgsql |  |  | Air | LogManagerFS : convert code from sql to pgsql |  | 4.5 | 2 | 0
UZ | Thursday | 2015-02-19 | 7639 |  |  |  | Hotel | test replication on our server | server not available | 1 | 0 | -1
UZ | Thursday | 2015-02-19 | 8180 | pgsql |  |  | Air | Task table in postgres for stock | finish the task - script comments |  | 0.25 | 1
UZ | Thursday | 2015-02-19 | 8249 | pgsql |  |  | Air | Core module migration | check tables of all code modules |  | 3.5 | 1
UZ | Thursday | 2015-02-19 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.25 | 1
UZ | Friday | 2015-02-20 | 8250 | pgsql |  |  | Air | LogManagerFS : convert code from sql to pgsql | Created 2 SPs + tried to create 3 more SPs, but facing problem in that. | 5.5 | 6 | 1
UZ | Monday | 2015-02-23 | 8250 | pgsql |  |  | Air | LogManagerFS : convert code from sql to pgsql | Modify sps + call with ST for queries | 4 | 1.5 | 0
UZ | Monday | 2015-02-23 | 8278 |  |  |  | Hotel | Wiki: Hotel Database Knowledge |  | 2 | 1.5 | 0
UZ | Tuesday | 2015-02-24 |  | 2.8_test |  | 2.8 | Hotel | Dashboard tests | assist in data checks | 1 | 0 | -1
UZ | Tuesday | 2015-02-24 | 8249 | pgsql |  |  | Air | Core module migration | Created 4 SPs, facing problem in 2 SPs | 2.5 | 2.5 | 0
UZ | Tuesday | 2015-02-24 |  | Discussions | internal |  |  | Coordination with Dhanesh for setup |  |  | 0.5 | 1
UZ | Tuesday | 2015-02-24 |  | Training |  |  | Stock | KT on stock DB | read wikis provided by ST + Call with ST, AR, TC |  | 3 | 1
UZ | Wednesday | 2015-02-25 |  | 2.8_test |  | 2.8 | Hotel | Dashboard tests | assist in data checks | 1 | 0 | -1
UZ | Wednesday | 2015-02-25 | 8287 | pgsql |  |  | Stock | KT on stock DB | Create task + call with ST + study + coordination with DM | 5 | 5.5 | 1
UZ | Wednesday | 2015-02-25 |  | Training | internal |  |  | Help Dhanesh for server connectivity |  |  | 0.25 | 1
UZ | Wednesday | 2015-02-25 | 8249 8250 | pgsql |  |  | Stock | Core module migration | Update task + assign to ST |  | 0.25 | 1
UZ | Thursday | 2015-02-26 |  | 2.8_test |  | 2.8 | Hotel | Dashboard tests | assist in data checks | 1 | 0 | -1
UZ | Thursday | 2015-02-26 | 8287 | pgsql |  |  | Stock | KT on stock DB | study + call with ST for queries + call with DM for his queries | 5 | 6 | 1
UZ | Friday | 2015-02-27 |  | 2.8_test |  | 2.8 | Hotel | Dashboard tests | assist in data checks | 1 | 0 | -1
UZ | Friday | 2015-02-27 | 8287 | pgsql |  |  | Stock | KT on stock DB | Call with ST for queries + study |  | 4.75 | 1
UZ | Friday | 2015-02-27 | 8249 | pgsql |  |  | Stock | Core module migration | Call with ST + tried to create SP |  | 0.75 | 1
UZ | Friday | 2015-02-27 | 7757 |  |  | 2.9 | Hotel | log the steps of post processing | Modified SPs + Applied on 2.9 DB |  | 0.5 | 1