## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0 | -1 | Leaves 2015-05-01 2015-05-25 I will need some leaves in APR/MAY on short notice
JS | Wednesday | 2015-04-01 | 8093 | 2.8_tests |  | 2.8 | Hotel | SQA tests between precache and prod | test + analysis | 3 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | 2.8 | Hotel | Make a list of quality control actions then tools to automate (JS+AF) | First discussion with Anne | 1 | 0 | -1
JS | Wednesday | 2015-04-01 |  | New | Documentation | 2.8 | Hotel | Describe usage +behavior of test tool EXP for DH |  | 1.5 | 0 | -1
JS | Wednesday | 2015-04-01 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 2 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | Afidium |  | Daily call |  | 0.25 | 0 | -1
JS | Wednesday | 2015-04-01 | 8586 | 2.8_tests |  | 2.8 | Hotel | Patch preparation + application | FTP patch update + test cleanup patch + apply . Wrote to CC on progress. + data check |  | 3.5 | 0
JS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates | tracking sheet + weekly meetings table | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-02 | 8586 | 2.8_tests |  | 2.8 | Hotel | Checked precache GTA data | checkded data + relaunched GTA GT + queued L + checked results afterwards |  | 2 | 1
JS | Thursday | 2015-04-02 | 8577 | New |  | 2.7 | Hotel | Cuba extrapolation | Patch for 2.7 : prepare + test |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8554 | Maintenance |  |  | Hotel | Check why RMT update fails on prod after new URL update | reproduce problem + fix + test. + change to remove DTD |  | 2.5 | 0
JS | Thursday | 2015-04-02 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | tests + analysis | 2 | 0 | -1
JS | Thursday | 2015-04-02 | 8309 | New |  | 2.9 | Hotel | Dynamic search EXP | studied RQ document for EXP |  | 1 | 0
JS | Thursday | 2015-04-02 | 8283 | Discussion | internal |  | TUI | Assist PS for updating SD-29142 instance + guide for fix | update + guide |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8093 | 2.8_tests |  | 2.8 | Hotel | Launch SQA test tool |  | 0.25 | 0 | -1
JS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Friday | 2015-04-03 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Changed code for DTD removal + tested on SD. To PS for further tests. Discuss with PS |  | 1.5 | 0
JS | Friday | 2015-04-03 | 8309 | New | Analysis |  | Hotel | Dynamic search EXP | Manual requests + analysis + discussion with DF | 4 | 3.5 | 0
JS | Friday | 2015-04-03 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | XSL change + started DB change |  | 1.25 | 0
JS | Friday | 2015-04-03 |  |  |  |  | Hotel | Merged 2.8 changes to 2.9 |  |  | 1 | 1
JS | Friday | 2015-04-03 |  | Planning | internal | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions |  | 3.5 | 0 | -1
JS | Friday | 2015-04-03 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.5 | 1
JS | Monday | 2015-04-06 |  | Planning | internal |  |  | Weekly planning | tracking sheet + objective status update | 1 | 1 | 0
JS | Monday | 2015-04-06 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | changes SQA + SPR SPs. Yet to implement Match + XSL change. Asked PS for test cases | 2 | 2 | 0
JS | Monday | 2015-04-06 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | updated devcache + GTs + L + mentioned how to check | 1 | 1 | 0
JS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Check update files + finalize patch |  | 1.5 | 1
JS | Tuesday | 2015-04-07 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | finish code + Tests | 2 | 4.5 | 1
JS | Tuesday | 2015-04-07 |  | Discussion | internal |  | Hotel | Answer CC questions regarding EXP | EXP update for hotel + checked corrections for booking ref in 2.8 |  | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8309 | New |  |  | Hotel | Dynamic search EXP | Started test tool dev | 3 | 0.5 | 0
JS | Tuesday | 2015-04-07 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Tuesday | 2015-04-07 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Discuss with CC + start implementation | 2.5 | 0 | -1
JS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8654 | 2.8_tests |  | 2.8 | Hotel | EXP CB problem on precache | check + fix + test + patch |  | 3 | 1
JS | Wednesday | 2015-04-08 |  | Planning | internal | Afidium | Hotel | Hotel weekly planning | with DF, CC |  | 0.5 | 1
JS | Wednesday | 2015-04-08 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8309 | New |  |  | Hotel | Dynamic search EXP | Tool coding |  | 2.5 | 0
JS | Wednesday | 2015-04-08 |  | Discussion | snapin |  | Hotel | Call with Raj + Shubhad for brief on hotel and what to do for 8660 |  |  | 1 | 1
JS | Wednesday | 2015-04-08 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Implementation + tests | 7.5 | 0 | -1
JS | Wednesday | 2015-04-08 | 8566 | Discussion | internal | 2.8 | Hotel | Dashboard issue | Discussion with everybody + conclude as corner case. To DF for approval of planning for 2.9 |  | 0.5 | 1
JS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-09 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-09 | 8309 | New |  |  | Hotel | Dynamic search EXP | code + test + initial measurements | 7.5 | 3.5 | 0
JS | Thursday | 2015-04-09 |  | Analysis | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Analyse + document + call with DF |  | 3.5 | 1
JS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0.25 | 1
JS | Friday | 2015-04-10 | 8566 | 2.8_tests | Dashboard |  | Hotel | Dashboard problem | update devcache instance + instructions for test for EM + test later |  | 1.25 | 1
JS | Friday | 2015-04-10 |  | New | Documentation | 2.9 | Hotel | Document galaxyref use cases | http://projets2.afidium.com/projects/wnj-htldb/wiki/Galaxyref_synchronization_use_cases |  | 2 | 0
JS | Friday | 2015-04-10 | 7688 | New |  | 2.9 | Hotel | Farebasis | Brief from CC |  | 0.25 | 1
JS | Friday | 2015-04-10 |  | New | Documentation | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions | review + list evolutions and patches |  | 2 | 1
JS | Friday | 2015-04-10 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Friday | 2015-04-10 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | finalize wiki + discuss with DF + Call with Raj to answer questions, native test utility etc. |  | 2 | 1
JS | Friday | 2015-04-10 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5 | 0 | -1
JS | Friday | 2015-04-10 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Monday | 2015-04-13 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | Analysed time measurement. Decision to remove sort + table very likely. Need measurements before finalizing the proposal. To ST for measurements |  | 0.5 | 1
JS | Monday | 2015-04-13 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Review Raj understanding + answer |  | 0.5 | 1
JS | Monday | 2015-04-13 | 7688 | New | farebasis | 2.8.1 | Hotel | Farebasis | Analysis. Need CC advise for proceeding further |  | 1.5 | 0
JS | Monday | 2015-04-13 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launched tool + scheduled tasks + approach |  | 0.5 | 0
JS | Monday | 2015-04-13 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Added code for common use for CSV generation |  | 2.5 | 0
JS | Monday | 2015-04-13 | 8690 | Maintenance |  | 2.7 | Hotel | JNV Availability update problem | Analysis + decision to wait |  | 0.5 | 1
JS | Monday | 2015-04-13 |  | Planning | internal |  | Hotel | Weekly planning | Weekly planning call with DF, CC |  | 1 | 1
JS | Monday | 2015-04-13 |  | Discussion | internal |  | Hotel | Discussion for dashboard install | With EP, DF. Same server + EP installs + JS configures + with Shubhad + Raj |  | 0.5 | 1
JS | Monday | 2015-04-13 | 8566 | 2.8_tests |  | 2.8 | Hotel | Dashboard issue | graft to stable + update dashboard on preprod + to test team |  | 0.5 | 1
JS | Tuesday | 2015-04-14 |  | New | email |  | Hotel | GTA room id query of CC | Checked XSLs + replied |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8566 | 2.8_tests |  | 2.8 | Hotel | Dashboard issue | discuss with RN + check the issue she talked about. I do not see any problem |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8689 | Discussion | internal | 2.9 | Hotel | Load test replication DBs | Document what it means to check SQA in backend + GTA GT + get JNV city data + discuss with ST UZ |  | 1 | 1
JS | Tuesday | 2015-04-14 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Review Raj understanding + correct + discussions | 1 | 1 | 0
JS | Tuesday | 2015-04-14 |  | Planning | internal |  | Hotel | Tracking sheet for week |  |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8047 | Analysis |  |  | Hotel | EXP hotels with missing information | Check response : status code |  | 0.5 | 1
JS | Tuesday | 2015-04-14 |  | Discussion | internal | 2.9 | Hotel | Call with Emilise for transaction code | Understand uAPI implementation from EP | 0.5 | 0 | -1
JS | Tuesday | 2015-04-14 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | finish code + Tests | 4 | 4 | 0
JS | Tuesday | 2015-04-14 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | Start implementation | 1 | 0 | -1
JS | Tuesday | 2015-04-14 |  | Analysis | HtlProduct |  | Hotel | TravelCo | read about travelco | 1 | 0 | -1
JS | Tuesday | 2015-04-14 |  | Planning | internal | Afidium |  | Daily update call |  |  | 0.5 | 1
JS | Wednesday | 2015-04-15 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | code | 4 | 0 | -1 | half day
JS | Wednesday | 2015-04-15 |  | New | email |  | Hotel | EXP empty rate detail problem | Analyse attachments + Provide example to CC |  | 1 | 1
JS | Wednesday | 2015-04-15 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | rate detail code change + measurements |  | 3 | 0
JS | Thursday | 2015-04-16 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | code + test + finish | 4 | 0 | -1 | LEAVE
JS | Thursday | 2015-04-16 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launched SQA tool + checked some response + update tasks | 2 | 0.5 | 1
JS | Thursday | 2015-04-16 |  | Analysis | HtlProduct |  | Hotel | TravelCo | analysis + queries + first contact | 2 | 0 | -1
JS | Thursday | 2015-04-16 |  | Release |  | 2.8 | Hotel | Update prod FTP files + SVN dir | mail to CC about it |  | 0.5 | 1
JS | Thursday | 2015-04-16 | [5 empty] | Task creation for se_availability__update + check other tasks |  |  | 0.25 | 1
JS | Friday | 2015-04-17 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Call with Raj + discussions | 1 | 0.5 | 0
JS | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Friday | 2015-04-17 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | Measured time for XSL + margine engine + document margine engine proposal |  | 3 | 1
JS | Friday | 2015-04-17 |  | Analysis |  |  | Hotel | Transaction context code analysis | Call with EP for uAPI | 3 | 0.25 | 0
JS | Friday | 2015-04-17 |  | Planning | internal |  | Hotel | Next week objectives discussion + feedback on EXP dynamic search | Call with DF |  | 0.5 | 1
JS | Friday | 2015-04-17 |  | Analysis | HtlProduct |  | Hotel | TravelCo | First contact travelco, go west, cali-fun + checked teamamerica documentation | 2 | 1 | 0
JS | Friday | 2015-04-17 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | Checked DB does not need change + started checking XSL |  | 1 | 0
JS | Friday | 2015-04-17 |  | Planning | internal | Afidium |  | Daily call |  |  | 0.5 | 1
JS | Friday | 2015-04-17 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Load test batches + analysis | 2 | 0 | -1
JS | Friday | 2015-04-17 | 7639 | New | Replication | 2.9 | Hotel | Replication | Checked ST response + replied |  | 0.25 | 1
JS | Friday | 2015-04-17 | 8244 | Maintenance |  | 2.7 | Hotel | JNV reports 0 count in mail | Checked + described |  | 0.5 | 1
JS | Monday | 2015-04-20 |  | Planning | internal |  |  | Tracking sheet for week |  | 1 | 1 | 1
JS | Monday | 2015-04-20 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | update specs to extract data in XSL + review Raj;s code + discussions | 2 | 1 | 0
JS | Monday | 2015-04-20 |  | New | DynamicSearch | 2.9 | Hotel | Bonotel dynamic search | Analysis + specification | 4 | 4 | 1
JS | Monday | 2015-04-20 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launch SQA test tool + monitor | 0.5 | 0.5 | 1
JS | Monday | 2015-04-20 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | start coding : SQA RS | 0.5 | 0.5 | 0
JS | Monday | 2015-04-20 |  | Discussion | internal | Afidium |  | Daily call |  |  | 0.25 | 1
JS | Monday | 2015-04-20 | 8749 | Maintenance |  | 2.8 | Hotel | Bonotel room update problem | Launched BNO update and checked room update. Need to check this further as problem not reproduced + discussion with PS to get data about past updates |  | 0.75 | 0
JS | Tuesday | 2015-04-21 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Tuesday | 2015-04-21 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj + code review | 1 | 0.5 | 0
JS | Tuesday | 2015-04-21 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Listed questions that we need answers for to finalize replication |  | 0.5 | 0
JS | Tuesday | 2015-04-21 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | code + test : SQA, GQA . Code CB + test in oxygen | 6.75 | 3.5 | 0
JS | Tuesday | 2015-04-21 | 8637 | New |  | 2.8.1 | Hotel | Create 2.9 DB without galaxyref | Created 2.8.1 DB for use for tasks |  | 2 | 1
JS | Tuesday | 2015-04-21 |  | Discussion | internal | Afidium |  | Daily update call |  |  | 0.25 | 1
JS | Tuesday | 2015-04-21 | 8166 | New |  | 2.9 | Hotel | Time Measurrement | Analysed timings + conclusion + proposal. For Anne to approve |  | 0.5 | 1
JS | Wednesday | 2015-04-22 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-22 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj + code review | 0.75 | 0.5 | 0
JS | Wednesday | 2015-04-22 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | documentation of implementation | 1.5 | 5.5 | 1
JS | Wednesday | 2015-04-22 |  | Discussion | internal |  | Hotel | Discussion with Shweta for VDM synchro + guidance + feedback on Uma tasks + discussion with PS + Shubhad for testers |  |  | 1 | 1
JS | Wednesday | 2015-04-22 |  | Planning | internal | Afidium |  | Daily call |  |  | 0.25 | 1
JS | Wednesday | 2015-04-22 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launch SQA test tool + monitor | 0.5 | 0.5 | 1
JS | Wednesday | 2015-04-22 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Add code to measure extraction with XSL. Test possible scenarios. Time comparison with DB SQAs | 5 | 0 | -1
JS | Thursday | 2015-04-23 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Finish time measurements + document | 3 | 0 | -1 | half day
JS | Thursday | 2015-04-23 | 8309 | New | DynamicSearch | 2.9 | Hotel | Dynamic search | Analysis + proposal for dynamic SQA flow + merging |  | 1 | 1
JS | Thursday | 2015-04-23 |  | Analysis | HtlProduct |  | Hotel | Team america analysis | Started analysis. Need credentials. Sent email | 1 | 0.5 | 0
JS | Thursday | 2015-04-23 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | checked request + CSV + follow up |  | 0.25 | 1
JS | Thursday | 2015-04-23 | 8747 | New | DynamicSearch | 2.9 | Hotel | BNO dynamic search | Reviewed Raj understanding wiki + correct |  | 0.5 | 1
JS | Thursday | 2015-04-23 |  | New | HtlProduct |  | Hotel | Go West Tours | Analyse response + download docs + for decision of IP sent email to Anne |  | 0.5 | 1
JS | Thursday | 2015-04-23 |  | Maintenance | Analysis | 2.8 | Hotel | Prod GTA updates show 0 | Checked server + analysed + sent mail + task for EP for dashboard V2 installation |  | 0.5 | 1
JS | Thursday | 2015-04-23 | 7688 | New | farebasis | 2.8.1 | Hotel | Farebasis | Finished documentation |  | 0.5 | 1
JS | Friday | 2015-04-24 |  | Analysis | HtlProduct |  | Hotel | Team america analysis | checked documentation + mail sent | 4 | 0.5 | 0
JS | Friday | 2015-04-24 |  | Analysis |  | 2.9 | Hotel | Transaction context code analysis | analysis + documentation | 3 | 0 | -1
JS | Friday | 2015-04-24 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj + code review | 1 | 0.25 | 1
JS | Friday | 2015-04-24 |  | Planning | internal |  |  | Daily updates | tracking sheet + call |  | 0.5 | 1
JS | Friday | 2015-04-24 | 8787 | Analysis | HtlProduct |  | Hotel | Go West Tours | Initial analysis |  | 3.5 | 1
JS | Friday | 2015-04-24 |  | Communication | HtlProduct |  | Hotel | Follow up mails to TravalCo, Cali-fun |  |  | 0.25 | 1
JS | Friday | 2015-04-24 | 8309 | Analysis | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | Wrote XSL + started tests |  | 3 | 0
JS | Monday | 2015-04-27 | 8309 | Analysis | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | Finish measurements | 2 | 1.5 | 1
JS | Monday | 2015-04-27 |  | Planning | internal |  |  | Weekly planning | Planning for week | 1.5 | 1 | 0
JS | Monday | 2015-04-27 | 8787 | Analysis | HtlProduct |  | Hotel | Go West Tours | DF feedback on initial analysis. Check + update wiki | 1 | 1 | 1
JS | Monday | 2015-04-27 |  | Planning | internal | Afidium | Hotel | Planning call for hotel | With DF, AF | 0.5 | 0 | -1
JS | Monday | 2015-04-27 | 8798 | New |  | 2.8.1 | Hotel | Expedia status code implementation | code + test + document | 3 | 1 | 0
JS | Tuesday | 2015-04-28 | 8808 | Analysis |  | 2.9 | Hotel | Trasnaction context code | analysis + documentation | 4 | 1.5 | 1
JS | Tuesday | 2015-04-28 |  | Planning | internal |  | Hotel | Daily updates + discussions | tracking sheet update | 0.5 | 0.25 | 1
JS | Tuesday | 2015-04-28 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | SQA load tests on replication DB | Review tests + finalize | 3.5 | 0.5 | 0
JS | Tuesday | 2015-04-28 | 8789 | Release | Dashboard | 2.8 | Hotel | Hotel Dashboard installation for Prod | Configuration + check + task update |  | 0.5 | 1
JS | Tuesday | 2015-04-28 | 8798 | New |  | 2.8.1 | Hotel | Expedia status code implementation | code + started tests |  | 1.5 | 0
JS | Tuesday | 2015-04-28 |  | Review | internal | 2.9 | Hotel | Review of dynamic search with DF + hotel planning |  |  | 1 | 1
JS | Tuesday | 2015-04-28 |  | Planning | internal |  | Hotel | Daily update call |  |  | 0.25 | 1
JS | Tuesday | 2015-04-28 | 8789 | Release | Dashboard | 2.8 | Hotel | Hotel Dashboard installation for Prod | checked dashboard post EP correction + checked prod data + asked DF to ask VDM if they have installed scheduled tasks correctly |  | 0.5 | 1
JS | Tuesday | 2015-04-28 | 8811 | Maintenance | email | 2.8 | Hotel | Service startup issue for search instance of prod | answer + code change + tests + patch |  | 2.5 | 1
JS | Wednesday | 2015-04-29 | 8719 | 2.9_tests |  | 2.9 | Hotel | se_availability__update change | Review + test + finalize | 1 | 0 | -1
JS | Wednesday | 2015-04-29 | 8427 | 2.9_tests |  | 2.9 | Hotel | Automation of Hotel and VDM synchro tests | Review + test + finalize | 2 | 0 | -1
JS | Wednesday | 2015-04-29 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | code review + suggested changes | 2 | 0.5 | 1
JS | Wednesday | 2015-04-29 | 8747 | New | DynamicSearch | 2.9 | Hotel | BNO dynamic search | code review + tests | 2 | 0 | -1
JS | Wednesday | 2015-04-29 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.25 | 1
JS | Wednesday | 2015-04-29 |  | Analysis | DynamicSearch | 2.9 | Hotel | ATI dynamic search | Analysis + specification for test tool + updated native test utility for ATI prod |  | 3.5 | 1
JS | Wednesday | 2015-04-29 | 8309 | Discussion | internal | 2.9 | Hotel | Discussion with Shweta for cases used for SQA comparison during EXP time measurements |  |  | 0.25 | 1
JS | Thursday | 2015-04-30 |  | Planning | internal |  |  | Daily updates + discussions | tracking sheet | 0.5 | 0.25 | 1
JS | Thursday | 2015-04-30 |  | Analysis | DynamicSearch | 2.9 | Hotel | ATI dynamic search | already done | 6 | 0 | -1
JS | Thursday | 2015-04-30 |  | Discussion | DynamicSearch | 2.9 | Hotel | Dynamic search merging | discuss with DF + code + test | 1.5 | 0 | -1
JS | Thursday | 2015-04-30 |  | Planning | internal | Afidium |  | Daily call |  |  | 0.25 | 1
JS | Thursday | 2015-04-30 | 8798 | New |  | 2.8.1 | Hotel | Expedia status code implementation | finish tests |  | 1 | 1
JS | Thursday | 2015-04-30 | 7639 | New | Replication | 2.9 | Hotel | Load test replication DBs | Changed test tool to count SQA time + include in report + started tests |  | 1 | 1
JS | Thursday | 2015-04-30 | 8675 | Discussion | DynamicSearch | 2.9 | Hotel | Discussion with Raj | hg + instance setup |  | 1 | 1
JS | Thursday | 2015-04-30 |  | Discussion | internal |  | Hotel | Call with DF | PA feedback + TCC with EP + Q & A |  | 1 | 1
JS | Thursday | 2015-04-30 |  | New | server setup |  |  | Install IIS + setup FTP + wenji test tool website + rever RG changes to get latest version for my code |  |  | 2.5 | 1
JS | Thursday | 2015-04-30 | 8808 | Analysis |  | 2.8.1 | Hotel | Transaction context code analysis | Went through DF feedback + comment |  | 0.25 | 1
JS | Thursday | 2015-04-30 |  | Analysis |  | 2.9 | Hotel | Galaxyref list of actions | went through DF feedback |  | 0.25 | 1
JS | Thursday | 2015-04-30 |  | Discussion | internal | 2.8 | Hotel | Discussion with Anne | 2.8 updates + next actions + schedule call for Wed + checking |  | 0.5 | 1
PS | Wednesday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.5 | 1 | Leaves 2015-04-08 to 2015-04-12 2015-05-01
PS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 1 | 1 | 1
PS | Wednesday | 2015-04-01 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-01 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schema | based on CC's suggestion | 3 | 0 | -1
PS | Wednesday | 2015-04-01 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | read doc + xsl + questions and problems to CC + test | 2 | 5 | 0
PS | Wednesday | 2015-04-01 | 8238 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | correction of an issue with CC + test |  | 1 | 1
PS | Thursday | 2015-04-02 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet + venda report | 0.5 | 1 | 1
PS | Thursday | 2015-04-02 |  | Discussion | snapin |  |  | discussions + support for snapin | MM + SK | 1.5 | 1 | 1
PS | Thursday | 2015-04-02 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | Done + remaining listed in task | 3 | 2.5 | 0
PS | Thursday | 2015-04-02 | 8283 | New |  |  | TUI | Addition of parend log in Response | Checked Issue + corrections C# + test + problems on my computer | 3 | 3 | 1
PS | Friday | 2015-04-03 |  | Maintenance |  |  | Hotel | Production COT | Mails+ Reply | 0.25 | 0.25 | 1
PS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 0.5 | 1.5 | 1
PS | Friday | 2015-04-03 |  | Discussion | snapin |  |  | discussions + support for snapin | Feedback to Raj for mail | 1.5 | 0.5 | 1
PS | Friday | 2015-04-03 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schemas according to the documentation Update |  | 3 | 3 | 1
PS | Friday | 2015-04-03 | 8554 | New |  |  | Hotel | RMT failed on production | Loads + analysis | 3 | 3 | 1
PS | Monday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates + discussions | Uma : some testcases to her | 1 | 0.5 | 1
PS | Monday | 2015-04-06 |  | Discussion | snapin |  |  | discussions + support for snapin | SK + Raj + MM | 1.5 | 0.5 | 1
PS | Monday | 2015-04-06 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency |  | 2 | 2 | 1
PS | Monday | 2015-04-06 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Remaing : questins with CC + 3rd step | 4 | 2.75 | 0
PS | Monday | 2015-04-06 | 8581 | New |  |  | Hotel | RMT failed on production |  | 2 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Maintenance |  |  | Hotel | Production COT | Prod Mail | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet+ ST (2.8_rep tests) | 1 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Discussion | snapin |  |  | discussions + support for snapin | Raj + SK + RN | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8554 | New |  |  | Hotel | RMT failed on production | Some testcases to execute | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency | Testcases correction | 0.5 | 1.5 | 1
PS | Tuesday | 2015-04-07 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | questions with CC + proceed, not finished | 2 | 1.5 | 0
PS | Tuesday | 2015-04-07 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add Service/Insurance segments, seat assignment and insurance booking in Bookings | Output to CC for verification + question | 2.25 | 0.75 | 0
PS | Wednesday | 2015-04-08 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates + discussions | Uma + JS + ST | 0.5 | 1 | 1
PS | Wednesday | 2015-04-08 |  | Discussion | snapin |  |  | discussions + support for snapin | RN + MM : call | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-08 | 8566 | New |  |  | Hotel | dashboard data mismatch on different machines | ST+JS+MM+RN : call over issue investigation |  | 1.5 | 1
PS | Wednesday | 2015-04-08 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Finished with CC + test in oxygen + discussion with CC | 5 | 3 | 0
PS | Wednesday | 2015-04-08 | 8661 |  |  |  | Hotel | Cache Currency 2.9 | Started preparing testgrid + testcases for tests |  | 1.75 | 0
PS | Thursday | 2015-04-09 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet | 0.5 | 0.5 | 1
PS | Thursday | 2015-04-09 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.25 | 1
PS | Thursday | 2015-04-09 | 8661 | 2.9_tests |  | 2.9 | Hotel | Cache Currency 2.9 | SPR SQA K and Testgrid Done + few SQA F remaining | 5 | 4.5 | 0
PS | Thursday | 2015-04-09 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Work with CC + 3 xsls prepared + test | 2 | 2.5 | 0
PS | Friday | 2015-04-10 |  | Maintenance |  |  | Hotel | Production COT | Prod status + mail + data for ST in mail | 0.25 | 0.75 | 1
PS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 0.5 | 1 | 1
PS | Friday | 2015-04-10 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.5 | 1
PS | Friday | 2015-04-10 | 8678 |  |  |  | TUI | Issue Ticket: make possible the issuance of EMDs | 6 xsls + test | 2 | 2 | 1
PS | Friday | 2015-04-10 | 6830 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Xsl prepared plus tested plus questions with CC | 5 | 3.5 | 1
PS | Monday | 2015-04-13 |  | Maintenance |  |  | Hotel | Production COT | Mails + task creation(#8690) | 0.25 | 0.25 | 1
PS | Monday | 2015-04-13 |  | Planning | internal |  |  | Daily updates + discussions | Prod issue with JS | 0.5 | 0.5 | 1
PS | Monday | 2015-04-13 |  | Discussion | snapin |  |  | discussions + support for snapin | Support RN | 0.5 | 0.5 | 1
PS | Monday | 2015-04-13 | 8680 | New |  |  | TUI | [Search AddOn] - Update Insurance Segment | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8682 | New |  |  | TUI | Update Booking - Addition of insurance in the booking | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8684 | New |  |  | TUI | [CB/GB/UB] - Properly parse EMD ticket in responses | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Questions and confirmations with CC | 2 | 1 | 1
PS | Tuesday | 2015-04-14 |  | Maintenance |  |  | Hotel | Production COT | Prod Mail | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-14 |  | Planning | internal |  |  | Daily updates + discussions | Tracking Sheet + JS + ST | 1 | 1 | 1
PS | Tuesday | 2015-04-14 |  | Discussion | snapin |  |  | discussions + support for snapin | RN regarding #8566 | 1 | 1 | 1
PS | Tuesday | 2015-04-14 | 8691 | New |  |  | TUI | Test Scenarios | Preparations + questions with CC / only started | 4 | 1 | 0
PS | Tuesday | 2015-04-14 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add Service/Insurance segments, seat assignment and insurance booking in Bookings | Xsl new changes + co-ordination with CC | 2 | 3.25 | 1
PS | Tuesday | 2015-04-14 | 8678 | New |  |  | TUI | Issue Ticket: make possible the issuance of EMDs | Changes as per CC |  | 1 | 1
PS | Tuesday | 2015-04-14 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Some more changes |  | 1.5 | 1
PS | Wednesday | 2015-04-15 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-15 |  | Planning | internal |  |  | Daily updates + discussions | JS + TS + CC + Tracking sheet | 0.5 | 0.5 | 1
PS | Wednesday | 2015-04-15 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-15 | 8691 | New |  |  | TUI | Test Scenarios | Tests + issues + corrections + co-ordination with CC | 1 | 6.75 | 0
PS | Thursday | 2015-04-16 |  | Maintenance |  |  | Hotel | Production COT | Prod status + mail | 0.25 | 0.5 | 1
PS | Thursday | 2015-04-16 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet | 0.5 | 0 | -1
PS | Thursday | 2015-04-16 |  | Discussion | snapin |  |  | discussions + support for snapin | MM | 1 | 0.25 | 1
PS | Thursday | 2015-04-16 | 8661 |  |  |  | Hotel | Cache Currency 2.9 | Finish | 4 | 0 | -1
PS | Thursday | 2015-04-16 | 8691 | New |  |  | TUI | Test Scenarios | Tests with CC and issues | 2.25 | 7.25 | 0
PS | Friday | 2015-04-17 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 1 | 0.5 | 1
PS | Friday | 2015-04-17 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1 | 0 | -1
PS | Friday | 2015-04-17 | 8691 | New |  |  | TUI | Test Scenarios | If anything to test | 2 | 6.75 | 1
PS | Friday | 2015-04-17 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Xsl prepared plus tested plus questions with CC | 3.75 | 0.5 | 1
PS | Monday | 2015-04-20 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.5 | 1
PS | Monday | 2015-04-20 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet + JS co-ordination over devcache + precache updates, task creation 8749 | 1 | 1.75 | 1
PS | Monday | 2015-04-20 |  | Discussion | snapin |  |  | discussions + support for snapin | MM + RN | 0.5 | 0.5 | 1
PS | Monday | 2015-04-20 | 8733 | New |  |  | TUI | Enrichissement de la récupération de dossier | Co-ordination with EP and Rncs making | 2 | 2.5 | 1
PS | Monday | 2015-04-20 | 8741 | New |  |  | TUI | [GQA] - Implement Insurance_Pricing xsls | Xsl + tests | 2 | 2.25 | 1
PS | Monday | 2015-04-20 | 8732 | New |  |  | Hotel | Farebasis: Update RNC schemas | Started | 2.25 | 0.5 | 0
PS | Tuesday | 2015-04-21 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-21 |  | Planning | internal |  |  | Daily updates + discussions | JS + UZ + tracking sheet | 1 | 0.75 | 1
PS | Tuesday | 2015-04-21 |  | Discussion | snapin |  |  | discussions + support for snapin | RN + MM : call | 1 | 1 | 1
PS | Tuesday | 2015-04-21 | 8740 | New |  |  | TUI | [RNC] - CB/GB/UB |  | 5.75 | 4 | 0
PS | Tuesday | 2015-04-21 | 8732 | New |  | 2.8.1 | Hotel | Farebasis: Update RNC schemas | Finished |  | 2 | 1
PS | Wednesday | 2015-04-22 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-22 |  | Planning | internal |  |  | Daily updates + discussions | JS + TS + Travking Sheet | 0.5 | 0.75 | 1
PS | Wednesday | 2015-04-22 |  | Discussion | snapin |  |  | discussions + support for snapin | MM : Call | 1 | 0.5 | 1
PS | Wednesday | 2015-04-22 | 8740 | New |  |  | TUI | [RNC] - CB/GB/UB | Finish | 2 | 5.5 | 1
PS | Wednesday | 2015-04-22 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Read and start + questions | 4.25 | 1 | 0
PS | Thursday | 2015-04-23 |  | Maintenance |  |  | Hotel | Production COT | Read mails | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-23 |  | Planning | internal |  |  | Daily updates + discussions | ST + EP | 0.5 | 0.5 | 1
PS | Thursday | 2015-04-23 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1 | 0.5 | 1
PS | Thursday | 2015-04-23 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Q/A with EP , dev server set up and started with SQA, SSH installation + Informations from EP to configure SQA | 6.25 | 6.5 | 0
PS | Friday | 2015-04-24 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-04-24 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 1 | 2 | 1
PS | Friday | 2015-04-24 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1 | 0 | -1
PS | Friday | 2015-04-24 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 5.75 | 5.75 | 0
PS | Monday | 2015-04-27 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.5 | 1
PS | Monday | 2015-04-27 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet | 1 | 0.5 | 1
PS | Monday | 2015-04-27 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 0.5 | 0.25 | 1
PS | Monday | 2015-04-27 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 6.25 | 6.75 | 0
PS | Tuesday | 2015-04-28 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-28 |  | Planning | internal |  |  | Daily updates + discussions |  | 1 | 0.5 | 1
PS | Tuesday | 2015-04-28 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 0.5 | 0.5 | 1
PS | Tuesday | 2015-04-28 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 6.25 | 6.75 | 0
PS | Wednesday | 2015-04-29 |  | Maintenance |  |  | Hotel | Production COT | Mail | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-29 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet | 0.5 | 0.5 | 1
PS | Wednesday | 2015-04-29 |  | Discussion | snapin |  |  | discussions + support for snapin | - | 1 | 0.25 | 1
PS | Wednesday | 2015-04-29 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Co-rodination EP + CB tested, GQA RS in progress, lot of debugging | 6.25 | 7 | 0
PS | Thursday | 2015-04-30 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-30 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5 | 0.5 | 1
PS | Thursday | 2015-04-30 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1 | 0 | -1
PS | Thursday | 2015-04-30 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 6.25 | 7.25 | 0
ST | Thursday | 2015-04-02 | [5 empty] | Leave |  |  |  |  | Leaves 2015-03-30 to 2015-04-05 2015-05-01
ST | Friday | 2015-04-03 | [5 empty] | Leave
ST | Monday | 2015-04-06 |  | Discussion | internal |  | Stock | Discussion with Uma | Discussion about this week's plan, 8619, 8395, Hotel new server | 1 | 1.4 | 1
ST | Monday | 2015-04-06 | 8187 | New | server setup | 2.8 | Hotel | 2.8 New server DB : Updates Issues | Apply the recent installation script, executed post processing manually | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8188 | New | server setup | 2.9 | Hotel | 2.9 New server DB : Updates Issues | Correct the synonyms | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Checked the GQA script and suggested UZ to take help of PS and run some sqa, spr and gqa valid queries |  | 0.4 | 1
ST | Monday | 2015-04-06 | 8244 | Maintenance |  | 2.8 | Hotel | Mail shows 0 room updated for JNV | check and updated task with details |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | New | server setup |  |  | Setup of sql server for Rajendra | Setup Raj id on sd-29142 and checked his access problem |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates and discussion | tracking sheet and weekly task | 0.25 | 0.4 | 1
ST | Tuesday | 2015-04-07 | 8636 | Maintenance |  | 2.8 | Hotel | sp_checkIndex need correction for 2.8 | Analysis and testing and task updated | 1 | 0.5 | 0
ST | Tuesday | 2015-04-07 | 8637 | New |  |  | Hotel | Create 2.9 DB without galaxyref | guide uma | 0.5 | 0 | -1
ST | Tuesday | 2015-04-07 | 8575 | 2.8_tests |  | 2.8 | Hotel | Check se_versioned_tarif cleanup | Analysis and testing and task updated | 1 | 2 | 1
ST | Tuesday | 2015-04-07 | 8619 | New |  | 1.1 | Stock | Change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Analysis, discussion and proposal | 1.25 | 1 | 1
ST | Tuesday | 2015-04-07 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Testing of SQA, GQA and SPR on 2.8_rep database |  | 0.5 | 1
ST | Wednesday | 2015-04-08 | 8619 | New | internal | 1.1 | Stock | Change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | discussion with Uma and guide her and task updated with final plan | 0.25 | 0.5 | 0
ST | Wednesday | 2015-04-08 | 8634 | New |  | 1.1 | Stock | Refresh Materialized View vdi_airport | Analysis, discussion and guide, code, wiki review | 1 | 0.5 | 1
ST | Wednesday | 2015-04-08 | 8566 | 2.8_tests | Dashboard | 2.8 | Hotel | dashboard data mismatch on different machines | Testing, discussion | 2 | 2 | 1
ST | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and new server setup of galaxyref and ref_afidium, discussion with PS for devcache update check | 0.25 | 0.75 | 1
ST | Thursday | 2015-04-09 | 8636 | Maintenance |  | 2.8 | Hotel | sp_checkIndex need correction for 2.8 | Task updated with the details |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8480 | New |  | 1.1 | Stock | Update PNR (Passive Booking) on booking | Code and wiki review and testing |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8493 | New |  | 1.1 | Stock | Corrections related to external booking references | Code and wiki review and testing |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8395 | New |  | 1.1 | Stock | Improve stats speed | Analysis, prposed tests and changes |  | 0.5 | 0
ST | Thursday | 2015-04-09 | 8666 | New |  | 1.2 | Stock | Update SP Bkg_booking_get | Analysis and Discussion |  | 0.75 | 1
ST | Thursday | 2015-04-09 | 8612 | New |  | 1.1 | Stock | bkg_booking__get implementation NOK | Analysis and task updated |  | 0.5 | 0
ST | Friday | 2015-04-10 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Testing of SQA, GQA and SPR on 2.8_rep database , done data check | 0.6 | 0 | -1
ST | Friday | 2015-04-10 | 8493 | New |  | 1.1 | Stock | Corrections related to external booking references | wiki reviewed and confirmed | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7639 | New | Replication |  | Hotel | setup of replication activity | Checked SPR, SQA , GQA, corrected ref_Afidium problem , task updated with details. | 2 | 2 | 1
ST | Friday | 2015-04-10 | 8636 | Maintenance |  | 2.8.1 | Hotel | sp_checkIndex need correction for 2.8 | Task updated, installation script created | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7079 | New |  | 2.8 | Hotel | Dashboar_2.8 : Data Checking | assigned to PS and discussed with her | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7337 | Documentation |  |  | Hotel | Update documentation for dashboard and update SPs | reviewed wiki and close the task | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 4776 | Documentation |  |  | Hotel | [TABLE] : document the tables of the search engine | reviewed wiki and close the task | 0.4 | 0.4 | 1
ST | Monday | 2015-04-13 | 8651 | Development |  | 1.2 | Stock | [db] add information in db to handle additional booking features | Analysis, Discussion with DF and task updated | 2.5 | 2.5 | 0
ST | Monday | 2015-04-13 | 8619 |  |  |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Guide Uma for coding , coordinated with AR for testing | 1 | 1 | 0
ST | Monday | 2015-04-13 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, #7639, #8604 | 0.5 | 0.5 | 1
ST | Tuesday | 2015-04-14 | 8689 | New | Replication | 2.9 | Hotel | Load Replication server with SQA | Discussion with JS, test, discussion with Uma | 1.5 | 1.5 | 1
ST | Tuesday | 2015-04-14 | 7639 | New | Replication |  | Hotel | setup of replication activity | Check VDM synchro issue, and started complete VDM synchro, got error in full and focussed synchro both | 0.5 | 0.5 | 0
ST | Tuesday | 2015-04-14 | 8619 |  |  | 1.1 | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Code review and wiki review and testing | 1.5 | 1.5 | 1
ST | Wednesday | 2015-04-15 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet for the week | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 8709 |  |  | 1.1 | Stock | bbkg_booking__replace booking selection is NOK | coding, testing | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 8376 | Development |  | 3.6 | AIR | Routine AIR DB Cleanup | Code review and wiki review and testing | 1.5 | 1.5 | 1
ST | Wednesday | 2015-04-15 | 8711 |  |  | 1.1 | Stock | bkg_booking__replace not work anymore | coding, testing | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 7639 | New | Replication |  | Hotel | setup of replication activity | Resolve vdm synchro issue and test full day updates with replication | 1 | 1 | 1
ST | Thursday | 2015-04-16 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, prod update check, coordinated with Uma for diff tasks | 0.5 | 0.75 | 1
ST | Thursday | 2015-04-16 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Changes applied in database 2.8 and task updated with plan |  | 0.5 | 0
ST | Thursday | 2015-04-16 | 7639 | New | Replication | 2.9 | Hotel | setup of replication activity | Executed VDM update successfully, checked replication setup for verification as SQA was timeout of rep database |  | 0.75 | 0
ST | Thursday | 2015-04-16 | 8272 | Maintenance |  | 1.1 | Stock | Fiw installation script to NOT delete existing users from sto_auth_assignement table | Understanding, Analysis, coding and testing, discussion |  | 1.5 | 1
ST | Thursday | 2015-04-16 | 8722 | Maintenance |  | 1.1 | Stock | [Booking] Wrong total cost amount when created with Replace in post | Analysis, discussion, coding and testing |  | 0.5 | 1
ST | Thursday | 2015-04-16 | 8442 | Development |  | 1.2 | Stock | [Query][DB] Create table and SPs for SearchQuery | wiki and code review and tests | 2.5 | 0 | -1
ST | Thursday | 2015-04-16 | 8166 | New |  | 2.9 | Hotel | Time Measurrement | Test data from Database | 1 | 0 | -1
ST | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, discussion with Uma for 2.9_refafidium Db, daily check | 0.5 | 0.4 | 1
ST | Friday | 2015-04-17 | 8623 | Development |  | 1.2 | Stock | tables.inc.pgsql rules not respected + | Review the code and wiki and tests | 2 | 0 | -1
ST | Friday | 2015-04-17 | 8166 | New |  | 2.9 | Hotel | Time Measurrement | Analysis and testing and task updation | 1.5 | 1 | 1
ST | Friday | 2015-04-17 | 8187 | New | server setup | 2.8 | Hotel | 2.8 New server DB : Updates Issues | Task updated with the details, checked 2.8 DB updates, tried to find the issue |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8625 | New |  | 1.2 | Stock | enrich dictionary | Analysis and task updated |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8727 | Maintenance |  | 1.1 | Stock | Fiw installation script to NOT delete existing users from sto_auth_assignement table | Applied changes in 1.2 and discussion with Ar |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | Execute Hotel synchro and checked in all DBs |  | 0.4 | 1
ST | Monday | 2015-04-20 |  | Planning | internal |  |  | Planning for whole DB team | Check the diff task of DB with DB team, create some planned task, assign to related person | 2 | 2.5 | 1
ST | Monday | 2015-04-20 | 8651 | Discussion | internal | 1.2 | Stock | [db] add information in db to handle additional booking features | Discussion with SP to explain the req and changes. Discussion with Uma for testing and issue found in diff SP. Corrected the code and retest | 2 | 2 | 1
ST | Monday | 2015-04-20 | 8187 | 2.8_tests |  | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the updates and related checks on new server | 0.5 | 0 | -1
ST | Monday | 2015-04-20 | 8376 | New |  | 3.2 | AIR | Routine air DB Clean up | Code review and testing |  | 0 | -1
ST | Tuesday | 2015-04-21 | 8442 | New |  | 1.2 | Stock | [Query][DB] Create table and SPs for SearchQuery | Code review, discussion with TC, GK and AR | 2 | 1.5 | 0
ST | Tuesday | 2015-04-21 | 7639 | New | Replication | 2.9 | Hotel | Setup of Replication Activity | Checked VDM synchro issue and deleted old data of VDM from all tables and executed complete VDm synchro | 1 | 1 | 0
ST | Tuesday | 2015-04-21 | 8187 | 2.8_tests |  | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the updates and related checks on new server | 0.5 | 0.5 | 1
ST | Tuesday | 2015-04-21 |  | Planning | internal |  |  | Daily updates + discussions | Discussion with Uma for diff tasks and JS for Replication task | 0.5 | 0.5 | 1
ST | Tuesday | 2015-04-21 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | Review the req and code and test |  | 0.5 | 1
ST | Wednesday | 2015-04-22 | 8249 | New |  | 1.2 | Stock | [PGSQL] Check All core_modules Tables | Review the req and code and test | 0 | 0 | -1
ST | Wednesday | 2015-04-22 | 8623 | New |  | 1.2 | Stock | tables.inc.pgsql rules not respected + | Review the req and code and test | 2 | 0 | -1
ST | Wednesday | 2015-04-22 | 7639 | New | Replication | 2.9 | Hotel | Setup of Replication Activity | Check the VDM test query in wiki, analyse the data for them, corrected the queries, executed VDM synchro for the hotels having issue | 1.5 | 2.5 | 0
ST | Wednesday | 2015-04-22 |  | Planning | internal |  |  | Daily updates + discussions | Explain Uma her next activity, tracking sheet, discussion with JS | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-22 |  | Discussion | internal |  | Hotel | Coordinated with Uma for all documentation task closure |  |  | 0.6 | 1
ST | Wednesday | 2015-04-22 | 8637 | New |  | 2.8.1 | Hotel | Create DB 2.9 without galaxyref | checked 2.8 and 2.8_rep because of file copy from 2.8 to 2.8.1 by JS |  | 0.4 | 1
ST | Thursday | 2015-04-23 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Testing | 3 | 0 | -1
ST | Thursday | 2015-04-23 | 8553 | New |  | 2.9 | Hotel | GQA should generate and error | Review the req and code and test, coded for 2.9 and tested | 0.5 | 0.8 | 1
ST | Thursday | 2015-04-23 |  | Review | internal |  |  | Review the work done by diff DB team member |  | 0.5 | 0 | -1
ST | Thursday | 2015-04-23 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | Review the req and code and test | 0.5 | 0 | -1
ST | Thursday | 2015-04-23 |  | Discussion | internal |  |  | Daily updates + discussions | Discussion with Uma, JS |  | 0.6 | 1
ST | Thursday | 2015-04-23 | 8427 | New |  | 2.9 | Hotel | Automation of Hotel and VDM Snchro Tests | Code review, test and wiki review and corrected wiki |  | 0.6 | 1
ST | Thursday | 2015-04-23 | 7639 | New | Replication | 2.9 | Hotel | setup of replication activity | Understand how to check the SQA result from file given by JS. Tested for some cases where there is no information and found that the data is not available in the database. |  | 2 | 0
ST | Friday | 2015-04-24 |  | Discussion | internal |  |  | Discussion with Sp for sto_journey SPs |  | 2 | 0 | -1
ST | Friday | 2015-04-24 |  | Planning | internal |  |  | Planning for whole DB team |  | 1 | 0 | -1
ST | Friday | 2015-04-24 | 8689 | New |  | 2.8 | Hotel | Load replication server with SQA | Done some more tests using files from server. Explain Uma about all tests done, corrected her understnding, task updated |  | 1.5 | 1
ST | Friday | 2015-04-24 |  | Discussion | internal |  | Hotel | Discussion with JS for diff topics and SQA |  |  | 1 | 1
ST | Friday | 2015-04-24 | 8788 | New |  | 2.8.1 | Hotel | Create New database wenji_log_2.8.1 for sm_searchengine_2.8.1 | Created , reviewed, closed |  | 0.25 | 1
ST | Friday | 2015-04-24 | 8188 | New |  | 2.9 | Hotel | Sd- 2.9 New server DB : Updates Issues | reviewed , clsoed |  | 0.25 | 1
ST | Monday | 2015-04-27 | 7639 | New | Replication | 2.9 | Hotel | Setup replication activity | Test diff updates with and without replication, SQA tests with and without updates, wiki for all tests | 3.5 | 2 | 1
ST | Monday | 2015-04-27 |  | Planning | internal |  |  | Daily updates + discussions | tracking sheet + discussions | 0.5 | 0.5 | 1
ST | Monday | 2015-04-27 |  | Planning | internal |  |  | Planning for whole DB team | Check the diff task of DB with DB team, create some planned task, assign to related person |  | 1.5 | 1
|  |  |  | Discussion | internal |  |  | Coordinate with diff DB team memebers |  |  | 0 | -1
ST | Tuesday | 2015-04-28 | 7639 | New | Replication | 2.9 | Hotel | Setup replication activity | Documentation : wiki for setup of replication | 3 | 1.25 | 1
ST | Tuesday | 2015-04-28 |  | Discussion | internal | 1.1 | Stock | Coordinate with stock team for 1.1 installation | coordinate for diff issues |  | 1.5 | 1
ST | Tuesday | 2015-04-28 | 8309 | New |  | 2.8 | Hotel | Dynamic search EXP | rebuild all indexes and tested all SQA , discussion with JS, task updated |  | 1.25 | 1
ST | Tuesday | 2015-04-28 |  | Review | internal |  |  | Review work done by DB team member |  | 1 | 0 | -1
ST | Tuesday | 2015-04-28 |  | Discussion | internal |  |  | Coordinate with diff DB team memebers |  |  | 0 | -1
ST | Tuesday | 2015-04-28 |  | Analysis |  |  |  | Analysis of diff tasks for DB team to work on |  |  | 0 | -1
ST | Wednesday | 2015-04-29 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Testing |  | 0 | -1
ST | Wednesday | 2015-04-29 |  | Review | internal |  |  | Review work done by DB team member |  |  | 0 | -1
ST | Wednesday | 2015-04-29 |  | Discussion | internal |  |  | Coordinate with diff DB team memebers |  |  | 0 | -1
ST | Wednesday | 2015-04-29 |  | Discussion | internal | 1.2 | Stock | Coordinated with AR for branch merge of stockportal and stockportal_1.2 |  |  | 0.75 | 1
ST | Wednesday | 2015-04-29 | 8802 | New |  | 1.2 | Stock | Add the forth indicator 01 to APIS and SFPD indicator | code review, testing, code correction, code committed in hg for shilpa, wiki review |  | 0.75 | 1
ST | Wednesday | 2015-04-29 |  | Discussion | internal | 1.2 | Stock | Explained Shilpa for work of diff task and #8396 basic requirement |  |  | 0.75 | 1
ST | Wednesday | 2015-04-29 | 8197 | New |  | 1.2 | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis and discussion with Uma |  | 0.75 | 0
ST | Wednesday | 2015-04-29 | 8790 | New |  | 1.2 | Stock | Need a SP for Checking if the route exists in DB. | Discussion with RG, Task updated with queries |  | 0.75 | 0
ST | Wednesday | 2015-04-29 | [5 empty] | Discussion wuth Uma for other task, tracking sheet |  |  | 0.25 | 1
ST | Thursday | 2015-04-30 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Executed updates on 2.8.1 database | 0.5 | 0.5 | 0
ST | Thursday | 2015-04-30 |  | Review | internal |  |  | Review work done by DB team member |  |  | 0 | -1
ST | Thursday | 2015-04-30 |  | Discussion | internal |  |  | Coordinate with diff DB team memebers |  |  | 0 | -1
ST | Thursday | 2015-04-30 | 8197 | New |  | 1.2 | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis , discussion with Uma for diff changes |  | 0.5 | 1
ST | Thursday | 2015-04-30 | 7639 | New | Replication | 2.9 | Hotel | Setup replication activity | Document the replication setup in detail |  | 3 | 1
UZ | Wednesday | 2015-04-01 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1 | 0.5 | 1 | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Wednesday | 2015-04-01 | 8187 |  |  | 2.8 | Hotel | Sd-2.8 New server DB: Updates issues | checked updated on new server |  | 0.25 | 1
UZ | Wednesday | 2015-04-01 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | Modified SP + testing | 1 | 1.25 | 0
UZ | Wednesday | 2015-04-01 | 8528 | New | pgsql |  | Stock | improve location management | modified view + created SP + testing | 4 | 4 | 1
UZ | Thursday | 2015-04-02 | 8272 |  |  |  | Hotel | test data in replication server & execute search | data validation | 1 | 0.5 | 1
UZ | Thursday | 2015-04-02 | 7639 | New | Replication |  | Hotel | setup of replication activity | check for indexes are present or not on new server |  | 0.25 | 1
UZ | Thursday | 2015-04-02 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | added column in table + Modified SP |  | 1.25 | 0
UZ | Thursday | 2015-04-02 | 8604 | New | pgsql |  | Stock | create a SP to return external references for given booking | created SP + testing + coordinate with SS (to help him) |  | 2.5 | 1
UZ | Thursday | 2015-04-02 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | testing + update task |  | 1.25 | 1
UZ | Friday | 2015-04-03 | 8272 |  |  |  | Hotel | test data in replication server & execute search | testing + update task | 1 | 1 | 1
UZ | Friday | 2015-04-03 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | Modified SP + testing | 1 | 1.5 | 1
UZ | Friday | 2015-04-03 | 8619 | New | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | analysis | 4 | 1.75 | 0
UZ | Friday | 2015-04-03 | 8637 | New | pgsql |  | Stock | modify sys function | discuss with ST + update task |  | 0.25 | 1
UZ | Friday | 2015-04-03 |  | Planning | internal |  |  | discuss with ST | call with ST for Planning + work status |  | 0.5 | 1
UZ | Friday | 2015-04-03 | 8460 | New |  |  | Stock | booking + winter | correct daigram |  | 1 | 1
UZ | Monday | 2015-04-06 | 8188 | New | Replication | 2.9 | Hotel | 2.9 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.5 | 1
UZ | Monday | 2015-04-06 | 8187 | New | Replication | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.25 | 1
UZ | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | test data in replication server & execute search | data validation + created wiki + updated task | 1 | 1 | 1
UZ | Monday | 2015-04-06 | 8619 | New |  | 1.1 | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | discuss with ST + update task | 1 | 1 | 0
UZ | Monday | 2015-04-06 | 8395 | New |  | 1.1 | Stock | Improve stats speed | Discuss with ST, testing, updated task | 1 | 1.25 | 0
UZ | Monday | 2015-04-06 | 8528 | New | Documentation | 1.1 | Stock | improve location management | Created wiki for view & SP | 1.5 | 1.5 | 1
UZ | Monday | 2015-04-06 |  | Planning | internal |  |  | discuss with ST | call with ST for work planning | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-04-07 | 8272 |  |  |  | Hotel | test data in replication server & execute search | tested data + excuted search + updated task | 0.5 | 0.75 | 1
UZ | Tuesday | 2015-04-07 | 8188 |  |  |  | Hotel | Sd-2.9 New server DB : Updates Issues | checked updates | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | checked updates + updated task | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | call with ST + analysis + planning | 2.5 | 2.5 | 0
UZ | Tuesday | 2015-04-07 | 8567 |  | pgsql |  | Stock | Add error message into SP sto_quotation__search if quotation search doesn't return any results | discuss with YT and coding and testing | 1 | 1 | 1
UZ | Tuesday | 2015-04-07 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport | Analysis+praposal | 1.5 | 1 | 0
UZ | Tuesday | 2015-04-07 |  |  | internal |  |  | fill up tracking sheet |  |  | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 0.25 | 0.75 | 1
UZ | Wednesday | 2015-04-08 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task | 0.25 | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task | 0.25 | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8651 |  |  |  | Stock | [db] add information in db to handle additional booking features | analysis |  | 0.5 | 0
UZ | Wednesday | 2015-04-08 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions |  | 4 | 1.25 | 0
UZ | Wednesday | 2015-04-08 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport |  | 1 | 3 | 1
UZ | Thursday | 2015-04-09 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8250 |  | pgsql |  | Stock | LogManagerFS : convert code from sql to pgsql | Coordinate with Dhanesh and help him to finish it |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8249 |  | pgsql |  | Stock | [PGSQL] Check All core_modules Tables | Coordinate with Dhanesh and help him to finish it |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8197 |  | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis and Discussion |  | 0 | -1
UZ | Friday | 2015-04-10 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task | 0.25 | 0 | -1
UZ | Friday | 2015-04-10 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task | 0.25 | 0 | -1
UZ | Friday | 2015-04-10 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task | 0.5 | 0.5 | 1
UZ | Friday | 2015-04-10 | 8187 | New | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Coding and testing | 4 | 0 | -1
UZ | Friday | 2015-04-10 | 8629 | New | pgsql |  | Stock | document bkg_booking__replace | Documentation | 1 | 0 | -1
UZ | Friday | 2015-04-10 | 8395 | New | pgsql |  | Stock | Improve stats speed | discussion with ST Modify+test + update |  | 3 | 1
UZ | Friday | 2015-04-10 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | Discussion with ST + Created DB |  | 2 | 0
UZ | Friday | 2015-04-10 |  | Planning | internal |  |  | discuss with ST | call with ST for work planning |  | 0.5 | 1
UZ | Monday | 2015-04-13 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Discussion with ST,AR+ Modified SP, created table+SP, documentation, testing | 6 | 6 | 1
UZ | Monday | 2015-04-13 | 8604 |  | pgsql |  | Stock | Create a SP to return external references for given booking | Modified SP + testing + documentation |  | 1 | 1
UZ | Tuesday | 2015-04-14 | 8637 |  |  |  | Hotel | Create DB 2.9 without galaxyref | added SPs, checked SPs with 2.8, updated task | 2.5 | 3 | 1
UZ | Tuesday | 2015-04-14 | 8689 |  |  |  | Hotel | Load replication server with SQA | discussion with JS, call with ST, understanding, test | 3.5 | 3 | 0
UZ | Wednesday | 2015-04-15 | 8689 |  |  |  | Hotel | Load replication server with SQA | checked for loads | 0.5 | 0.25 | 1
UZ | Wednesday | 2015-04-15 | 7639 |  |  |  | Hotel | setup of replication activity | tested data on replication DB | 0.75 | 0.75 | 1
UZ | Wednesday | 2015-04-15 | 8651 |  |  |  | Stock | [db] add information in db to handle additional booking features | documentation | 5 | 6 | 0
UZ | Thursday | 2015-04-16 | 8689 |  |  |  | Hotel | Load replication server with SQA | checked for loads + testing | 2 | 2 | 1
UZ | Thursday | 2015-04-16 | 8719 |  |  |  | Hotel | change se_availability__update | Modified SP + testing | 1 | 1 | 1
UZ | Thursday | 2015-04-16 | 8729 |  | pgsql |  | Stock | bkg_booking__get with new traveller and | documentation + modified SP | 3 | 3 | 0
UZ | Friday | 2015-04-17 | 8729 |  | pgsql |  | Stock | bkg_booking__get with new traveller and | Discussion with ST +documentation + modified SP + testing | 2 | 2 | 1
UZ | Friday | 2015-04-17 | 8651 |  | pgsql |  | Stock | [db] add information in db to handle additional booking features | Discussion with ST +Documentation + testing SPs | 4 | 4.5 | 1
UZ | Friday | 2015-04-17 | 8637 |  |  |  | Hotel | Create DB 2.9 without galaxyref | Inserted data in DB |  | 0.75 | 0
UZ | Monday | 2015-04-20 | 8729 | New | Documentation | 1.2 | Stock | bkg_booking__get with new Info | Update the ticket with what u had done and assign to shilpa for completion of wiki. Also guide Shilpa for testing SPs related to 8651. | 0.25 | 0.5 | 1
UZ | Monday | 2015-04-20 | 7639 | 2.9_tests | Replication | 2.9 | Hotel | Setup of Replication Activity | Test VDm data in 2.8 Db against the wiki mentioned in task | 1 | 0.5 | 1
UZ | Monday | 2015-04-20 | 8651 | New | pgsql |  | Stock | [db] add information in db to handle additional booking features | Discussion with ST + testing SPs |  | 3 | 1
UZ | Monday | 2015-04-20 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | complete the remaining things and close the task |  | 0.5 | 1
UZ | Monday | 2015-04-20 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Test SQA output |  | 1.5 | 1
UZ | Tuesday | 2015-04-21 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Checked if tests were played. None were played by JS | 1.5 | 0.25 | 1
UZ | Tuesday | 2015-04-21 | 8553 | New |  | 2.9 | Hotel | GQA should generate and error | Analysis, coding, testing and doc | 3.5 | 4.25 | 1
UZ | Tuesday | 2015-04-21 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | create the checklist wiki for this | 1 | 0.75 | 1
UZ | Tuesday | 2015-04-21 | 8427 | New |  | 2.9 | Hotel | Automation of Hotel and VDM Snchro Tests | complete the remaining things and close the task |  | 0.75 | 0
UZ | Wednesday | 2015-04-22 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Test SQA output | 1.5 | 1 | 1
UZ | Wednesday | 2015-04-22 |  | Review | Documentation |  | Hotel | Close the documentation tasks -- Hotel | Discussion with ST, created blanck wikis | 3.5 | 2 | 1
UZ | Wednesday | 2015-04-22 | 8427 | New |  | 2.9 | Hotel | Automation of Hotel and VDM Snchro Tests | complete the remaining things and close the task | 1 | 2.5 | 1
UZ | Wednesday | 2015-04-22 |  | Discussion | internal |  |  | Call with ST for task planning | call with ST for work planning |  | 0.5 | 1
UZ | Thursday | 2015-04-23 | 8612 | New |  | 1.2 | Stock | bkg_booking__get implementation NOK | Analysis, coding, testing and doc | 4 | 0.5 | 0
UZ | Thursday | 2015-04-23 |  | Discussion | internal |  | Stock | Discussion with SP to explain sto_journey SPs |  | 2 | 0 | -1
UZ | Thursday | 2015-04-23 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | Wiki |  | 0.75 | 1
UZ | Thursday | 2015-04-23 | 8533 | New |  | 2.8.1 | Hotel | GQA should generate and error | Wiki |  | 2 | 1
UZ | Thursday | 2015-04-23 | 8689 | New | Replication | 2.9 | Hotel | Load replication server with SQA | Test SQA output |  | 1.75 | 1
UZ | Thursday | 2015-04-23 | 8188 | New |  | 2.9 | Hotel | Sd- 2.9 New server DB : Updates Issues | Update check |  | 0.25 | 1
UZ | Thursday | 2015-04-23 |  | Discussion | internal |  |  | Discussion with ST | call with ST for work planning |  | 0.5 | 1
UZ | Friday | 2015-04-24 | 8188 | New |  | 2.9 | Hotel | Sd- 2.9 New server DB : Updates Issues | checked updates |  | 0.5 | 1
UZ | Friday | 2015-04-24 | 8689 | New | Replication | 2.9 | Hotel | Load replication server with SQA | discussion with ST +Testing + wiki |  | 3 | 1
UZ | Friday | 2015-04-24 | 8778 | New |  | 1.2 | Stock | History of sto_journey & sto_stock | analysis |  | 1 | 0
UZ | Friday | 2015-04-24 | 8612 | New |  | 1.2 | Stock | bkg_booking__get implementation NOK | analysis |  | 0.75 | 0
UZ | Friday | 2015-04-24 | 8788 | New |  | 2.9 | Hotel | Create wenji_log_2.8.1 DB | Created DB |  | 0.75 | 1
UZ | Monday | 2015-04-27 | 8778 | New |  | 1.2 | Stock | History of sto_journey and sto_stock | coding + testing | 4 | 5 | 1
UZ | Monday | 2015-04-27 | 8612 | New |  | 1.2 | Stock | bkg_booking__get implementation NOK | Analysis, coding, testing and doc | 2 | 1 | 1
UZ | Tuesday | 2015-04-28 | 8369 | New |  | 1.2 | Stock | Update SPs : implement SPs to update only what has changed | Discussion with ST + created proposal | 5 | 4 | 1
UZ | Tuesday | 2015-04-28 |  | Discussion | internal | 1.2 | Stock | Discussion with Shilpa about journey SPs if she has any queries |  | 1 | 0 | -1
UZ | Tuesday | 2015-04-28 | 8778 | New |  | 1.2 | Stock | History of sto_journey & sto_stock | Moved changes to stock_portal_1.2 branch |  | 0.25 | 1
UZ | Tuesday | 2015-04-28 | 8197 | New |  | 1.2 | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis |  | 1.25 | 0
UZ | Tuesday | 2015-04-28 |  | Discussion | internal |  | Stock | coordination with SS | Helped to SS & solved his problem |  | 0.75 | 1
UZ | Wednesday | 2015-04-29 | 8197 | New |  | 1.2 | Stock | [QUOTATION] Cleanup sto_tariff functions and related | analysis, discussion, documentation | 4 | 3 | 0
UZ | Wednesday | 2015-04-29 | 8799 | New |  | 1.2 | Stock | Modify vdi_airport view | Analysis, coding, testing and doc | 2 | 0.75 | 0
UZ | Wednesday | 2015-04-29 | 8369 | New |  | 1.2 | Stock | Update SPs : implement SPs to update only what has changed | call with SP |  | 0.25 | 1
UZ | Wednesday | 2015-04-29 | 8813 | New |  | 1.2 | Stock | Get information from AR and TC | call with AR,DM,SP |  | 2 | 1
UZ | Thursday | 2015-04-30 | 8197 | New |  | 1.2 | Stock | [QUOTATION] Cleanup sto_tariff functions and related | discussion with ST, update task with proposal, coding, testing,documentation |  | 6 | 0