## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Monday | 2015-05-04 | [5 empty] | Leave |  |  | 0 | -1 | Leaves 2015-05-25 I will need some leaves in MAY/June on short notice
JS | Tuesday | 2015-05-05 |  | Planning | internal |  |  | Weekly planning sheet |  | 1.5 | 1.5 | 1
JS | Tuesday | 2015-05-05 |  | New |  | 2.8 | Hotel | Check CC mail for availability VDM |  | 0.5 | 0.5 | 1
JS | Tuesday | 2015-05-05 | 8789 | Maintenance |  | 2.8 | Hotel | Check prod update schedule + dashboard | Checked updates OK. But dashboard is not loading redmine wiki. To EP | 1 | 1 | 0
JS | Tuesday | 2015-05-05 |  | Discussion | internal | Afidium |  | Daily call |  | 0.25
JS | Tuesday | 2015-05-05 | 8719 | 2.9_tests |  | 2.9 | Hotel | se_availability__update change | Review + test + finalize | 1 | 1 | 1
JS | Tuesday | 2015-05-05 |  | Analysis |  | 2.9 | Hotel | galaxyref import | analysis change + specs + start describing test process | 3
JS | Wednesday | 2015-05-06 |  | Planning | internal |  |  | Daily updates | tracking sheet + daily call | 0.5
JS | Wednesday | 2015-05-06 | 8427 | 2.9_tests |  | 2.9 | Hotel | Automation of Hotel and VDM synchro tests | Review + test + finalize | 1
JS | Wednesday | 2015-05-06 |  | Discussion | internal |  | Hotel | Discussion with Anne for galaxyref changes |  | 1
JS | Wednesday | 2015-05-06 |  | Analysis | DynamicSearch | 2.9 | Hotel | ATI dynamic search | analysis for searching with city | 2
JS | Wednesday | 2015-05-06 | 8798 | New |  | 2.8.1 | Hotel | Expedia status code implementation | finish tests | 0.5
JS | Wednesday | 2015-05-06 | 8689 | New | Replication | 2.9 | Hotel | SQA response times on replicated DB | launch tool + review report + cases for ST to analyse | 1
JS | Wednesday | 2015-05-06 |  | Analysis |  | 2.9 | Hotel | galaxyref import | Finish describing test process | 2
JS | Thursday | 2015-05-07 | 8427 | 2.9_tests |  | 2.9 | Hotel | Automation of Hotel and VDM synchro tests | finalize | 1
JS | Thursday | 2015-05-07 |  | Planning | internal |  |  | daily updates | tracking sheet + daily call | 0.5
JS | Thursday | 2015-05-07 | 8808 | Analysis |  | 2.8.1 | Hotel | TCC analysis after DF/EP call | check for each provider + document | 2.5
JS | Thursday | 2015-05-07 | 8787 | Analysis | DynamicSearch | 2.9 | Hotel | Analysis for Tourplan after DF call | Justifications for why things are not possible + compare against current GQA | 2.5
JS | Thursday | 2015-05-07 | 8085 | New |  | 2.8.1 | Hotel | Cost currency overrride for SQA | Remove warning from code : PA answer + test | 1
JS | Thursday | 2015-05-07 |  | Planning | internal |  |  | Plan for hotel handover from ST |  | 0.5
JS | Friday | 2015-05-08 |  | Planning | internal |  |  | daily updates | tracking sheet + daily call | 0.5
JS | Friday | 2015-05-08 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Check against updated RNC + fix if needed + test | 1
JS | Friday | 2015-05-08 | 8789 | Maintenance |  | 2.8 | Hotel | Check Prod updates for the week if OK + check through dashboard |  | 0.5
JS | Friday | 2015-05-08 | 8689 | New | Replication | 2.9 | Hotel | SQA response times on replicated DB | launch tool + review report + cases for ST to analyse | 1
JS | Friday | 2015-05-08 | 8087 | New | Documentation | 2.9 | Hotel | Document public access to EXP error hotel test tool for DB3 | For GK to plan DB3 | 1
JS | Friday | 2015-05-08 | 7643 | 2.9_tests |  | 2.9 | Hotel | TRP focussed updates test | compare against devcache | 1
JS | Friday | 2015-05-08 | 7787 | 2.9_tests |  | 2.9 | Hotel | JNV focussed update tests | compare against devcache | 1
JS | Friday | 2015-05-08 |  | Analysis |  | 2.9 | Hotel | EXP UPC analysis | to keep prices in DB even when we don’t get it from EXP | 2
PS | Monday | 2015-05-04 |  | Maintenance |  |  | Hotel | Production COT | Mails (4 days) | 0.25 | 0.5 | 1 | Leaves 2015-06-11 to 2015-06-12
PS | Monday | 2015-05-04 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet: week plan | 1 | 0.5 | 1
PS | Monday | 2015-05-04 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 0.5 | 0.25 | 1
PS | Monday | 2015-05-04 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Questions and solution with CC | 6 | 6.5 | 0
PS | Monday | 2015-05-04 | 8732 | New |  |  | TUI | Farebasis: Update RNC schemas | correct order in CB GB | 0.15 | 0.25 | 1
PS | Tuesday | 2015-05-05 |  | Maintenance |  |  | Hotel | Production COT | Mail | 0.25
PS | Tuesday | 2015-05-05 |  | Planning | internal |  |  | Daily updates + discussions | JS + Tracking sheet | 1
PS | Tuesday | 2015-05-05 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 0.5
PS | Tuesday | 2015-05-05 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Start Testing after finish | 6.25
PS | Wednesday | 2015-05-06 |  | Maintenance |  |  | Hotel | Production COT | Mail | 0.25
PS | Wednesday | 2015-05-06 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Wednesday | 2015-05-06 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Wednesday | 2015-05-06 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Tests | 6.25
PS | Thursday | 2015-05-07 |  | Maintenance |  |  | Hotel | Production COT | Mail | 0.25
PS | Thursday | 2015-05-07 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Thursday | 2015-05-07 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Thursday | 2015-05-07 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Tests | 6.25
PS | Friday | 2015-05-08 |  | Maintenance |  |  | Hotel | Production COT | Mail | 0.25
PS | Friday | 2015-05-08 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Friday | 2015-05-08 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Friday | 2015-05-08 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Tests | 6.25
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
ST
UZ | Monday | 2015-05-05 | [5 empty] | leave |  |  |  |  | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Tuesday | 2015-05-06 | [5 empty] | leave
UZ | Wednesday | 2015-05-07 | [5 empty] | leave
UZ | Thursday | 2015-05-08 | [5 empty] | leave
UZ | Friday | 2015-05-09 | [5 empty] | leave