## Sheet1
Initials | Day | Date | Task | Category | sub-category | version | Project | Task description | Next action | Planned time | Actually spent | Status | Important information
JS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0 | -1 | Leaves 2015-05-01 2015-05-25 I will need some leaves in APR/MAY on short notice
JS | Wednesday | 2015-04-01 | 8093 | 2.8_tests |  | 2.8 | Hotel | SQA tests between precache and prod | test + analysis | 3 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | 2.8 | Hotel | Make a list of quality control actions then tools to automate (JS+AF) | First discussion with Anne | 1 | 0 | -1
JS | Wednesday | 2015-04-01 |  | New | Documentation | 2.8 | Hotel | Describe usage +behavior of test tool EXP for DH |  | 1.5 | 0 | -1
JS | Wednesday | 2015-04-01 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | Implementation + tests | 2 | 0 | -1
JS | Wednesday | 2015-04-01 |  | Discussion | internal | Afidium |  | Daily call |  | 0.25 | 0 | -1
JS | Wednesday | 2015-04-01 | 8586 | 2.8_tests |  | 2.8 | Hotel | Patch preparation + application | FTP patch update + test cleanup patch + apply . Wrote to CC on progress. + data check |  | 3.5 | 0
JS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates | tracking sheet + weekly meetings table | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-02 | 8586 | 2.8_tests |  | 2.8 | Hotel | Checked precache GTA data | checkded data + relaunched GTA GT + queued L + checked results afterwards |  | 2 | 1
JS | Thursday | 2015-04-02 | 8577 | New |  | 2.7 | Hotel | Cuba extrapolation | Patch for 2.7 : prepare + test |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8554 | Maintenance |  |  | Hotel | Check why RMT update fails on prod after new URL update | reproduce problem + fix + test. + change to remove DTD |  | 2.5 | 0
JS | Thursday | 2015-04-02 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | tests + analysis | 2 | 0 | -1
JS | Thursday | 2015-04-02 | 8309 | New |  | 2.9 | Hotel | Dynamic search EXP | studied RQ document for EXP |  | 1 | 0
JS | Thursday | 2015-04-02 | 8283 | Discussion | internal |  | TUI | Assist PS for updating SD-29142 instance + guide for fix | update + guide |  | 0.5 | 1
JS | Thursday | 2015-04-02 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Thursday | 2015-04-02 | 8093 | 2.8_tests |  | 2.8 | Hotel | Launch SQA test tool |  | 0.25 | 0 | -1
JS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Friday | 2015-04-03 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Changed code for DTD removal + tested on SD. To PS for further tests. Discuss with PS |  | 1.5 | 0
JS | Friday | 2015-04-03 | 8309 | New | Analysis |  | Hotel | Dynamic search EXP | Manual requests + analysis + discussion with DF | 4 | 3.5 | 0
JS | Friday | 2015-04-03 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | XSL change + started DB change |  | 1.25 | 0
JS | Friday | 2015-04-03 |  |  |  |  | Hotel | Merged 2.8 changes to 2.9 |  |  | 1 | 1
JS | Friday | 2015-04-03 |  | Planning | internal | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions |  | 3.5 | 0 | -1
JS | Friday | 2015-04-03 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.5 | 1
JS | Monday | 2015-04-06 |  | Planning | internal |  |  | Weekly planning | tracking sheet + objective status update | 1 | 1 | 0
JS | Monday | 2015-04-06 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | changes SQA + SPR SPs. Yet to implement Match + XSL change. Asked PS for test cases | 2 | 2 | 0
JS | Monday | 2015-04-06 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | updated devcache + GTs + L + mentioned how to check | 1 | 1 | 0
JS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8554 | Maintenance |  | 2.7 | Hotel | Check why RMT update fails on prod after new URL update | Check update files + finalize patch |  | 1.5 | 1
JS | Tuesday | 2015-04-07 | 8085 | New |  | 2.9 | Hotel | CCO for SQA | finish code + Tests | 2 | 4.5 | 1
JS | Tuesday | 2015-04-07 |  | Discussion | internal |  | Hotel | Answer CC questions regarding EXP | EXP update for hotel + checked corrections for booking ref in 2.8 |  | 0.5 | 1
JS | Tuesday | 2015-04-07 | 8309 | New |  |  | Hotel | Dynamic search EXP | Started test tool dev | 3 | 0.5 | 0
JS | Tuesday | 2015-04-07 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Tuesday | 2015-04-07 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Discuss with CC + start implementation | 2.5 | 0 | -1
JS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8654 | 2.8_tests |  | 2.8 | Hotel | EXP CB problem on precache | check + fix + test + patch |  | 3 | 1
JS | Wednesday | 2015-04-08 |  | Planning | internal | Afidium | Hotel | Hotel weekly planning | with DF, CC |  | 0.5 | 1
JS | Wednesday | 2015-04-08 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Wednesday | 2015-04-08 | 8309 | New |  |  | Hotel | Dynamic search EXP | Tool coding |  | 2.5 | 0
JS | Wednesday | 2015-04-08 |  | Discussion | snapin |  | Hotel | Call with Raj + Shubhad for brief on hotel and what to do for 8660 |  |  | 1 | 1
JS | Wednesday | 2015-04-08 | 7688 | New |  | 2.8.1 | Hotel | Farebasis | Implementation + tests | 7.5 | 0 | -1
JS | Wednesday | 2015-04-08 | 8566 | Discussion | internal | 2.8 | Hotel | Dashboard issue | Discussion with everybody + conclude as corner case. To DF for approval of planning for 2.9 |  | 0.5 | 1
JS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-09 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.5 | 1
JS | Thursday | 2015-04-09 | 8309 | New |  |  | Hotel | Dynamic search EXP | code + test + initial measurements | 7.5 | 3.5 | 0
JS | Thursday | 2015-04-09 |  | Analysis | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Analyse + document + call with DF |  | 3.5 | 1
JS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates |  | 0.25 | 0.25 | 1
JS | Friday | 2015-04-10 | 8566 | 2.8_tests | Dashboard |  | Hotel | Dashboard problem | update devcache instance + instructions for test for EM + test later |  | 1.25 | 1
JS | Friday | 2015-04-10 |  | New | Documentation | 2.9 | Hotel | Document galaxyref use cases | http://projets2.afidium.com/projects/wnj-htldb/wiki/Galaxyref_synchronization_use_cases |  | 2 | 0
JS | Friday | 2015-04-10 | 7688 | New |  | 2.9 | Hotel | Farebasis | Brief from CC |  | 0.25 | 1
JS | Friday | 2015-04-10 |  | New | Documentation | 2.9 | Hotel | review 2.9 tasks + list of patches & evolutions | review + list evolutions and patches |  | 2 | 1
JS | Friday | 2015-04-10 |  | Discussion |  | Afidium |  | Daily call |  | 0.25 | 0.25 | 1
JS | Friday | 2015-04-10 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | finalize wiki + discuss with DF + Call with Raj to answer questions, native test utility etc. |  | 2 | 1
JS | Friday | 2015-04-10 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | test + analyse + decide removal of sort + discuss with Anne + change code | 1.5 | 0 | -1
JS | Friday | 2015-04-10 | 8036 | 2.9_tests | galaxyref | 2.9 | Hotel | exchange rate import | test | 0.5 | 0 | -1
JS | Monday | 2015-04-13 | 8166 | Analysis |  | 2.9 | Hotel | Analyse the time measurements done for se_pricePerDay | Analysed time measurement. Decision to remove sort + table very likely. Need measurements before finalizing the proposal. To ST for measurements |  | 0.5 | 1
JS | Monday | 2015-04-13 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Review Raj understanding + answer |  | 0.5 | 1
JS | Monday | 2015-04-13 | 7688 | New | farebasis | 2.8.1 | Hotel | Farebasis | Analysis. Need CC advise for proceeding further |  | 1.5 | 0
JS | Monday | 2015-04-13 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launched tool + scheduled tasks + approach |  | 0.5 | 0
JS | Monday | 2015-04-13 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Added code for common use for CSV generation |  | 2.5 | 0
JS | Monday | 2015-04-13 | 8690 | Maintenance |  | 2.7 | Hotel | JNV Availability update problem | Analysis + decision to wait |  | 0.5 | 1
JS | Monday | 2015-04-13 |  | Planning | internal |  | Hotel | Weekly planning | Weekly planning call with DF, CC |  | 1 | 1
JS | Monday | 2015-04-13 |  | Discussion | internal |  | Hotel | Discussion for dashboard install | With EP, DF. Same server + EP installs + JS configures + with Shubhad + Raj |  | 0.5 | 1
JS | Monday | 2015-04-13 | 8566 | 2.8_tests |  | 2.8 | Hotel | Dashboard issue | graft to stable + update dashboard on preprod + to test team |  | 0.5 | 1
JS | Tuesday | 2015-04-14 |  | New | email |  | Hotel | GTA room id query of CC | Checked XSLs + replied |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8566 | 2.8_tests |  | 2.8 | Hotel | Dashboard issue | discuss with RN + check the issue she talked about. I do not see any problem |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8689 | Discussion | internal | 2.9 | Hotel | Load test replication DBs | Document what it means to check SQA in backend + GTA GT + get JNV city data + discuss with ST UZ |  | 1 | 1
JS | Tuesday | 2015-04-14 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Review Raj understanding + correct + discussions | 1 | 1 | 0
JS | Tuesday | 2015-04-14 |  | Planning | internal |  | Hotel | Tracking sheet for week |  |  | 0.5 | 1
JS | Tuesday | 2015-04-14 | 8047 | Analysis |  |  | Hotel | EXP hotels with missing information | Check response : status code |  | 0.5 | 1
JS | Tuesday | 2015-04-14 |  | Discussion | internal | 2.9 | Hotel | Call with Emilise for transaction code | Understand uAPI implementation from EP | 0.5 | 0 | -1
JS | Tuesday | 2015-04-14 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | finish code + Tests | 4 | 4 | 0
JS | Tuesday | 2015-04-14 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | Start implementation | 1 | 0 | -1
JS | Tuesday | 2015-04-14 |  | Analysis | HtlProduct |  | Hotel | TravelCo | read about travelco | 1 | 0 | -1
JS | Tuesday | 2015-04-14 |  | Planning | internal | Afidium |  | Daily update call |  |  | 0.5 | 1
JS | Wednesday | 2015-04-15 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | code | 4 | 0 | -1 | half day
JS | Wednesday | 2015-04-15 |  | New | email |  | Hotel | EXP empty rate detail problem | Analyse attachments + Provide example to CC |  | 1 | 1
JS | Wednesday | 2015-04-15 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | rate detail code change + measurements |  | 3 | 0
JS | Thursday | 2015-04-16 | 7866 | New | farebasis | 2.9 | Hotel | Farebasis | code + test + finish | 4 | 0 | -1 | LEAVE
JS | Thursday | 2015-04-16 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launched SQA tool + checked some response + update tasks | 2 | 0.5 | 1
JS | Thursday | 2015-04-16 |  | Analysis | HtlProduct |  | Hotel | TravelCo | analysis + queries + first contact | 2 | 0 | -1
JS | Thursday | 2015-04-16 |  | Release |  | 2.8 | Hotel | Update prod FTP files + SVN dir | mail to CC about it |  | 0.5 | 1
JS | Thursday | 2015-04-16 | [5 empty] | Task creation for se_availability__update + check other tasks |  |  | 0.25 | 1
JS | Friday | 2015-04-17 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | Call with Raj + discussions | 1 | 0.5 | 0
JS | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25 | 0.25 | 1
JS | Friday | 2015-04-17 | 8309 | New | DynamicSearch | 2.9 | Hotel | Expedia dynamic search tests | Measured time for XSL + margine engine + document margine engine proposal |  | 3 | 1
JS | Friday | 2015-04-17 |  | Analysis |  |  | Hotel | Transaction context code analysis | Call with EP for uAPI | 3 | 0.25 | 0
JS | Friday | 2015-04-17 |  | Planning | internal |  | Hotel | Next week objectives discussion + feedback on EXP dynamic search | Call with DF |  | 0.5 | 1
JS | Friday | 2015-04-17 |  | Analysis | HtlProduct |  | Hotel | TravelCo | First contact travelco, go west, cali-fun + checked teamamerica documentation | 2 | 1 | 0
JS | Friday | 2015-04-17 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | Checked DB does not need change + started checking XSL |  | 1 | 0
JS | Friday | 2015-04-17 |  | Planning | internal | Afidium |  | Daily call |  |  | 0.5 | 1
JS | Friday | 2015-04-17 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Load test batches + analysis | 2 | 0 | -1
JS | Friday | 2015-04-17 | 7639 | New | Replication | 2.9 | Hotel | Replication | Checked ST response + replied |  | 0.25 | 1
JS | Friday | 2015-04-17 | 8244 | Maintenance |  | 2.7 | Hotel | JNV reports 0 count in mail | Checked + described |  | 0.5 | 1
JS | Monday | 2015-04-20 |  | Planning | internal |  |  | Tracking sheet for week |  | 1 | 1 | 1
JS | Monday | 2015-04-20 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | update specs to extract data in XSL + review Raj;s code + discussions | 2 | 1 | 0
JS | Monday | 2015-04-20 |  | New | DynamicSearch | 2.9 | Hotel | Bonotel dynamic search | Analysis + specification | 4 | 4 | 1
JS | Monday | 2015-04-20 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launch SQA test tool + monitor | 0.5 | 0.5 | 1
JS | Monday | 2015-04-20 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | start coding : SQA RS | 0.5
JS | Tuesday | 2015-04-21 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25
JS | Tuesday | 2015-04-21 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj | 1
JS | Tuesday | 2015-04-21 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | code + test : SQA, GQA . Code CB + test in oxygen | 6.75
JS | Wednesday | 2015-04-22 |  | Planning | internal |  |  | Daily updates | tracking sheet | 0.25
JS | Wednesday | 2015-04-22 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj + code review | 0.75
JS | Wednesday | 2015-04-22 | 7866 | New | farebasis | 2.8.1 | Hotel | Farebasis | documentation of implementation | 1.5
JS | Wednesday | 2015-04-22 | 8689 | New | Replication | 2.9 | Hotel | Load test replication DBs | Launch SQA test tool + monitor | 0.5
JS | Wednesday | 2015-04-22 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Add code to measure extraction with XSL. Test possible scenarios. Time comparison with DB SQAs | 5
JS | Thursday | 2015-04-23 | 8309 | New | DynamicSearch | 2.9 | Hotel | EXP dynamic search | Finish time measurements + document | 3 |  |  | half day
JS | Thursday | 2015-04-23 |  | Analysis | HtlProduct |  | Hotel | Team america analysis | Start analysis | 1
JS | Friday | 2015-04-24 |  | Analysis | HtlProduct |  | Hotel | Team america analysis | analysis + documentation + mail | 4
JS | Friday | 2015-04-24 |  | Analysis |  | 2.9 | Hotel | Transaction context code analysis | analysis + documentation | 3
JS | Friday | 2015-04-24 | 8675 | New | DynamicSearch | 2.9 | Hotel | GTA dynamic search | follow up + discussion with Raj + code review | 1
PS | Wednesday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.5 | 1 | Leaves 2015-04-08 to 2015-04-12 2015-05-01
PS | Wednesday | 2015-04-01 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 1 | 1 | 1
PS | Wednesday | 2015-04-01 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-01 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schema | based on CC's suggestion | 3 | 0 | -1
PS | Wednesday | 2015-04-01 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | read doc + xsl + questions and problems to CC + test | 2 | 5 | 0
PS | Wednesday | 2015-04-01 | 8238 | New |  |  | TUI | [SQA] - Enhancement in the Amadeus transaction | correction of an issue with CC + test |  | 1 | 1
PS | Thursday | 2015-04-02 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-02 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet + venda report | 0.5 | 1 | 1
PS | Thursday | 2015-04-02 |  | Discussion | snapin |  |  | discussions + support for snapin | MM + SK | 1.5 | 1 | 1
PS | Thursday | 2015-04-02 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add service Insurance | Done + remaining listed in task | 3 | 2.5 | 0
PS | Thursday | 2015-04-02 | 8283 | New |  |  | TUI | Addition of parend log in Response | Checked Issue + corrections C# + test + problems on my computer | 3 | 3 | 1
PS | Friday | 2015-04-03 |  | Maintenance |  |  | Hotel | Production COT | Mails+ Reply | 0.25 | 0.25 | 1
PS | Friday | 2015-04-03 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC | 0.5 | 1.5 | 1
PS | Friday | 2015-04-03 |  | Discussion | snapin |  |  | discussions + support for snapin | Feedback to Raj for mail | 1.5 | 0.5 | 1
PS | Friday | 2015-04-03 | 8580 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Complete RNC schemas according to the documentation Update |  | 3 | 3 | 1
PS | Friday | 2015-04-03 | 8554 | New |  |  | Hotel | RMT failed on production | Loads + analysis | 3 | 3 | 1
PS | Monday | 2015-04-01 |  | Maintenance |  |  | Hotel | Production COT | Mails | 0.25 | 0.25 | 1
PS | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates + discussions | Uma : some testcases to her | 1 | 0.5 | 1
PS | Monday | 2015-04-06 |  | Discussion | snapin |  |  | discussions + support for snapin | SK + Raj + MM | 1.5 | 0.5 | 1
PS | Monday | 2015-04-06 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency |  | 2 | 2 | 1
PS | Monday | 2015-04-06 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Remaing : questins with CC + 3rd step | 4 | 2.75 | 0
PS | Monday | 2015-04-06 | 8581 | New |  |  | Hotel | RMT failed on production |  | 2 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Maintenance |  |  | Hotel | Production COT | Prod Mail | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-07 |  | Planning | internal |  |  | Daily updates + discussions | JS+CC + tracking sheet+ ST (2.8_rep tests) | 1 | 2 | 1
PS | Tuesday | 2015-04-07 |  | Discussion | snapin |  |  | discussions + support for snapin | Raj + SK + RN | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8554 | New |  |  | Hotel | RMT failed on production | Some testcases to execute | 1 | 1 | 1
PS | Tuesday | 2015-04-07 | 8085 | New |  |  | Hotel | [Point Projet 28 Janvier] - Convert when required Cache output from EUR to vendor currency | Testcases correction | 0.5 | 1.5 | 1
PS | Tuesday | 2015-04-07 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | questions with CC + proceed, not finished | 2 | 1.5 | 0
PS | Tuesday | 2015-04-07 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add Service/Insurance segments, seat assignment and insurance booking in Bookings | Output to CC for verification + question | 2.25 | 0.75 | 0
PS | Wednesday | 2015-04-08 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-08 |  | Planning | internal |  |  | Daily updates + discussions | Uma + JS + ST | 0.5 | 1 | 1
PS | Wednesday | 2015-04-08 |  | Discussion | snapin |  |  | discussions + support for snapin | RN + MM : call | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-08 | 8566 | New |  |  | Hotel | dashboard data mismatch on different machines | ST+JS+MM+RN : call over issue investigation |  | 1.5 | 1
PS | Wednesday | 2015-04-08 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Finished with CC + test in oxygen + discussion with CC | 5 | 3 | 0
PS | Wednesday | 2015-04-08 | 8661 |  |  |  | Hotel | Cache Currency 2.9 | Started preparing testgrid + testcases for tests |  | 1.75 | 0
PS | Thursday | 2015-04-09 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet | 0.5 | 0.5 | 1
PS | Thursday | 2015-04-09 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.25 | 1
PS | Thursday | 2015-04-09 | 8661 | 2.9_tests |  | 2.9 | Hotel | Cache Currency 2.9 | SPR SQA K and Testgrid Done + few SQA F remaining | 5 | 4.5 | 0
PS | Thursday | 2015-04-09 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Work with CC + 3 xsls prepared + test | 2 | 2.5 | 0
PS | Friday | 2015-04-10 |  | Maintenance |  |  | Hotel | Production COT | Prod status + mail + data for ST in mail | 0.25 | 0.75 | 1
PS | Friday | 2015-04-10 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 0.5 | 1 | 1
PS | Friday | 2015-04-10 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.5 | 1
PS | Friday | 2015-04-10 | 8678 |  |  |  | TUI | Issue Ticket: make possible the issuance of EMDs | 6 xsls + test | 2 | 2 | 1
PS | Friday | 2015-04-10 | 6830 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Xsl prepared plus tested plus questions with CC | 5 | 3.5 | 1
PS | Monday | 2015-04-13 |  | Maintenance |  |  | Hotel | Production COT | Mails + task creation(#8690) | 0.25 | 0.25 | 1
PS | Monday | 2015-04-13 |  | Planning | internal |  |  | Daily updates + discussions | Prod issue with JS | 0.5 | 0.5 | 1
PS | Monday | 2015-04-13 |  | Discussion | snapin |  |  | discussions + support for snapin | Support RN | 0.5 | 0.5 | 1
PS | Monday | 2015-04-13 | 8680 | New |  |  | TUI | [Search AddOn] - Update Insurance Segment | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8682 | New |  |  | TUI | Update Booking - Addition of insurance in the booking | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8684 | New |  |  | TUI | [CB/GB/UB] - Properly parse EMD ticket in responses | Questions and confirmations with CC | 2 | 2 | 1
PS | Monday | 2015-04-13 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Questions and confirmations with CC | 2 | 1 | 1
PS | Tuesday | 2015-04-14 |  | Maintenance |  |  | Hotel | Production COT | Prod Mail | 0.25 | 0.25 | 1
PS | Tuesday | 2015-04-14 |  | Planning | internal |  |  | Daily updates + discussions | Tracking Sheet + JS + ST | 1 | 1 | 1
PS | Tuesday | 2015-04-14 |  | Discussion | snapin |  |  | discussions + support for snapin | RN regarding #8566 | 1 | 1 | 1
PS | Tuesday | 2015-04-14 | 8691 | New |  |  | TUI | Test Scenarios | Preparations + questions with CC / only started | 4 | 1 | 0
PS | Tuesday | 2015-04-14 | 8581 | New |  |  | TUI | [GB: Ancillary Services/Insurances] - Add Service/Insurance segments, seat assignment and insurance booking in Bookings | Xsl new changes + co-ordination with CC | 2 | 3.25 | 1
PS | Tuesday | 2015-04-14 | 8678 | New |  |  | TUI | Issue Ticket: make possible the issuance of EMDs | Changes as per CC |  | 1 | 1
PS | Tuesday | 2015-04-14 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Some more changes |  | 1.5 | 1
PS | Wednesday | 2015-04-15 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Wednesday | 2015-04-15 |  | Planning | internal |  |  | Daily updates + discussions | JS + TS + CC + Tracking sheet | 0.5 | 0.5 | 1
PS | Wednesday | 2015-04-15 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1.5 | 0.5 | 1
PS | Wednesday | 2015-04-15 | 8691 | New |  |  | TUI | Test Scenarios | Tests + issues + corrections + co-ordination with CC | 1 | 6.75 | 0
PS | Thursday | 2015-04-16 |  | Maintenance |  |  | Hotel | Production COT | Prod status + mail | 0.25 | 0.5 | 1
PS | Thursday | 2015-04-16 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet | 0.5 | 0 | -1
PS | Thursday | 2015-04-16 |  | Discussion | snapin |  |  | discussions + support for snapin | MM | 1 | 0.25 | 1
PS | Thursday | 2015-04-16 | 8661 |  |  |  | Hotel | Cache Currency 2.9 | Finish | 4 | 0 | -1
PS | Thursday | 2015-04-16 | 8691 | New |  |  | TUI | Test Scenarios | Tests with CC and issues | 2.25 | 7.25 | 0
PS | Friday | 2015-04-17 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25 | 0.25 | 1
PS | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 1 | 0.5 | 1
PS | Friday | 2015-04-17 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1 | 0 | -1
PS | Friday | 2015-04-17 | 8691 | New |  |  | TUI | Test Scenarios | If anything to test | 2 | 6.75 | 1
PS | Friday | 2015-04-17 | 8630 | New |  |  | TUI | Update Booking - Addition of ancillary services in a booking | Xsl prepared plus tested plus questions with CC | 3.75 | 0.5 | 1
PS | Monday | 2015-04-20 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Monday | 2015-04-20 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet | 1
PS | Monday | 2015-04-20 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 0.5
PS | Monday | 2015-04-20 | 8733 | New |  |  | TUI | Enrichissement de la récupération de dossier |  | 2
PS | Monday | 2015-04-20 | 8741 | New |  |  | TUI | [GQA] - Implement Insurance_Pricing xsls |  | 2
PS | Monday | 2015-04-20 | 8732 | New |  |  | Hotel | Farebasis: Update RNC schemas |  | 2.25
PS | Tuesday | 2015-04-21 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Tuesday | 2015-04-21 |  | Planning | internal |  |  | Daily updates + discussions |  | 1
PS | Tuesday | 2015-04-21 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Tuesday | 2015-04-21 | 8740 | New |  |  | TUI | [RNC] - CB/GB/UB |  | 5.75
PS | Wednesday | 2015-04-22 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Wednesday | 2015-04-22 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Wednesday | 2015-04-22 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Wednesday | 2015-04-22 | 8740 | New |  |  | TUI | [RNC] - CB/GB/UB | Finish | 2
PS | Wednesday | 2015-04-22 | 8728 | New |  |  | TUI | Implement standard booking flow XSL | Read and start + questions | 4.25
PS | Thursday | 2015-04-23 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Thursday | 2015-04-23 |  | Planning | internal |  |  | Daily updates + discussions |  | 0.5
PS | Thursday | 2015-04-23 |  | Discussion | snapin |  |  | discussions + support for snapin |  | 1
PS | Thursday | 2015-04-23 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 6.25
PS | Friday | 2015-04-24 |  | Maintenance |  |  | Hotel | Production COT |  | 0.25
PS | Friday | 2015-04-24 |  | Planning | internal |  |  | Daily updates + discussions | JS + tracking sheet + ST | 1
PS | Friday | 2015-04-24 |  | Discussion | snapin |  |  | discussions + support for snapin | RN | 1
PS | Friday | 2015-04-24 | 8728 | New |  |  | TUI | Implement standard booking flow XSL |  | 5.75
ST | Thursday | 2015-04-02 | [5 empty] | Leave |  |  |  |  | Leaves 2015-03-30 to 2015-04-05 2015-05-01
ST | Friday | 2015-04-03 | [5 empty] | Leave
ST | Monday | 2015-04-06 |  | Discussion | internal |  | Stock | Discussion with Uma | Discussion about this week's plan, 8619, 8395, Hotel new server | 1 | 1.4 | 1
ST | Monday | 2015-04-06 | 8187 | New | server setup | 2.8 | Hotel | 2.8 New server DB : Updates Issues | Apply the recent installation script, executed post processing manually | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8188 | New | server setup | 2.9 | Hotel | 2.9 New server DB : Updates Issues | Correct the synonyms | 0.5 | 0.5 | 1
ST | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Checked the GQA script and suggested UZ to take help of PS and run some sqa, spr and gqa valid queries |  | 0.4 | 1
ST | Monday | 2015-04-06 | 8244 | Maintenance |  | 2.8 | Hotel | Mail shows 0 room updated for JNV | check and updated task with details |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | New | server setup |  |  | Setup of sql server for Rajendra | Setup Raj id on sd-29142 and checked his access problem |  | 0.4 | 1
ST | Monday | 2015-04-06 |  | Planning | internal |  |  | Daily updates and discussion | tracking sheet and weekly task | 0.25 | 0.4 | 1
ST | Tuesday | 2015-04-07 | 8636 | Maintenance |  | 2.8 | Hotel | sp_checkIndex need correction for 2.8 | Analysis and testing and task updated | 1 | 0.5 | 0
ST | Tuesday | 2015-04-07 | 8637 | New |  |  | Hotel | Create 2.9 DB without galaxyref | guide uma | 0.5 | 0 | -1
ST | Tuesday | 2015-04-07 | 8575 | 2.8_tests |  | 2.8 | Hotel | Check se_versioned_tarif cleanup | Analysis and testing and task updated | 1 | 2 | 1
ST | Tuesday | 2015-04-07 | 8619 | New |  | 1.1 | Stock | Change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Analysis, discussion and proposal | 1.25 | 1 | 1
ST | Tuesday | 2015-04-07 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Testing of SQA, GQA and SPR on 2.8_rep database |  | 0.5 | 1
ST | Wednesday | 2015-04-08 | 8619 | New | internal | 1.1 | Stock | Change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | discussion with Uma and guide her and task updated with final plan | 0.25 | 0.5 | 0
ST | Wednesday | 2015-04-08 | 8634 | New |  | 1.1 | Stock | Refresh Materialized View vdi_airport | Analysis, discussion and guide, code, wiki review | 1 | 0.5 | 1
ST | Wednesday | 2015-04-08 | 8566 | 2.8_tests | Dashboard | 2.8 | Hotel | dashboard data mismatch on different machines | Testing, discussion | 2 | 2 | 1
ST | Thursday | 2015-04-09 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet and new server setup of galaxyref and ref_afidium, discussion with PS for devcache update check | 0.25 | 0.75 | 1
ST | Thursday | 2015-04-09 | 8636 | Maintenance |  | 2.8 | Hotel | sp_checkIndex need correction for 2.8 | Task updated with the details |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8480 | New |  | 1.1 | Stock | Update PNR (Passive Booking) on booking | Code and wiki review and testing |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8493 | New |  | 1.1 | Stock | Corrections related to external booking references | Code and wiki review and testing |  | 0.5 | 1
ST | Thursday | 2015-04-09 | 8395 | New |  | 1.1 | Stock | Improve stats speed | Analysis, prposed tests and changes |  | 0.5 | 0
ST | Thursday | 2015-04-09 | 8666 | New |  | 1.2 | Stock | Update SP Bkg_booking_get | Analysis and Discussion |  | 0.75 | 1
ST | Thursday | 2015-04-09 | 8612 | New |  | 1.1 | Stock | bkg_booking__get implementation NOK | Analysis and task updated |  | 0.5 | 0
ST | Friday | 2015-04-10 | 8272 | New | Replication | 2.9 | Hotel | Test data in replication server and execute Search | Testing of SQA, GQA and SPR on 2.8_rep database , done data check | 0.6 | 0 | -1
ST | Friday | 2015-04-10 | 8493 | New |  | 1.1 | Stock | Corrections related to external booking references | wiki reviewed and confirmed | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7639 | New | Replication |  | Hotel | setup of replication activity | Checked SPR, SQA , GQA, corrected ref_Afidium problem , task updated with details. | 2 | 2 | 1
ST | Friday | 2015-04-10 | 8636 | Maintenance |  | 2.8.1 | Hotel | sp_checkIndex need correction for 2.8 | Task updated, installation script created | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7079 | New |  | 2.8 | Hotel | Dashboar_2.8 : Data Checking | assigned to PS and discussed with her | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 7337 | Documentation |  |  | Hotel | Update documentation for dashboard and update SPs | reviewed wiki and close the task | 0.4 | 0.4 | 1
ST | Friday | 2015-04-10 | 4776 | Documentation |  |  | Hotel | [TABLE] : document the tables of the search engine | reviewed wiki and close the task | 0.4 | 0.4 | 1
ST | Monday | 2015-04-13 | 8651 | Development |  | 1.2 | Stock | [db] add information in db to handle additional booking features | Analysis, Discussion with DF and task updated | 2.5 | 2.5 | 0
ST | Monday | 2015-04-13 | 8619 |  |  |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Guide Uma for coding , coordinated with AR for testing | 1 | 1 | 0
ST | Monday | 2015-04-13 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, #7639, #8604 | 0.5 | 0.5 | 1
ST | Tuesday | 2015-04-14 | 8689 | New | Replication | 2.9 | Hotel | Load Replication server with SQA | Discussion with JS, test, discussion with Uma | 1.5 | 1.5 | 1
ST | Tuesday | 2015-04-14 | 7639 | New | Replication |  | Hotel | setup of replication activity | Check VDM synchro issue, and started complete VDM synchro, got error in full and focussed synchro both | 0.5 | 0.5 | 0
ST | Tuesday | 2015-04-14 | 8619 |  |  | 1.1 | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Code review and wiki review and testing | 1.5 | 1.5 | 1
ST | Wednesday | 2015-04-15 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet for the week | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 8709 |  |  | 1.1 | Stock | bbkg_booking__replace booking selection is NOK | coding, testing | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 8376 | Development |  | 3.6 | AIR | Routine AIR DB Cleanup | Code review and wiki review and testing | 1.5
ST | Wednesday | 2015-04-15 | 8711 |  |  | 1.1 | Stock | bkg_booking__replace not work anymore | coding, testing | 0.5 | 0.5 | 1
ST | Wednesday | 2015-04-15 | 7639 | New | Replication |  | Hotel | setup of replication activity | Resolve vdm synchro issue and test full day updates with replication | 1 | 1 | 1
ST | Thursday | 2015-04-16 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, prod update check, coordinated with Uma for diff tasks | 0.5 | 0.75 | 1
ST | Thursday | 2015-04-16 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Changes applied in database 2.8 and task updated with plan |  | 0.5 | 0
ST | Thursday | 2015-04-16 | 7639 | New | Replication | 2.9 | Hotel | setup of replication activity | Executed VDM update successfully, checked replication setup for verification as SQA was timeout of rep database |  | 0.75 | 0
ST | Thursday | 2015-04-16 | 8272 | Maintenance |  | 1.1 | Stock | Fiw installation script to NOT delete existing users from sto_auth_assignement table | Understanding, Analysis, coding and testing, discussion |  | 1.5 | 1
ST | Thursday | 2015-04-16 | 8722 | Maintenance |  | 1.1 | Stock | [Booking] Wrong total cost amount when created with Replace in post | Analysis, discussion, coding and testing |  | 0.5 | 1
ST | Thursday | 2015-04-16 | 8442 | Development |  | 1.2 | Stock | [Query][DB] Create table and SPs for SearchQuery | wiki and code review and tests | 2.5 | 0 | -1
ST | Thursday | 2015-04-16 | 8166 | New |  | 2.9 | Hotel | Time Measurrement | Test data from Database | 1 | 0 | -1
ST | Friday | 2015-04-17 |  | Planning | internal |  |  | Daily updates + discussions | Tracking sheet, discussion with Uma for 2.9_refafidium Db, daily check | 0.5 | 0.4 | 1
ST | Friday | 2015-04-17 | 8623 | Development |  | 1.2 | Stock | tables.inc.pgsql rules not respected + | Review the code and wiki and tests | 2 | 0 | -1
ST | Friday | 2015-04-17 | 8166 | New |  | 2.9 | Hotel | Time Measurrement | Analysis and testing and task updation | 1.5 | 1 | 1
ST | Friday | 2015-04-17 | 8187 | New | server setup | 2.8 | Hotel | 2.8 New server DB : Updates Issues | Task updated with the details, checked 2.8 DB updates, tried to find the issue |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8625 | New |  | 1.2 | Stock | enrich dictionary | Analysis and task updated |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8727 | Maintenance |  | 1.1 | Stock | Fiw installation script to NOT delete existing users from sto_auth_assignement table | Applied changes in 1.2 and discussion with Ar |  | 0.4 | 1
ST | Friday | 2015-04-17 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | Execute Hotel synchro and checked in all DBs |  | 0.4 | 1
ST | Monday | 2015-04-20 |  | Planning | internal |  |  | Planning for whole DB team | Check the diff task of DB with DB team, create some planned task, assign to related person
ST | Monday | 2015-04-20 | 8651 | Discussion | internal | 1.2 | Stock | [db] add information in db to handle additional booking features | Discussion with SP to explain the req and changes
ST | Monday | 2015-04-20 | 8187 | 2.8_tests |  | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the updates and related checks on new server
ST | Monday | 2015-04-20 | 8376 | New |  | 3.2 | AIR | Routine air DB Clean up | Code review and testing
ST | Tuesday | 2015-04-21 | 8442 | New |  | 1.2 | Stock | [Query][DB] Create table and SPs for SearchQuery | Code review and testing
ST | Tuesday | 2015-04-21 | 7639 | New | Replication | 2.9 | Hotel | Setup of Replication Activity | Check the SQA problem and why the server is slow
ST | Wednesday | 2015-04-22 | 8249 | New |  | 1.2 | Stock | [PGSQL] Check All core_modules Tables | Review the req and code and test
ST | Wednesday | 2015-04-22 | 8623 | New |  | 1.2 | Stock | tables.inc.pgsql rules not respected + | Review the req and code and test
ST | Thursday | 2015-04-23 | 7768 | New |  | 2.9 | Hotel | Modify extrapolation procedure - limit end date | Testing
ST | Thursday | 2015-04-23 | 8553 | New |  | 2.9 | Hotel | GQA should generate and error | Review the req and code and test
ST | Thursday | 2015-04-23 |  | Review | internal |  |  | Review the work done by diff DB team member
ST | Thursday | 2015-04-23 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | Review the req and code and test
ST | Friday | 2015-04-24 |  | Discussion | internal |  |  | Discussion with Sp for sto_journey SPs
ST | Friday | 2015-04-24 |  | Planning | internal |  |  | Planning for whole DB team
ST | Friday | 2015-04-24 |  | Review | internal |  |  | Review the work done by diff DB team member
UZ | Wednesday | 2015-04-01 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 1 | 0.5 | 1 | Leaves 2015-05-01 2015-05-02 - 2015-05-10
UZ | Wednesday | 2015-04-01 | 8187 |  |  | 2.8 | Hotel | Sd-2.8 New server DB: Updates issues | checked updated on new server |  | 0.25 | 1
UZ | Wednesday | 2015-04-01 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | Modified SP + testing | 1 | 1.25 | 0
UZ | Wednesday | 2015-04-01 | 8528 | New | pgsql |  | Stock | improve location management | modified view + created SP + testing | 4 | 4 | 1
UZ | Thursday | 2015-04-02 | 8272 |  |  |  | Hotel | test data in replication server & execute search | data validation | 1 | 0.5 | 1
UZ | Thursday | 2015-04-02 | 7639 | New | Replication |  | Hotel | setup of replication activity | check for indexes are present or not on new server |  | 0.25 | 1
UZ | Thursday | 2015-04-02 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | added column in table + Modified SP |  | 1.25 | 0
UZ | Thursday | 2015-04-02 | 8604 | New | pgsql |  | Stock | create a SP to return external references for given booking | created SP + testing + coordinate with SS (to help him) |  | 2.5 | 1
UZ | Thursday | 2015-04-02 | 8493 | New | pgsql |  | Stock | corrections related to external booking references | testing + update task |  | 1.25 | 1
UZ | Friday | 2015-04-03 | 8272 |  |  |  | Hotel | test data in replication server & execute search | testing + update task | 1 | 1 | 1
UZ | Friday | 2015-04-03 | 8605 | New | pgsql |  | Stock | add a column to bkg_booking_external + propagate in diff SPs | Modified SP + testing | 1 | 1.5 | 1
UZ | Friday | 2015-04-03 | 8619 | New | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | analysis | 4 | 1.75 | 0
UZ | Friday | 2015-04-03 | 8637 | New | pgsql |  | Stock | modify sys function | discuss with ST + update task |  | 0.25 | 1
UZ | Friday | 2015-04-03 |  | Planning | internal |  |  | discuss with ST | call with ST for Planning + work status |  | 0.5 | 1
UZ | Friday | 2015-04-03 | 8460 | New |  |  | Stock | booking + winter | correct daigram |  | 1 | 1
UZ | Monday | 2015-04-06 | 8188 | New | Replication | 2.9 | Hotel | 2.9 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.5 | 1
UZ | Monday | 2015-04-06 | 8187 | New | Replication | 2.8 | Hotel | Sd- 2.8 New server DB : Updates Issues | checked update issues+ updated task | 0.25 | 0.25 | 1
UZ | Monday | 2015-04-06 | 8272 | New | Replication | 2.9 | Hotel | test data in replication server & execute search | data validation + created wiki + updated task | 1 | 1 | 1
UZ | Monday | 2015-04-06 | 8619 | New |  | 1.1 | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | discuss with ST + update task | 1 | 1 | 0
UZ | Monday | 2015-04-06 | 8395 | New |  | 1.1 | Stock | Improve stats speed | Discuss with ST, testing, updated task | 1 | 1.25 | 0
UZ | Monday | 2015-04-06 | 8528 | New | Documentation | 1.1 | Stock | improve location management | Created wiki for view & SP | 1.5 | 1.5 | 1
UZ | Monday | 2015-04-06 |  | Planning | internal |  |  | discuss with ST | call with ST for work planning | 0.5 | 0.5 | 1
UZ | Tuesday | 2015-04-07 | 8272 |  |  |  | Hotel | test data in replication server & execute search | tested data + excuted search + updated task | 0.5 | 0.75 | 1
UZ | Tuesday | 2015-04-07 | 8188 |  |  |  | Hotel | Sd-2.9 New server DB : Updates Issues | checked updates | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | checked updates + updated task | 0.25 | 0.25 | 1
UZ | Tuesday | 2015-04-07 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | call with ST + analysis + planning | 2.5 | 2.5 | 0
UZ | Tuesday | 2015-04-07 | 8567 |  | pgsql |  | Stock | Add error message into SP sto_quotation__search if quotation search doesn't return any results | discuss with YT and coding and testing | 1 | 1 | 1
UZ | Tuesday | 2015-04-07 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport | Analysis+praposal | 1.5 | 1 | 0
UZ | Tuesday | 2015-04-07 |  |  | internal |  |  | fill up tracking sheet |  |  | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8272 |  |  |  | Hotel | test data in replication server & execute search |  | 0.25 | 0.75 | 1
UZ | Wednesday | 2015-04-08 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task | 0.25 | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task | 0.25 | 0.25 | 1
UZ | Wednesday | 2015-04-08 | 8651 |  |  |  | Stock | [db] add information in db to handle additional booking features | analysis |  | 0.5 | 0
UZ | Wednesday | 2015-04-08 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions |  | 4 | 1.25 | 0
UZ | Wednesday | 2015-04-08 | 8634 |  | pgsql |  | Stock | Refresh Materialized view vdi_airport |  | 1 | 3 | 1
UZ | Thursday | 2015-04-09 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8250 |  | pgsql |  | Stock | LogManagerFS : convert code from sql to pgsql | Coordinate with Dhanesh and help him to finish it |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8249 |  | pgsql |  | Stock | [PGSQL] Check All core_modules Tables | Coordinate with Dhanesh and help him to finish it |  | 0 | -1
UZ | Thursday | 2015-04-09 | 8197 |  | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Analysis and Discussion |  | 0 | -1
UZ | Friday | 2015-04-10 | 8188 |  |  |  | Hotel | Sd- 2.9 New server DB : Updates Issues | Check the status and update task | 0.25 | 0 | -1
UZ | Friday | 2015-04-10 | 8187 |  |  |  | Hotel | Sd- 2.8 New server DB : Updates Issues | Check the status and update task | 0.25 | 0 | -1
UZ | Friday | 2015-04-10 | 8272 |  |  |  | Hotel | test data in replication server & execute search | Tests the data and update in task | 0.5 | 0.5 | 1
UZ | Friday | 2015-04-10 | 8187 | New | pgsql |  | Stock | [QUOTATION] Cleanup sto_tariff functions and related | Coding and testing | 4 | 0 | -1
UZ | Friday | 2015-04-10 | 8629 | New | pgsql |  | Stock | document bkg_booking__replace | Documentation | 1 | 0 | -1
UZ | Friday | 2015-04-10 | 8395 | New | pgsql |  | Stock | Improve stats speed | discussion with ST Modify+test + update |  | 3 | 1
UZ | Friday | 2015-04-10 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | Discussion with ST + Created DB |  | 2 | 0
UZ | Friday | 2015-04-10 |  | Planning | internal |  |  | discuss with ST | call with ST for work planning |  | 0.5 | 1
UZ | Monday | 2015-04-13 | 8619 |  | pgsql |  | Stock | change bkg_booking__replace so that a winter booking will keep its bbkg_id_booking during its evolutions | Discussion with ST,AR+ Modified SP, created table+SP, documentation, testing | 6 | 6 | 1
UZ | Monday | 2015-04-13 | 8604 |  | pgsql |  | Stock | Create a SP to return external references for given booking | Modified SP + testing + documentation |  | 1 | 1
UZ | Tuesday | 2015-04-14 | 8637 |  |  |  | Hotel | Create DB 2.9 without galaxyref | added SPs, checked SPs with 2.8, updated task | 2.5 | 3 | 1
UZ | Tuesday | 2015-04-14 | 8689 |  |  |  | Hotel | Load replication server with SQA | discussion with JS, call with ST, understanding, test | 3.5 | 3 | 0
UZ | Wednesday | 2015-04-15 | 8689 |  |  |  | Hotel | Load replication server with SQA | checked for loads | 0.5 | 0.25 | 1
UZ | Wednesday | 2015-04-15 | 7639 |  |  |  | Hotel | setup of replication activity | tested data on replication DB | 0.75 | 0.75 | 1
UZ | Wednesday | 2015-04-15 | 8651 |  |  |  | Stock | [db] add information in db to handle additional booking features | documentation | 5 | 6 | 0
UZ | Thursday | 2015-04-16 | 8689 |  |  |  | Hotel | Load replication server with SQA | checked for loads + testing | 2 | 2 | 1
UZ | Thursday | 2015-04-16 | 8719 |  |  |  | Hotel | change se_availability__update | Modified SP + testing | 1 | 1 | 1
UZ | Thursday | 2015-04-16 | 8729 |  | pgsql |  | Stock | bkg_booking__get with new traveller and | documentation + modified SP | 3 | 3 | 0
UZ | Friday | 2015-04-17 | 8729 |  | pgsql |  | Stock | bkg_booking__get with new traveller and | Discussion with ST +documentation + modified SP + testing | 2 | 2 | 1
UZ | Friday | 2015-04-17 | 8651 |  | pgsql |  | Stock | [db] add information in db to handle additional booking features | Discussion with ST +Documentation + testing SPs | 4 | 4.5 | 1
UZ | Friday | 2015-04-17 | 8637 |  |  |  | Hotel | Create DB 2.9 without galaxyref | Inserted data in DB |  | 0.75 | 0
UZ | Monday | 2015-04-20 | 8729 | New | Documentation | 1.2 | Stock | bkg_booking__get with new Info | Update the ticket with what u had done and assign to shilpa for completion of wiki. Also guide Shilpa for testing SPs related to 8651.
UZ | Monday | 2015-04-20 | 7639 | 2.9_tests | Replication | 2.9 | Hotel | Setup of Replication Activity | Test VDm data in 2.8 Db against the wiki mentioned in task
UZ | Monday | 2015-04-20 | 8637 | New |  | 2.9 | Hotel | Create DB 2.9 without galaxyref | complete the remaining things and close the task
UZ | Monday | 2015-04-20 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Test SQA output
UZ | Tuesday | 2015-04-21 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Test SQA output
UZ | Tuesday | 2015-04-21 | 8553 | New |  | 2.9 | Hotel | GQA should generate and error | Analysis, coding, testing and doc
UZ | Tuesday | 2015-04-21 | 8719 | New |  | 2.8 | Hotel | Change se_availability__update | create the checklist wiki for this
UZ | Wednesday | 2015-04-22 | 8689 | 2.9_tests | Replication | 2.9 | Hotel | Load Replication server with SQA | Test SQA output
UZ | Wednesday | 2015-04-22 |  | Review | Documentation |  | Hotel | Close the documentation tasks -- Hotel
UZ | Wednesday | 2015-04-22 | 8427 | New |  | 2.9 | Hotel | Automation of Hotel and VDM Snchro Tests | complete the remaining things and close the task
UZ | Thursday | 2015-04-23 | 8612 | New |  | 1.2 | Stock | bkg_booking__get implementation NOK | Analysis, coding, testing and doc
UZ | Thursday | 2015-04-23 |  | Discussion | internal |  | Stock | Discussion with SP to explain sto_journey SPs
UZ | Friday | 2015-04-24 | [5 empty] | Free to allocate